## Foglio1
MIDOR REFINERY EXPANSION – ALEXANDRIA, EGYPT ATTACHMENT D.1 TO APPENDIX 8.1 EARLY WORKS OFFICIAL CORRESPONDENCE
Type Correspondance | Company | UNIT | Discipline | Document Code | Document Date | Doc. Description | Note | Action | Expected Date | Response | Response Date
CRS | EARLY WORKS OFFICIAL CORRESPONDENCE LIST | 00 | INSTRUMENTATION | 2544-00-1500-03-B-CRS_0 | 06/04/17 | CLIENT COMMENT TO SITE SURVEY REPORT FOR ESD EQUIPMENTS | REF. T-2572/MIDOR-TPIT-T-00258 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-1500-05-B-CRS_0 | 06/04/17 | CLIENT COMMENT TO SITE SURVEY REPORT FOR F&G EQUIPMENTS | REF. T-2572/MIDOR-TPIT-T-00258 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-CN-0410-01-1-CRS_0 | 30/11/17 | CLIENT COMMENTS TO CN REACTOR 08-R-01 | REF:T-02796/MIDOR-TPIT-T-00418 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-CN-0410-02-1-CRS_0 | 30/11/17 | CLIENT COMMENTS TO CN REACTOR 08-R-02 | REF:T-02796/MIDOR-TPIT-T-00418 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-CN-0410-03-0-CRS_0 | 30/11/17 | CLIENT COMMENTS TO CN REACTOR 07-R-01 | REF:T-02796/MIDOR-TPIT-T-00418 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-CN-0410-04-0-CRS_0 | 30/11/17 | CLIENT COMMENTS TO CN REACTOR 05-V-51 | REF:T-02796/MIDOR-TPIT-T-00418 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1621-01-1-CRS_0 | 10/03/16 | CLIENT COMMENTS TO ELECTRICAL CABLE SIZING | REF:T-0884/MIDOR-TPIT-E-2016-03-10_14-17
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1626-01-A-CRS_0 | 03/05/16 | CLIENT COMMENTS TO ELECTRICAL POWER BALANCE | REF:T-1677/MIDOR-TPIT-E-2016-05-03_17-34 | TPIT RESPONSE REQUIRED |  | 2544-00-CN-1626-01-A-CRS-REPLY_0 TPIT-MIDOR-E-01586 | 13/05/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1626-01-A-CRS_1 | 16/05/16 | CLIENT COMMENTS TO ELECTRICAL POWER BALANCE | REF.:2544-00-CN-1626-01-A-CRS-REPLY_0 | TPIT RESPONSE REQUIRED |  | 2544-00-CN-1626-01-A-CRS-REPLY_1/TPIT-MIDOR-E-01622 | 19/05/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1626-01-A-CRS-REPLY_0 | 13/05/16 | TPIT REPLY TO CLIENT COMMENTS TO ELECTRICAL POWER BALANCE | REF:2544-00-CN-1626-01-A-CSR_0/-E-01586 | OWNER RESPONSE REQUIRED |  | 2544-00-CN-1626-01-A-CSR_1/MIDOR-TPIT-E-2016-05-16_18-14 | 16/05/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1626-01-A-CRS-REPLY_1 | 19/05/16 | TPIT REPLY TO CLIENT COMMENTS TO ELECTRICAL POWER BALANCE | REF:2544-00-CN-1626-01-A-CSR_1/-E-01622
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1626-01-B CRS-REPLY_0 | 10/08/16 | TPIT REPLY TO CLIENT COMMENTS TO HYDRAULIC STUDY | REF: T-2287/TPIT-MIDOR-E-2077 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1626-01-B-CRS_0 | 23/07/16 | CLIENT COMMENTS TO ELECTRICAL POWER BALANCE | REF:T-2287/MIDOR-TPIT-E-2016-08-10_21-18 | TPIT RESPONSE REQUIRED |  | 2544-00-CN-1626-01_B CRS-REPLY_0 TPIT-MIDOR-E-02077 | 10/08/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-CN-1626-01-B-CRS_1 | 24/02/17 | CLIENT COMMENTS TO HYDRAULIC STUDY | REF: T-2287/TPIT-E-2077/MIDOR-T-00189 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PROCESS | 2544-00-CN-1901-01-A-CRS_0 | 27/03/16 | CLIENT COMMENTS TO UNIT 00 - HYDRAULIC STUDY FOR FIRE WATER NETWORK | REF:T-1045/MIDOR-TPIT-E-2016-03-27_21-26 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01268/2544-00-CN-1901-01-A-CSR-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | PROCESS | 2544-00-CN-1901-01-A-CRS_1 | 27/03/16 | CLIENT COMMENTS TO UNIT 00 - HYDRAULIC STUDY FOR FIRE WATER NETWORK | REF:T-1045/MIDOR-TPIT-E-2016-03-29_13-49 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01268/2544-00-CN-1901-01-A-CSR-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | PROCESS | 2544-00-CN-1901-01-A-CRS_2 | 04/04/16 | CLIENT COMMENTS TO UNIT 00 - HYDRAULIC STUDY FOR FIRE WATER NETWORK | REF:2544-00-CN-1901-01-A-CRS-REPLY_0 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01284/2544-00-CN-1901-01-A-CRS-REPLY_1 | 04/04/16
CRS | MIDOR | 00 | PROCESS | 2544-00-CN-1901-01-A-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS TO HYDRAULIC STUDY | REF:2544-00-CN-1901-01-A-CSR_0/1/E-01268 | OWNER RESPONSE REQUIRED |  | 2544-00-CN-1901-01-A-CRS_2 MIDOR-TPIT-E-2016-04-04_08-18 | 04/04/16
CRS | MIDOR | 00 | PROCESS | 2544-00-CN-1901-01-A-CRS-REPLY_1 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO HYDRAULIC STUDY | REF:2544-00-CN-1901-01-A-CSR_2/-E-01284
CRS | MIDOR | 00 | PROCESS | 2544-00-CN-1901-02-A-CRS_0 | 14/06/16 | CLIENT COMMENTS TO FLARE STUDY | REF:ED-01641/MIDOR-TPIT-T-00018 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-DL-0910-402-A-CRS_0 | 27/06/16 | CLIENT COMMENTS TO DEVIATION LIST FOR VERTICAL SULPHUR PUMPS (2544-00-MR-0910-402) | REF:ED-0032/MIDOR-TPIT-T-00022 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-DL-1013-201-A-CRS_0 | 13/06/16 | CLIENT COMMENTS TO DEVIATION LIST FOR INTEGRALLY GEARED CENTRIFUGAL AIR COMPRESSOR | REF:T-1739/MIDOR-TPIT-E-2016-06-13_13-07
CRS | MIDOR | 00 | PACKAGES | 2544-00-DL-4123-01-A-CRS_0 | 01/09/16 | CLIENT COMMENTS TO DEVIATION LIST FOR ELECTRICITY DIESEL GENERATOR | REF:MIDOR-TPIT-T-00057
CRS | MIDOR | 00 | PIPING | 2544-00-DW-0051-01-01-A-CRS_0 | 05/05/16 | CLIENT COMMENTS TO UNIT 00 OVERALL PLOT PLAN | REF:T-0666/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-00-DW-0051-01-01-A-CRS-REPLY_0 | 08/06/16
CRS | MIDOR | 00 | PIPING | 2544-00-DW-0051-01-01-A-CRS-REPLY_0 | 08/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 OVERALL PLOT PLAN | REF:E-2088/2089/2544-00-DW-0051-CRS_0
CRS | MIDOR | 00 | PIPING | 2544-00-DW-0051-01-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO OVERALL PLOT PLAN | REF.:T-0666/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-01-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA 1 | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-01-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA 1 | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-02-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA 2 | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-02-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA 2 | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-03-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA 3 (M4 AND M5) | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-03-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA 3 (M4 AND M5) | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-04-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION SECTIONS AND DETAILS | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-02-04-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION SECTIONS AND DETAILS | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-03-01-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION ACCESS ROAD | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-03-01-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION ACCESS ROAD | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-03-02-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION ACCESS ROAD | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-03-02-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION ACCESS ROAD | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-03-03-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION ACCESS ROAD | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-03-03-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION ACCESS ROAD | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-04-01-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION FREE ZONE - NEW ACCESS | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-04-01-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION FREE ZONE - NEW ACCESS | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-05-01-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA H | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1421-05-01-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION AREA H | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-02-01-B-CRS_0 | 18/03/16 | CLIENT COMMENTS TO MAJOR UNDERGROUND LAYOUT INTERCONNECTING TO WWT | REF:T-1095/MIDOR-TPIT-E-2016-03-18_17-58 | TPIT RESPONSE REQUIRED |  | 2544-00-DW-1442-02-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02202 | 30/09/16
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-02-01-B-CRS_1 | 11/10/16 | CLIENT COMMENTS TO MAJOR UNDERGROUND LAYOUT INTERCONNECTING TO WWT | REF:E-2202/MIDOR-TPIT-T-00079 |  |  | CLOSED | 11/10/16
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-02-01-B-CRS-REPLY_0 | 30/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MAJOR UNDERGROUND LAYOUT INTERCONNECTING TO WWT | REF:E-2202/2544-00-DW-1442-02-01-B-CRS_0 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-04-01-B-CRS_0 | 13/03/17 | CLIENT COMMENTS TO CONCEPTUAL OVERALL MAJOR ELECTRICAL INTERCONNECTING | REF:T-00365/MIDOR-TPIT-T-00214 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-04-01-C-CRS_0 | 24/03/16 | CLIENT COMMENTS TO CONCEPTUAL OVERALL MAJOR ELECTRICAL INTERCONNECTING | REF:T-1105/MIDOR-TPIT-T-00092 | TPIT RESPONSE REQUIRED |  | 2544-00-DW-1442-04-01-C-CRS-REPLY_0 TPIT-MIDOR-E-02241 | 07/10/16
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-04-01-C-CRS-REPLY_0 | 07/10/16 | TPIT REPLY TO CLIENT COMMENTS TO CONCEPTUAL OVERALL MAJOR ELECTRICAL INTERCONNECTING | REF:MIDOR-TPIT-T-0092/TPIT-MIDOR-E-02241 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-04-02-A-CRS_0 | 24/03/16 | CLIENT COMMENTS TO OVERALL MAJOR ELECTRICAL INTERCONNECTING ROUTING TO REVAMPING AREA | REF:T-1105 | TPIT RESPONSE REQUIRED |  | 2544-00-DW-1442-04-02-A-CRS-REPLY_0 TPIT-MIDOR-E-02241 | 07/10/16
CRS | MIDOR | 00 | CIVIL | 2544-00-DW-1442-04-02-A-CRS-REPLY_0 | 07/10/16 | TPIT REPLY TO CLIENT COMMENTS TO OVERALL MAJOR ELECTRICAL INTERCONNECTING ROUTING TO REVAMPING AREA | REF:T-1105/TPIT-MIDOR-E-02241 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-DW-1572-02-01-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - INSTRUMENT DRAWING | REF:T-0790/MIDOR-TPIT-E-2016-03-03_13-05
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-DW-1572-02-01-A-CRS_1 | 06/02/17 | CLIENT COMMENTS TO UNIT 00 - INSTRUMENT DRAWING | REF:T-0790/MIDOR-TPIT-T-00171
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-DW-1572-02-03-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - INSTRUMENT DRAWING | REF:T-0790/MIDOR-TPIT-E-2016-03-03_13-05
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-DW-1572-02-04-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - INSTRUMENT DRAWING | REF:T-0790/MIDOR-TPIT-E-2016-03-03_13-05
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-DW-1576-08-A-CRS_0 | 01/08/16 | CLIENT COMMENTS TO TYPICAL ELECTRICAL HOOK-UP SUMMARY COVER SHEET | REF:T-2217/MIDOR-TPIT-E-2016-08-01_14-08
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1612-01-01-A-CRS_0 | 13/10/16 | CLIENT COMMENTS TO UNITS 00 MAIN GROUNDING LAYOUT | REF.:TPIT-MIDOR-T-00091 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1612-01-01-A-CRS-REPLY_0 | 08/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNITS 00 MAIN GROUNDING LAYOUT | REF:E-2203/2544-00-DW-1612-01-01-A-CRS_0
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-01-01-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 00 - MAIN CABLE ROUTING | REF:T-0799/MIDOR-TPIT-E-2016-03-05_08-22
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-01-01-A-CRS_1 | 06/09/17 | CLIENT COMMENTS TO UNIT 00 - MAIN CABLE ROUTING | REF:T-0799/MDR-T-E-2016-03-05_08-22/T388 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-01-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL MAIN CABLE ROUTING | REF:T-0909/MIDOR-TPIT-E-2016-03-16_12-06 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-1150/2544-00-DW-1622-02-01-A-CRS_0 | 17/03/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL MAIN CABLE ROUTING | REF:T-0909/MIDOR-TPIT-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-01-A-CRS-REPLY_0 | 17/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - ELECTRICAL MAIN CABLE ROUTING | REF:2544-00-DW-1622-02-01-A-CRS_0/E-1150
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-01-B-CRS_0 | 17/04/16 | CLIENT COMMENTS TO UNIT 02-03-04 - H.D.T. NAPHTHA SPLITTER - CATALYTIC REFORMING - ELECTRICAL MAIN CABLE ROUTING | REF:T-1459/MIDOR-TPIT-E-2016-04-17_05-50 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01450/2544-00-DW-1622-02-01-B-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-01-B-CRS_1 | 01/01/17 | CLIENT COMMENTS TO UNIT 02-03-04 - ELECTRICAL MAIN CABLE ROUTINGS | REF:T-1459/MIDOR-T-00161 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-01-B-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02-03-04 - ELECTRICAL MAIN CABLE ROUTINGS | REF:T-1459/MIDOR-TPIT-E-2016-04-21_17-17
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-02-A-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNITS 05, 06, 12, 16, & 39 ELECTRICAL MAIN CABLE ROUTING |  | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01151/2544-00-DW-1622-02-02-A-CRS-REPLY_0 | 18/03/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-02-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNITS 05, 06, 12, 16, & 39 ELECTRICAL MAIN CABLE ROUTING | REF:T-00879/MIDOR-TPIT-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-02-02-A-CRS-REPLY_0 | 18/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNITS 05, 06, 12, 16, & 39 ELECTRICAL MAIN CABLE ROUTING | REF:2544-00-DW-1622-02-02-A-CRS_0/E-1151
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-03-01-A-CRS_0 | 18/03/16 | CLIENT COMMENTS TO UNIT 36, 37, 38, 41, 42, 43& 44 ELECTRICAL MAIN CABLE ROUTINGS | REF:T-0991/MIDOR-TPIT-E-2016-03-19_07-01 | TPIT RESPONSE REQUIRED |  | 2544-00-DW-1622-03-A-CRS-REPLY_0 TPIT-MIDOR-E-02201 | 22/03/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-03-01-B-CRS_0 | 17/04/16 | CLIENT COMMENTS TO UNIT 36, 37, 38, 41, 42, 43& 44 ELECTRICAL MAIN CABLE ROUTINGS | REF:T-1434/MIDOR-TPIT-E-2016-04-17_05-51 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01451/2544-00-DW-1622-03-01-B-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-03-01-B-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 36, 37, 38, 41, 42, 43& 44 ELECTRICAL MAIN CABLE ROUTINGS | REF:E-1451/2544-00-DW-1622-03-01-B-CRS_0
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-03-A-CRS_0 | 13/10/16 | CLIENT COMMENTS TO ELECTRICAL MAIN CABLE U36-37-38-41-42-43-44 | REF:MIDOR-TPIT-T-00090 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-03-A-CRS_1 | 17/11/16 | CLIENT COMMENTS TO UNIT 36, 37, 38, 41, 42, 43& 44 ELECTRICAL MAIN CABLE ROUTINGS | REF.:T-00991/TPIT-E-02201/MIDOR-T-00126 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-03-A-CRS-REPLY_0 | 22/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 36, 37, 38, 41, 42, 43& 44 ELECTRICAL MAIN CABLE ROUTINGS | REFE-02201/2544-00-DW-1622-03-01-A-CRS_0
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-01-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810/MIDOR-TPIT-E-2016-03-05_08-20
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810/MIDOR-TPIT-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-01-A-CRS-2 | 2018-02-18 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810/MIDOR TPIT-T-00445 | CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-01-A-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810/TPIT-E- | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-01-A-CRS-REPLY_1 | 2018-02-18 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810 | OWNER RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-00-DW-1622-04-01-A-CRS_2 | 2018-02-18
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-02-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810/MIDOR-TPIT-E-2016-03-05_08-20
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-02-A-CRS_2 | 2018-02-18 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810/MIDOR-TPIT-T-00445 | OWNER RESPONSE REQUIRED |  | APPROVED/CLOSED | 2018-02-18
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-04-02-A-CRS-REPLY_1 | 2018-02-18 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - ELECTRICAL DRAWINGS | REF:T-0810 | OWNER RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-00-DW-1622-04-02-A-CRS_2 | 2018-02-18
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-05-01-A-CRS_0 | 18/03/16 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL MAIN CABLE ROUTING | REF:T-1076/MIDOR-TPIT-E-2016-03-19_07-00
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1622-05-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL MAIN CABLE ROUTING | REF:T-1076/MIDOR-T-00161
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1652-11-01-B-CRS-REPLY_0 | 13/10/16 | TPIT REPLY TO CLIENT COMMENTS TO MAIN ONE LINE DIAGRAM SS 1
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1652-99-01-B-CRS_0 | 27/07/16 | CLIENT COMMENTS TO MAIN ONE LINE DIAGRAM FOR TEMPORARY ELECTRICAL POWER (TCF+CONTRUCTION AREAS) | REF:T-2263/MIDOR-TPIT-E-2016-07-31_15-48 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02034/2544-00-DW-1652-99-01-B-CRS-REPLY_0 | 03/08/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1652-99-01-B-CRS_1 | 08/08/16 | CLIENT COMMENTS TO MAIN ONE LINE DIAGRAM FOR TEMPORARY ELECTRICAL POWER (TCF+CONTRUCTION AREAS) | REF:2544-00-DW-1652-99-01-B-CRS_1 | TPIT RESPONSE REQUIRED |  | 2544-00-DW-1652-99-01-B -CRS-REPLY_1 | 08/08/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1652-99-01-B-CRS-REPLY_0 | 03/08/16 | TPIT REPLY TO CLIENT COMMENTS TO MAIN ONE LINE DIAGRAM FOR TEMPORARY ELECTRICAL POWER (TCF+CONTRUCTION AREAS) | REF:E-2034/2544-00-DW-1652-99-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-00-DW-1652-99-01-B-CRS_1 / MIDOR-TPIT-E-2016-08-08_09-09 | 08/08/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1652-99-01-B-CRS-REPLY_1 | 08/08/16 | TPIT REPLY TO CLIENT COMMENTS TO MAIN ONE LINE DIAGRAM FOR TEMPORARY ELECTRICAL POWER (TCF+CONTRUCTION AREAS) | REF:2544-00-DW-1652-99-01-B-CRS_1 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1663-01-A-CRS_0 | 13/10/16 | CLIENT COMMENTS TO ELECTRICAL AND CONTROL SYSTEM | REF:MIDOR-TPIT-T-00090 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-DW-1663-01-A-CRS_1 | 06/09/17 | CLIENT COMMENTS TO ELECTRICAL MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM-ECMS | REF:T-0405/MIDOR-TPIT-T-00388 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO OVERALL MAIN FIREFIGHTING LAYOUT | TPIT-MIDOR-T-0999/MIDOR-TPIT-T-00014
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION GENERAL LAYOUT | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION GENERAL LAYOUT | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-B-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - TCF AREAS LAYOUT | REF:T-0834/MIDOR-TPIT-E-2016-03-03_09-20 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01069 2544-00-DW-8200-01-01-B-CRS-REPLY_0 | 04/03/16
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-B-CRS_1 | 08/03/16 | CLIENT COMMENTS TO UNIT 00 - TCF AREAS LAYOUT | REF:E-1069/MIDOR-TPIT-E-2016-03-09_21-19
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-B-CRS-REPLY_0 | 04/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - TCF AREAS LAYOUT | REF:E-1069/2544-00-DW-8200-01-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-00-DW-8200-01-01-B-CRS_1 | 08/03/16
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-D-CRS_0 | 04/04/17 | CLIENT COMMENTS TO UNIT 00 - TCF AREAS LAYOUT | REF:T-1913/MIDOR-TPIT-T00247 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-D-CRS_1 | 05/04/17 | CLIENT COMMENTS TO UNIT 00 - TCF AREAS LAYOUT | REF:T-1913/MIDOR-T00247/MIDOR-T00255 |  |  | 2544-00-DW-8200-01-01-D-CRS-REPLY_1 TPIT-MIDOR-E-02856 | 06/04/17
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-D-CRS_2 | 31/05/17 | CLIENT COMMENTS TO UNIT 00 - TCF AREAS LAYOUT | REF:T-1913/MDR-T-255/TPIT-E-2856/T-334 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-01-01-D-CRS-REPLY_1 | 06/04/17 | CLIENT COMMENTS TO UNIT 00 - TCF AREAS LAYOUT | REF:T-1913/MIDOR-T00255/TPIT-E-02856 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-02-01-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION TEMPORARY CONSTRUCTON FACILITIES TEMPORARY INSTALLATION | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8200-02-01-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION TEMPORARY CONSTRUCTON FACILITIES TEMPORARY INSTALLATION | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8260-01-01-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION TEMPORARY UTILITIES LAYOUT | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8260-01-01-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION TEMPORARY UTILITIES LAYOUT | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8260-01-01-D-CRS_0 | 30/07/16 | CLIENT COMMENTS TO TEMPORARY UTILITIES LAYOUT | REF:T-2323/MIDOR-TPIT-E-2016-08-02_09-31
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8260-01-02-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION OFFICE AREA UTILITIES LAYOUT | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8260-01-02-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION OFFICE AREA UTILITIES LAYOUT | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8260-01-03-0-CRS_0 | 07/06/17 | CLIENT COMMENTS TO TCF SITE PREPARATION OFFICE AREA UTILITIES LAYOUT | REF:T-2611/MDR-TPIT-T-00342 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-DW-8260-01-03-0-CRS_1 | 12/07/17 | CLIENT COMMENTS TO TCF SITE PREPARATION OFFICE AREA UTILITIES LAYOUT | REF:T-2611/MDR-TPIT-T-00362 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-EL-001-4-CRS_0 | 14/07/17 | CLIENT COMMENTS TO ITEM INDEX | REF:T-2621/MIDOR-TPIT-T-00365 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-EL-001-4-CRS_1 | 18/07/17 | CLIENT COMMENTS TO ITEM INDEX | REF:T-2621/MDR-TPIT-T-00365/369 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-EL-001-4-CRS-REPLY-U11_0 | 30/10/17 | TPIT REPLY TO CLIENT COMMENT TO ITEM INDEX REV 4 UNIT11 | REF:T-2621/TPIT-MIDOR-E-03451 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-EL-001-4-CRS-U11_0 | 30/10/17 | CLIENT COMMENT TO ITEM INDEX REV 4 UNIT11 | REF:T-2621/MIDOR-TPIT-E-2017-10-27_15-14 | CLOSED |  | 2544-00-EL-001-4-CRS-REPLY-U11_0 TPIT-MIDOR-E-03451 | 30/10/17
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-EL-001-4-U11-CRS-REPLY_0 | 31/10/17 | TPIT REPLY TO CLIENT COMMENT TO ITEM INDEX REV 4 UNIT11 | REF:T-2621/TPIT-MIDOR-E-03451 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITB-0110-R01-CRS_0 | 15/09/16 | CLIENT COMMENTS TO OFFER FOR FIRED HEATER REVAMPING | REF: MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITB-0150-101-CRS-REPLY_1 | 02/03/17 | TPIT REPLY TO CLIENT COMMENTS TO AUXILIARY STEAM BOILER | REF: MOM-00082/E-02709 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITB-0910-R01-CRS_0 | 12/09/16 | CLIENT COMMENTS TO OFFER 16-ES-0800-U_REV6 | REF.: MIDOR-TPIT-T-00029
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITB-0910-R03-0-CRS_0 | 08/09/16 | CLIENT COMMENTS TO SUNSTRAD OFFER P-16049-EG (REVAMP) | REF.: MIDOR-TPIT-T-00022 | CLOSED |  | TPIT-MIDOR-MOM-00129 - APPROVED/CLOSED | 27/02/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITB-0910-R03-0-CRS-REPLY_0 | 27/02/17 | TPIT REPLY CLIENT COMMENTS TO SUNSTRAD OFFER P-16049-EG (REVAMP) | REF.:TPIT-MIDOR-MOM-00129 | CLOSED |  | APPROVED/CLOSED | 27/02/17
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-ITB-1515-003-A-CRS_0 | 02/08/16 | CLIENT COMMENTS TO GE 2ND OFFER MMS SYSTEM |  | TPIT RESPONSE REQUIRED |  | 2544-00-ITB-1515-003-A-CRS-REPLY_0 TPIT-MIDOR-E-02047 | 05/08/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-ITB-1515-003-A-CRS_1 | 09/09/16 | CLIENT COMMENTS TO GE 2ND OFFER MMS SYSTEM | REF. MIDOR-TPIT-T-00023 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02108/2544-00-ITB-1515-003-A-CRS-REPLY_1 DTD 03/10/2016/TPIT-MIDOR-E-02206 | 09/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-ITB-1515-003-A-CRS-REPLY_0 | 05/08/16 | TPIT REPLY TO CLIENT COMMENTS GE 2ND OFFER MMS SYSTEM | REF.: TPIT-MIDOR-E-02047
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-ITB-1515-003-A-CRS-REPLY_1 | 03/10/16 | TPIT REPLY TO CLIENT COMMENTS TO GE 2ND OFFER MMS SYSTEM | REF: E-2206/2544-00-ITB-1515-003-A-CRS_1 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITB-4141-201-CRS_0 | 15/09/16 | CLIENT COMMENTS TO OFFERS FOR DESALTER PACKAGES | REF: MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0110-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO INSEPCTION AND TEST PLAN FOR FIRED HEATERS | REF:T-0158/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0110-R01-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR FIRED HEATER REVAMPING | REF:T-0675/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0127-401-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR INCINERATOR STEAM SUPERHEATER | REF.: MIDOR-TPIT-T-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0150-101-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO ITP FOR AUXILIARY STEAM BOILER | REF:T-0271/MIDOR-TPIT-E-2016-07-31_16-44 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0150-101-A-CRS-REPLY_0 | 02/03/17 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN STEAM BOILERS | REF: MOM-00082/E-02709/T-00271 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0168-401-A-CRS_0 | 21/07/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR THERMAL REACTOR REQUISITION | REF. MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0172-401-A-CRS_0 | 06/10/16 | CLIENT COMMENTS TO TO INSPECTION AND TEST PLAN FOR STACK | REF.: MIDOR-TPIT-T-00077 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0172-401-A-CRS_1 | 14/10/16 | CLIENT COMMENTS TO TO INSPECTION AND TEST PLAN FOR STACK | REF.: MIDOR-TPIT-T-00097 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0182-101-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR DERRICK SUPPORTED ELEVATED FLARE | REF.T-00892/MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0191-401-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR THERMAL REACTOR BURNER | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ITP-0191-402-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR INCINERATOR BURNERS | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-0210-101-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR DEMINERALIZATION AND ULTRAFILTRATION PACKAGE | REF:T-1497/MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-0310-201-B-CRS_0 | 13/06/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-201 | REF:T-1888/MIDOR-TPIT-E-2016-06-13_13-06 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-0310-201-B-CRS_1 | 02/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-201 | REF:T-1888/MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED |  | 2544-00-ITP-0310-201-B-CRS-REPLY_0 | 17/10/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-0310-201-B-CRS-REPLY_0 | 17/10/16 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR COOLING TOWER | REF: 2544-00-ITP-0310-201-B-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00105 DTD 08/02/2017
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0411-101-A-CRS_0 | 30/05/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR LOW ALLOY REACTORS | REF:T-0045/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0411-101-A-CRS-REPLY_0 | 01/09/16 | TPIT-REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR LOW ALLOY REACTORS | REF:T-0045/TPIT-MIDOR-T-MOM-00078
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0470-101-A-CRS_0 | 06/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF.: MIDOR-TPIT-T-00024 | TPIT RESPONSE REQUIRED |  | 2544-00-ITP-0470-101-A-CRS-REPLY_0/TPIT-MIDOR-E-2171 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0470-101-A-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF. E-2171/2544-00-ITP-0470-101-A-CRS_0 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0511-001-A-CRS_0 | 01/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-00155 | TPIT RESPONSE REQUIRED |  | 2544-00-ITP-0511-001-A-CRS-REPLY_0 TPIT-MIDOR-MOM-00083 | 27/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0511-001-A-CRS-REPLY_0 | 27/09/16 | TPIT REPLY CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-00155/TPIT-MIDOR-MOM-00083
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0511-01-A-CRS_0 | 25/05/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0155/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0570-001-A-CRS_0 | 18/08/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR PROPRIETARY INTERNAL FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0233/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0570-002-A-CRS_0 | 19/08/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR INTERNALS FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0159/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0610-001-A-CRS_0 | 26/05/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:TPIT-MIDOR-T-00162/PMC-MIDOR-E-0052 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02023/2544-00-ITP-0610-001-A-CRS-REPLY_0 | 01/08/16
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0610-001-A-CRS_1 | 26/05/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:ED-0019-M-T-0162/MIDOR-TPIT-T-00013 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0610-001-A-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:E-2023/2544-00-ITP-0610-001-A-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00091 DTD 07/07/2017
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0610-103-A-CRS_0 | 31/05/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR HIGH PERFORMANCE TUBES FOR HEAT EXCHANGERS | REF.:T-234/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0610-403-A-CRS_0 | 29/06/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR SULPHUR CONDENSERS | REF:ED-0025/MIDOR-TPIT-T-00017 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0710-001-A-CRS_0 | 06/07/16 | CLIENT COMMENTS TO INSPECTION AND ACTIVITY PLAN FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-00566/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0710-001-A-CRSREPLY_0 | 15/09/16 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND ACTIVITY PLAN FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/MIDOR-T-00020/MOM-00097
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0811-101-A-CRS_0 | 01/06/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR HP PRESSURE VESSELS | REF:T-0052/MIDOR-TPIT-T-00013
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-0811-101-A-CRS-REPLY_0 | 30/09/16 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR HP PRESSURE VESSELS | REF:T-0052/M-TPIT-T-13/T-MIDOR-E-02195 | CLOSED |  | CLOSED WITH 2544-00-TPIT-MIDOR-MOM-00086 DTD 09/02/2017
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-0851-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR VACUUM UNIT PACKAGE | REF: T-00157/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-0910-402-A-CRS_0 | 27/06/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR VERTICAL SULPHUR PUMPS (2544-00-MR-0910-402) | REF:ED-0032/MIDOR-TPIT-T-00022 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-0910-402-A-CRS-REPLY_0 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR VERTICAL SULPHUR PUMPS | REF.: TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-0920-001-A-CRS_0 | 18/07/16 | CLIENT COMMENTS TO INSPECFTION AND TEST PLAN (ITP) FOR RECIPROCATING PUMPS | REF:T-01013/MIDOR-TPIT-T-00040
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-0931-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR PROPORTIONING PUMPS | REF:T-00257/MIDOR-TPIT-T-00064 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-1011-101-A-CRS_0 | 19/03/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR CENTRIFUGAL COMPRESSORS | REF.T-0173/MIDOR-TPIT-E-2016-03-22_22-38
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-1013-201-A-CRS_0 | 02/06/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR INTEGRALLY GEARED AIR COMPRESSORS | REF:T-00312/MIDOR-TPIT-T-00022
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-1020-001-A-CRS_0 | 10/06/16 | CLIENT COMMENTS TO ITP RECIPROCATING COMPRESSORS | REF:T-0145/PMC-MIDOR-E-0059 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-1020-001-A-CRS-REPLY_0 | 10/06/16 | TPIT REPLY TO CLIENT COMMENTS TO ITP RECIPROCATING COMPRESSORS | REF:2544-00-ITP-1020-001-A-CRS_0/E-02148
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-1031-101-A-CRS_0 | 26/05/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR ROTARY SCREW COMPRESSORS | REF:T-1073/MIDOR-TPIT-T-00012 |  |  | 2544-00-ITP-1031-101-0-CRS-REPLY_0 TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-1031-101-A-CRS-REPLY_0 | 23/12/16 | TPIT-REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR ROTARY SCREW COMPRESSORS | REF:T-1073/MIDOR-T-0012/TPIT-E-2539 | CLOSED |  | TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-ITP-1040-402-A-CRS-REPLY_1 | 04/04/17 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR COMBUSTION AIR BLOWERS | REF: TPIT-MIDOR MOM-00139 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-ITP-2520-101-A-CRS-REPLY_1 | 02/02/17 | TPIT REPLY TO CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR STORAGE TANKS ASSEMBLED ON SITE | REF: T-00413/TPIT-MIDOR MOM-00136 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-4110-101-A-CRS_0 | 06/10/17 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR MODULAR LPG TREATMENT UNIT (UNIT 25) | REF:T-02710/MIDOR-TPIT-T-00406
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-4111-001-A-CRS_0 | 29/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR PSA UNIT | REF.: T-0417/MIDOR-TPIT-T-00068
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-4123-01-A-CRS_0 | 01/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR ELECTRICITY DIESEL GENERATOR | REF:MIDOR-TPIT-T-00057
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-4141-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN (ITP) FOR DESALTER PACKAGES | REF:T-0174/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | PACKAGES | 2544-00-ITP-4171-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO INSPECTION AND TES PLAN (ITP) FOR INSTRUMENT AIR DRYING PACKAGE | REF: T-00255/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-01-A-CRS_0 | 19/05/16 | CLIENT COMMENTS TO UNIT 00 BASIC DESIGN DATA | REF.:TPIT-MIDOR-T-00154/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-0001-01-A-CRS-REPLY_0 | 07/07/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-01-A-CRS_1 | 15/07/16 | CLIENT COMMENTS TO UNIT 00 BASIC DESIGN DATA | REF.:MIDOR-T-00154/MIDOR-TPIT-T-00055 |  |  | 2544-00-JSD-0001-01-A-CRS-REPLY_1/TPIT-MIDOR-E-02179 | 28/09/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-01-A-CRS-REPLY_0 | 07/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 BASIC DESIGN DATA | REF.:TPIT-MIDOR-T-00154 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-0001-01-A-CRS_1 | 15/07/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-01-A-CRS-REPLY_1 | 28/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 BASIC DESIGN DATA | REF.: E-2179/2544-00-JSD-0001-01-A-CRS_1
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-0-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.T-1984/MIDOR-TPIT-E-2016-06-09_22-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01857/2544-00-JSD-0001-02-0-CRS-REPLY_0 | 23/06/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-0-CRS-REPLY_0 | 23/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.E-1857/2544-00-JSD-0001-02-0-CRS_0
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-A-CRS_0 | 24/03/16 | CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.T-0831/MIDOR-TPIT-E-2016-03-25_08-39 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01484/2544-00-JSD-0001-02-A-CRS_0 | 27/04/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-A-CRS_1 | 28/04/16 | CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.T-831/MIDOR-TPIT-E-2016-04-28_13-51 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01517/2544-00-JSD-0001-02-A-CRS-REPLY_1 | 04/05/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-A-CRS_2 | 14/05/16 | CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.T-831/MIDOR-TPIT-E-2016-05-16_06-18 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01775/2544-00-JSD-0001-02-A-CRS-REPLY_2 | 10/06/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-A-CRS-REPLY_0 | 27/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.E-1484/2544-00-JSD-0001-02-A-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-28_13-51/2544-00-JSD-0001-02-A-CRS_1 | 28/04/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-A-CRS-REPLY_1 | 04/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.E-1517/2544-00-JSD-0001-02-A-CRS_1 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-05-16_06-18/2544-00-JSD-0001-02-A-CRS-REPLY_2 | 14/05/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-02-A-CRS-REPLY_2 | 10/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF.E-1775/2544-00-JSD-0001-02-A-CRS_2 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-06-12_12-55 | 12/06/16
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-03-A-CRS_0 | 05/05/16 | CLIENT COMMENTS TO UNIT 00 STANDARD SPECIFICATION FOR PID PREPARATION | REF.:TPIT-MIDOR-T-00319/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PROCESS | 2544-00-JSD-0001-03-A-CRS_1 | 18/10/16 | CLIENT COMMENTS TO UNIT 00 STANDARD SPECIFICATION FOR PID PREPARATION | REF.:T-00319/PMC-E-0030/MIDOR-T-00101 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-JSD-0150-01-1-CRS_0 | 12/07/16 | CLIENT COMMENTS TO AUXILIARY STEAM BOILERS DESIGN SPECIFICATION | REF.:T-00590/PMC-MIDOR-E-0080
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-JSD-0150-01-1-CRS_1 | 17/10/16 | CLIENT COMMENTS TO JSD 0150-01 AUXILIARY STEAM BOILER | REF: MIDOR-TPIT-T-00096 | TPIT RESPONSE REQUIRED |  | NOT REQUIRED CRS APPROVAL | 17/10/16
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-JSD-0150-01-1-CRS-REPLY_0 | 10/10/16 | TPIT REPLY TO CLIENT COMMENTS TO JSD 0150-01 AUXILIARY STEAM BOILER | REF:T-00096/TPIT-MIDOR-E-02246 | OWNER RESPONSE REQUIRED |  | NOT REQUIRED CRS APPROVAL | 10/10/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSD-0400-01-2-CRS_0 | 05/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR DESIGN OF PRESSURE AND ATMOSPHERIC EQUIPMENT | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-0400-01-2-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSD-0400-01-2-CRS_1 | 03/11/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR DESIGN OF PRESSURE AND ATMOSPHERIC EQUIPMENT |  | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-JSD-0400-01-2-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB SPECIFICATION FOR DESIGN OF PRESSURE AND ATMOSPHERIC EQUIPMENT | REF.:MIDOR-T-01039/TPIT-MIDOR-E-02166
CRS | MIDOR | 00 | PVHE | 2544-00-JSD-0400-02-1-CRS_0 | 10/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR DESIGN OF ALLOWABLE EXTERNAL LOADS FOR PRESSURE AND ATMOSPHERIC EQUIPMENT | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSD-0400-02-1-CRS_1 | 03/11/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR DESIGN OF ALLOWABLE EXTERNAL LOADS FOR PRESSURE AND ATMOSPHERIC EQUIPMENT
CRS | MIDOR | 00 | PVHE | 2544-00-JSD-0400-02-1-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR DESIGN OF ALLOWABLE EXTERNAL LOADS FOR PRESSURE AND ATMOSPHERIC EQ. | REF.:MIDOR-T-01039/TPIT-MIDOR-E-02166 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-0400-02-1-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-01-1-CRS_0 | 29/03/16 | CLIENT COMMENTS TO PIPING MATERIAL CLASSES | REF:T-1202/MIDOR-TPIT-E-2016-03-30_06-08 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01239/2544-00-JSD-1300-01-1-CRS-REPLY_0 | 30/03/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-01-1-CRS-REPLY_0 | 29/03/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING MATERIAL CLASSES | REF: E-01239/2544-00-JSD-1300-01-1-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-01-2-CRS_0 | 25/07/16 | CLIENT COMMENTS TO PIPING MATERIAL CLASSES | REF:T-2121/MIDOR-TPIT-E-2016-07-31_08-23 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02135 / 2544-00-JSD-1300-01-2-CRS-REPLY_0 | 19/09/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-01-2-CRS_1 | 27/09/16 | CLIENT COMMENTS TO PIPING MATERIAL CLASSES | REF:T-2121/MIDOR-TPIT-T-00052
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-01-2-CRS-REPLY_0 | 19/09/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING MATERIAL CLASSES | REF:E-2135 / 2544-00-JSD-1300-01-2-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1300-01-2-CRS_1 MIDOR-TPIT-T-00051 (CLOSED) | 27/09/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-02-2-CRS_0 | 05/05/16 | CLIENT COMMENTS TO DESIGN SPECIFICATION FOR PIPING DESIGN | REF.:TPIT-MIDOR-T-01251/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1300-02-2-CRS-REPLY_0 TPIT-MIDOR-E-02088/MOM-0065 | 08/06/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-02-2-CRS-REPLY_0 | 08/06/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING MATERIAL CLASSES | REF: T-1251/TPIT-MIDOR-E-02088/MOM-0065
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-03-2-CRS_0 | 10/05/16 | CLIENT COMMENTS TO DESIGN SPECIFICATION FOR STEAM TRACING SPECIFICATION AND STANDARDS I - BASIC DESIGN SPECIFICATION | REF.:TPIT-MIDOR-T-01358/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-04-1-CRS_0 | 10/05/16 | CLIENT COMMENTS TO DESIGN SPECIFICATION RULES FOR THE DESIGN OF JACKETED PIPING I - BASIC SPECIFICATION | REF.:TPIT-MIDOR-T-00392/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-08-1-CRS_0 | 10/05/16 | CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR PIPING STRESS ANALYSIS | REF.:TPIT-MIDOR-T-00411/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1300-08-1-CRS-REPLY_0 TPIT-MIDOR-E-02176 | 14/06/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-08-1-CRS_1 | 03/10/16 | CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR PIPING STRESS ANALYSIS | REF.:TPIT-MIDOR-T-00411 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1300-08-1-CRS-REPLY_1 TPIT-MIDOR-E-02230 | 06/10/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-08-1-CRS_2 | 11/10/16 | CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR PIPING STRESS ANALYSIS | REF.:TPIT-MIDOR-T-00411/MIDOR TPIT-T-86
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-08-1-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR PIPING STRESS ANALYSIS | REF:TPIT-MIDOR-T-0411/TPIT-MIDOR-E-02176
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-1300-08-1-CRS-REPLY_1 | 06/10/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR PIPING STRESS ANALYSIS | REF:TPIT-MIDOR-T-0411/TPIT-MIDOR-E-02230
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1400-01-1-CRS_0 | 10/05/16 | CLIENT COMMENTS TO GENERAL DESIGN SPECIFICATION FOR UNDERGROUND SYSTEMS | REF:T-01189/PMC-MIDOR-E-0030 | CLOSED |  | 2544-00-JSD-1400-01-0-CRS-REPLY_0 | 24/06/16
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1400-01-1-CRS-REPLY_0 | 04/02/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL DESIGN SPECIFICATION FOR UNDERGROUND SYSTEMS | REF: T-01194/TPIT-MIDOR-E-2016-02-04 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1410-01-A-CRS_0 | 03/10/16 | CLIENT COMMENTS TO MIDOR REFINERY EXPANSION - GEOTECHNICAL RECOMMENDATION FOR EPC PHASE | REF:T-01712/MIDOR-TPIT-T-00072
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1410-01-A-CRS_1 | 13/10/16 | CLIENT COMMENTS TO MIDOR REFINERY EXPANSION - GEOTECHNICAL RECOMMENDATION FOR EPC PHASE | REF:T-01712/MIDOR-TPIT-T-00089
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1410-01-A-CRS-REPLY_0 | 10/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 GEOTECHNICAL RECOMMENDATION FOR EPC PHASE SPECIFICATION | REF: T-01712/TPIT-MIDOR-E-02244 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1440-01-0-CRS_0 | 27/05/16 | CLIENT COMMENTS TO GEOTECHNICAL RECOMMENDATIN FOR TCF SITE PREPARATION | REF:T-01394/PMC-MIDOR-E-0030 | CLOSED |  | 2544-00-JSD-1440-01-0-CRS-REPLY_0 | 26/06/16
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1440-01-0-CRS-REPLY_0 | 27/05/16 | TPITT REPLY TO CLIENT COMMENTS TO GEOTECHNICAL RECOMMENDATIN FOR TCF SITE PREPARATION | REF:T-01394/PMC-MIDOR-E-0030/MOM-00066_1 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00066_1DTD 07/07/2016
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1501-01-C-CRS_0 | 05/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR DESIGN FOR INSTRUMENTATION NUMBERING | REF.:TPIT-MIDOR-T-00689/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1501-02-B-CRS_0 | 05/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL DESIGN RULES FOR SMARTPLANT INSTRUMENTATION SET UP | REF.:TPIT-MIDOR-T-00689/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1510-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO UNIT 00 CONTROL & SAFETY SYSTEMS PHILOSOPHY | REF.:TPIT-MIDOR-T-0908/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1510-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02147 | 20/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1510-01-0-CRS_1 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 CONTROL & SAFETY SYSTEMS PHILOSOPHY | REF.:TPIT-MIDOR-T-0908/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1510-01-0-CRS_2 | 23/09/16 | CLIENT COMMENTS TO UNIT 00 CONTROL & SAFETY SYSTEMS PHILOSOPHY | REF.:T-0908/MIDOR-TPIT-T-00048
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1510-01-0-CRS-REPLY_0 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS JSD UNIT 00 CONTROL & SAFETY SYSTEMS PHILOSOPHY | REF. TPIT-MIDOR-T-00908/TPIT-MIDOR-E-021 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1510-01-0-CRS_2 MIDOR-TPIT-T-00048 (CLOSED) | 23/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1515-02-A-CRS_0 | 05/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR DESIGN PRELIMINARY ARCHITECTURE FOR SIL RATED SAFETY FUNCTION | REF.:TPIT-MIDOR-T-0689/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1515-02-A-CRS_1 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR DESIGN PRELIMINARY ARCHITECTURE FOR SIL RATED SAFETY FUNCTION | REF.:TPIT-MIDOR-T-0689/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1530-01-0-CRS_1 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 COMMUNICATION STYSTEM DESIGN SPECIFICATION | REF.:TPIT-MIDOR-T-00979/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1530-01-0-CRS-REPLY_1 TPIT-MIDOR-E-02147 | 20/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1530-01-0-CRS_2 | 27/09/16 | CLIENT COMMENTS TO UNIT 00 COMMUNICATION STYSTEM DESIGN SPECIFICATION | REF.:T-00979/MIDOR-TPIT-T-00058
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1530-01-0-CRS-REPLY_0 | 07/04/16 | TPIT REPLY TO CLIENT COMMENTS JSD COMMUNICATION SYSTEM DESIGN SPECIFICATION | TPIT-MIDOR-E-01401
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1530-01-0-CRS-REPLY_1 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS JSD COMMUNICATION STYSTEM DESIGN SPECIFICATION | REF. MIDOR-T-00976/TPIT-MIDOR-E-02147 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1530-01-0-CRS_2 MIDOR-TPIT-T-00058 (CLOSDE) | 27/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1530-01-1-CRS_0 | 03/05/16 | CLIENT COMMENTS TO UNIT 00 COMMUNICATION STYSTEM DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-01517 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1530-01-1-CRS-REPLY_0 TPIT-MIDOR-E-01617 | 19/05/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1530-01-1-CRS-REPLY_0 | 19/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 COMMUNICATION STYSTEM DESIGN SPECIFICATION
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1540-01-0-CRS_0 | 29/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR DESIGN INSTRUMENTATION | REF: TPIT-MIDOR-T-01068 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01418/2544-00-JSD-1540-01-0-CRS-REPLY_0 | 07/04/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1540-01-0-CRS_1 | 25/04/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR DESIGN INSTRUMENTATION | REF: 2544-00-JSD-1540-01-0-CRS-REPLY_0
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1540-01-0-CRS_2 | 05/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR DESIGN INSTRUMENTATION | REF.:TPIT-MIDOR-T-01068/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1540-01-0-CRS-REPLY_1 TPIT-MIDOR-E-02143 | 19/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1540-01-0-CRS_3 | 21/09/16 | CLIENT COMMENTS JOB SPECIFICATION FOR DESIGN INSTRUMENTATION | REF.:MIDOR-T-01068/MIDOR-TPIT-T-0039
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1540-01-0-CRS-REPLY_0 | 07/04/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 - JSD FOR DESIGN INSTRUMENTATION | TPIT-MIDOR-E-01418 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-25_20-00/2544-00-JSD-1540-01-0-CRS_1 | 25/04/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1540-01-0-CRS-REPLY_1 | 19/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 - JSD FOR DESIGN INSTRUMENTATION | TPIT-MIDOR-E-02143 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1540-01-0-CRS_3 MIDOR-TPIT-T-0039 CLOSED | 21/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1560-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR DESIGN FOR ANALYSER SYSTEMS | REF.:TPIT-MIDOR-T-0978/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1560-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02143 | 19/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1560-01-0-CRS_1 | 21/09/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR DESIGN FOR ANALYSER SYSTEMS | REF.:TPIT-MIDOR-T-0978/MIDOR-TPIT-T-0039
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1560-01-0-CRS-REPLY_0 | 19/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 - JOB SPECIFICATION FOR DESIGN FOR ANALYSER SYSTEMS | TPIT-MIDOR-E-02143 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1560-01-0-CRS_1 MIDOR-TPIT-T-0039 CLOSED | 21/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1560-02-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR ANALYZER SHELTERS | REF:T-0874/MIDOR-TPIT-E-2016-03-17_13-43 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01143/2544-00-JSD-1560-02-0-CRS-REPLY_0 | 17/03/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1560-02-0-CRS_1 | 06/05/16 | CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR ANALYZER SHELTERS | REF.:TPIT-MIDOR-T-0874/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1560-02-0-CRS-REPLY_0 | 17/03/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR ANALYZER SHELTERS | REF:2544-00-JSD-1560-02-0-CRS/E-1143 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-03-17_13-43/2544-00-JSD-1560-02-0-CRS_1 | 17/03/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1580-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL DESIGN RULES FOR PACKAGE INSTRUMENTATION AND CONTROL | REF.:TPIT-MIDOR-T-0908/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1580-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02143 | 19/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1580-01-0-CRS_1 | 21/09/16 | CLIENT COMMENTS TO GENERAL DESIGN RULES FOR PACKAGE INSTRUMENTATION AND CONTROL | REF.:TPIT-MIDOR-T-0908/MIDOR-TPIT-T-0039
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSD-1580-01-0-CRS-REPLY_0 | 19/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 - GENERAL DESIGN RULES FOR PACKAGE INSTRUMENTATION AND CONTROL | TPIT-MIDOR-E-02143 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1580-01-0-CRS_1 MIDOR-TPIT-T-0039 CLOSED | 21/09/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-01-2-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSD FOR BASIC SPC | REF.:TPIT-MIDOR-T-00855 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1600-01-2-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-01-2-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 JSD FOR ELECTRICAL DESIGN SPC I BASIC SPC | REF.:TPIT-MIDOR-T-855/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1600-01-2-CRS-REPLY_1 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-01-2-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 JSD FOR ELECTRICAL DESIGN SPC I BASIC SPC | REF.:TPIT-MIDOR-T-855/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-01-2-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSD ELECTRICAL DESIGN SPECIFICATION I-BASIC SPECIFICATIONS | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-01-2-CRS-REPLY_1 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS JSD ELECTRICAL DESIGN SPECIFICATION I-BASIC SPECIFICATIONS | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1600-01-2-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-02-1-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 ELECTRICAL DESIGN SPEC II INSTALLATIN PSC AND DRAWINGS | REF.:TPIT-MIDOR-T-0732/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1600-02-1-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-02-1-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 ELECTRICAL DESIGN SPEC II INSTALLATIN PSC AND DRAWINGS | REF.:TPIT-MIDOR-T-732/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-02-1-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS JSD ELECTRICAL DESIGN SPECIFICATION II-INSTALLATION SPECIFICATION AND DRAWINGS AS PER TEC | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1600-02-1-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-03-1-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM | REF.:TPIT-MIDOR-T-0855/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1600-03-1-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-03-1-CRS_1 | 27/07/16 | CLIENT COMMENTS TO GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM | REF.:TPIT-MIDOR-T-855/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSD-1600-03-1-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS JSD GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1600-03-1-CRS_1 | 27/07/16
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1700-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL DESIGN SPC FOR FOUDNATINS AND CONCRETE WORKS | REF:T-00259/PMC-MIDOR-E-0030 | CLOSED |  | 2544-00-JSD-1700-01-0-CRS-REPLY_0 | 26/09/16
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1700-01-0-CRS-REPLY_0 | 07/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL DESIGN SPC FOR FOUDNATINS AND CONCRETE WORKS | REF:T-00259/PMC-MIDOR-E-0030/MOM-00066_1 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00066_1 DTD 07/07/2016
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1800-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO GENERAL DESIGN SPECIFICATION FOR STEEL STRUCTURES | REF:T-00259/PMC-MIDOR-E-0030 | CLOSED |  | 2544-00-JSD-1800-01-0-CRS-REPLY_0 | 20/06/16
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1800-01-0-CRS_0_REPLY | 05/05/16 | CLIENT COMMENTS TO GENERAL DESIGN SPC FOR FOUDNATINS AND CONCRETE WORKS | REF:T-00259/PMC-MIDOR-E-0030 |  |  | TPIT-MIDOR-MOM-0066 | 07/07/16
CRS | MIDOR | 00 | CIVIL | 2544-00-JSD-1800-01-0-CRS-REPLY_0 | 07/07/16 | TPIT REPLYCLIENT COMMENTS TO GENERAL DESIGN SPECIFICATION FOR STEEL STRUCTURES | REF:T-00259/PMC-MIDOR-E-0030/MOM-00066_1 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00066_1 DTD 07/07/2016
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-0-CRS_0 | 19/04/16 | CLIENT COMMENTS TO UNIT 00 - FIRE FIGHTING SPECIFICATION | REF:T-1457/MIDOR-TPIT-E-2016-04-19_21-10 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01464/2544-00-JSD-1900-01-0-CRS-REPLY_0 | 22/04/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-0-CRS_1 | 24/04/16 | CLIENT COMMENTS TO UNIT 00 - FIRE FIGHTING SPECIFICATION | REF: 2544-00-JSD-1900-01-0-CRS-REPLY_0
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-0-CRS-REPLY_0 | 22/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - FIRE FIGHTING SPECIFICATION | REF: E-01464/2544-00-JSD-1900-01-0-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1900-01-0-CRS_1 | 24/04/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-0-CRS-REPLY_2 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - FIRE FIGHTING SPECIFICATION | TPIT-MIDOR-E-01529
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-B-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - FIRE FIGHTING SPECIFICATION | REF:T-0606/MIDOR-TPIT-E-2016-03-03_10-26 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-01271/2544-00-JSD-1900-01-B-CRS-REPLY_0 | 21/03/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-B-CRS_1 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 FIRE FIGHTING SPECIFICATION | REF.:TPIT-MIDOR-T-0606/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-B-CRS_2 | 30/08/16 | CLIENT COMMENTS TO UNIT 00 FIRE FIGHTING SPECIFICATION | REF.:T-0606/MIDOR-TPIT-T-00004 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02141 | 19/09/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-01-B-CRS-REPLY_0 | 21/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - FIRE FIGHTING SPECIFICATION | REF: 2544-00-JSD-1900-01-B-CRS_0/E-01271
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-03-A-CRS_0 | 30/05/16 | CLIENT COMMENTS TO UNIT 00 SAFETY PROCESS DESIGN CRITERIA | REF.:TPIT-MIDOR-T-01823/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1900-03-A-CRS-REPLY_0 TPIT-MIDOR-E-02197 | 30/09/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-03-A-CRS_1 | 30/08/16 | CLIENT COMMENTS TO UNIT 00 SAFETY PROCESS DESIGN CRITERIA | REF.:-T-01823/MIDOR-TPIT-T-00005
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1900-03-A-CRS-REPLY_0 | 30/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 SAFETY PROCESS DESIGN CRITERIA | REF.:T-01823/MIDOR-TPIT-T-00066
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1950-01-B-CRS_0 | 06/03/16 | CLIENT COMMENTS TO FIRE AND GAS SPECIFICATION | REF:T-0606/MIDOR-TPIT-E-2016-03-08_22-05 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01393/2544-00-JSD-1950-01-B-CRS-REPLY_0 | 14/04/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1950-01-B-CRS_1 | 18/04/16 | CLIENT COMMENTS TO FIRE AND GAS SPECIFICATION | REF: 2544-00-JSD-1950-01-B-CRS-REPLY_0 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01440/2544-00-JSD-1950-01-B-CRS-REPLY_1 | 20/04/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1950-01-B-CRS_2 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 FIRE AND GAS DETECTION AND ALARM SPECIFICATION | REF.:TPIT-MIDOR-T-0606/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1950-01-B-CRS-REPLY_0 | 14/04/16 | TPIT REPLY TO CLIENT COMMENTS TO FIRE AND GAS SPECIFICATION | REF: E-01393/2544-00-JSD-1950-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-00-JSD-1950-01-B-CRS_1 | 18/04/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1950-01-B-CRS-REPLY_1 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO FIRE AND GAS SPECIFICATION | REF: E-01440/2544-00-JSD-1950-01-B-CRS_1
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1980-01-B-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 FIRE PROOFING SPECIFICATION | REF.:TPIT-MIDOR-T-0606/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-1980-01-B-CRS_1 | 08/08/16 | CLIENT COMMENTS TO UNIT 00 FIRE PROOFING SPECIFICATION | REF.:T-0606/MIDOR-TPIT-T-00004 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02141 | 19/09/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-2300-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 JOB DESIGN SPECIFICATION FOR PAINTING | REF.:TPIT-MIDOR-T-0037/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-2300-01-0-CRS_1 | 26/07/16 | CLIENT COMMENTS TO UNIT 00 JOB DESIGN SPECIFICATION FOR PAINTING | REF.:TPIT-MIDOR-T-0037/PMC-MIDOR-E-0080 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-2300-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02222 | 05/10/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-2300-01-0-CRS-REPLY_0 | 05/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 JOB DESIGN SPECIFICATION FOR PAINTING | REF:TPIT-MIDOR-T-0037/TPIT-MIDOR-E-02222
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSD-2300-01-1-CRS_1 | 17/10/16 | CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR PAINTING | REF: MIDOR-TPIT-T-00096 | TPIT RESPONSE REQUIRED |  | NOT REQUIRED CRS APPROVAL | 17/10/16
CRS | MIDOR | 00 | BUILDINGS | 2544-00-JSD-3400-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO DESIGN SPECIFICATION FOR AIR CONDITIONING SYSTEM | REF:T-00915/PMC-MIDOR-E-0030 | CLOSED |  | 2544-00-JSD-3400-01-0-CRS-REPLY_0 | 20/09/17
CRS | MIDOR | 00 | BUILDINGS | 2544-00-JSD-3400-01-0-CRS-REPLY_0 | 07/07/16 | CLIENT COMMENTS TO DESIGN SPECIFICATION FOR AIR CONDITIONING SYSTEM | REF:T-00915/PMC-MIDOR-E-0030/MOM-00066_1 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00066_1 DTD 07/07/2016
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-01-A-CRS_0 | 26/07/16 | CLIENT COMMENTS TO PLANT NOISE CONTROL SPECIFICATION | REF.:TPIT-MIDOR-T-0106/PMC-MIDOR-E-0080
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-01-A-CRS_1 | 02/12/16 | CLIENT COMMENTS TO PLANT NOISE CONTROL SPECIFICATION | REF.:MIDOR-TPIT-T-00139
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-01-A-CRS-REPLY_0 | 17/10/16 | TPIT-REPLY TOCLIENT COMMENTS TO PLANT NOISE CONTROL SPECIFICATION | REF.:T-0106/PMC-E-0080/TPIT-E-02295
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-02-A-CRS_0 | 13/05/16 | CLIENT COMMENTS TO UNIT 00 EQUIPMENT NOISE SPECIFICATION | REF.:TPIT-MIDOR-T-0106/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-02-A-CRS_1 | 26/07/16 | CLIENT COMMENTS TO EQUIPMENT NOISE SPECIFICATION | REF.:TPIT-MIDOR-T-0106/PMC-MIDOR-E-0080
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-02-A-CRS-REPLY_0 | 17/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 EQUIPMENT NOISE SPECIFICATION | REF.:T-0106/PMC-E-0030/TPIT-E-2295
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-03-A-CRS_0 | 26/07/16 | CLIENT COMMENTS TO ACOUSTIC INSULATION FOR PIPES VALES AND FLAGES | REF.:TPIT-MIDOR-T-0106/PMC-MIDOR-E-0080
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-03-A-CRS_1 | 02/12/16 | CLIENT COMMENTS TO ACOUSTIC INSULATION FOR PIPES VALES AND FLAGES | REF.:MIDOR-TPIT-T-00139
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6000-03-A-CRS-REPLY_0 | 17/10/16 | TPIT REPLY TO CLIENT COMMENTS TO ACOUSTIC INSULATION FOR PIPES VALES AND FLAGES | REF.:T-0106/PMC-E-0080/TPIT-E-2295
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-JSD-6200-01-A-CRS_0 | 31/05/16 | CLIENT COMMENTS TO UNIT 00 ENVIRONMENTAL PROTECTION DESIGN CRITERIA | REF.:TPIT-MIDOR-T-01809/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-JSS-0110-01-2-CRS_0 | 28/04/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.:TPIT-MIDOR-T-00966/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-JSS-0110-01-2-CRS-REPLY_0 | 10/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.:T-00966/TPIT-MIDOR-E-02246 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-JSS-0180-01-0-CRS_0 | 28/04/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR FLARE PACKAGE | REF.:TPIT-MIDOR-T-00460/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0400-01-1-CRS_0 | 03/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR SUPPLY PRESSURE VESSELS | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0400-01-1-CRS_1 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR SUPPLY PRESSURE VESSELS | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-0400-01-1-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0400-01-1-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 JOB SPECIFICATION FOR SUPPLY PRESSURE VESSELS | REF.:MIDOR-T-01039/TPIT-MIDOR-E-02166
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0570-01-0-CRS_0 | 03/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR SUPPLY COLUMN INTERNALS | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0570-01-0-CRS_1 | 20/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR SUPPLY COLUMN INTERNALS | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-0570-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0570-01-0-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 JOB SPECIFICATION FOR SUPPLY COLUMN INTERNALS | REF.:MIDOR-T-01039/TPIT-MIDOR-E-02166
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0610-01-0-CRS_0 | 03/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR SUPPLY SHELL AND TUBE HEAT EXCHANGER | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0610-01-0-CRS_1 | 12/05/16 | CLIENT COMMENTS TO UNIT 00 JOB SPECIFICATION FOR SUPPLY SHELL AND TUBE HEAT EXCHANGER | REF.:TPIT-MIDOR-T-01039/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-0610-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0610-01-0-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 JOB SPECIFICATION FOR SUPPLY SHELL AND TUBE HEAT EXCHANGER | REF.:MIDOR-T-01039/TPIT-MIDOR-E-02166
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0610-01-0-CRS-REPLY_1 | 05/10/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 JOB SPECIFICATION FOR SUPPLY SHELL AND TUBE HEAT EXCHANGER | REF.:MIDOR-T-01039/TPIT-MIDOR-E-02121
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0710-01-0-CRS_0 | 03/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR AIR COOLED HEAT EXCHANGERS | REF.:TPIT-MIDOR-T-00562/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0710-01-0-CRS_1 | 25/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR AIR COOLED HEAT EXCHANGERS | REF.:TPIT-MIDOR-T-00562/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-0710-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0710-01-0-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 GENERAL SUPPLY RULES FOR AIR COOLED HEAT EXCHANGERS | REF.:MIDOR-T-00562/TPIT-MIDOR-E-02166
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-0710-01-0-CRS-REPLY_1 | 05/10/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 GENERAL SUPPLY RULES FOR AIR COOLED HEAT EXCHANGERS | REF.:MIDOR-T-00562/TPIT-MIDOR-E-02121
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0910-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS | REF.:TPIT-MIDOR-T-0529/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0910-01-0-CRS_1 | 04/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS | REF.:TPIT-MIDOR-T-00529/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0910-01-0-CRS-REPLY_0 | 14/10/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS | REF.T-0529/PMC-E-0030/TPIT-E-2281 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0910-01-2-CRS_0 | 11/01/17 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS | REF.:T-02526/MIDOR-T-00155
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0910-01-2-CRS_1 | 20/01/17 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS | REF.:T-02526/TPIT-E-2586/-MIDOR-T-00165 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0910-01-2-CRS-REPLY_0 | 18/01/17 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS | REF.:T-02526/MIDOR-T-00155/TPIT-E-2586 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0910-01-3-CRS_0 | 24/08/17 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS | REF.:T-2652/MDR-TPIT-T-00378 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0920-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR RECIPROCATING PUMPS | REF.:TPIT-MIDOR-T-0900/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0920-01-0-CRS_1 | 04/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SPECIFICATION FOR RECIPROCATING PUMPS | REF.:TPIT-MIDOR-T-00900/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0920-01-0-CRS_2 | 17/10/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SPECIFICATION FOR RECIPROCATING PUMPS | REF.:T-00900/PMC-E-0030/PMC-T-00098
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0930-01-0-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR MACHINERY | REF.:TPIT-MIDOR-T-00900
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0930-01-0-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR ROTARY PUMPS | REF.:TPIT-MIDOR-T-0900/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0930-01-0-CRS_2 | 04/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SPECIFICATION FOR ROTARY PUMPS | REF.:TPIT-MIDOR-T-00900/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0940-01-0-CRS_0 | 10/04/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR CONTROLLED VOLUME PUMPS | REF:T-1410/MIDOR-TPIT-E-2016-04-11_06-29 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01732 | 06/06/16
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0940-01-0-CRS_1 | 18/10/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL AIR COMPRESSORS | REF.:TPIT-MIDOR-T-00103
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0940-01-A-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CONTROLLED VOLUME PUMPS | REF.:TPIT-MIDOR-T-0087/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0940-01-A-CRS_1 | 04/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CONTROLLED VOLUME PUMPS | REF.:TPIT-MIDOR-T-0087/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-0950-01-1-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR SHAFT SEALING SYSTEMS FOR CENTRIFUGAL AND ROTARY PUMPS | REF.:TPIT-MIDOR-T-00511/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1011-01-1-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR MACHINERY | REF.:TPIT-MIDOR-T-00900
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1011-01-1-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL COMPRESSORS | REF.:TPIT-MIDOR-T-00900/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1011-01-1-CRS_2 | 04/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL COMPRESSORS | REF.:TPIT-MIDOR-T-00900/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1011-01-1-CRS_3 | 17/10/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR CENTRIFUGAL COMPRESSORS | REF.:REF.:T-00900/PMC-E-0030/PMC-T-00098
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1013-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR PACKAGED INTEGRALLY-GEARED CENTRIFUGAL AIR COMPRESSORS | REF.:TPIT-MIDOR-T-00522/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1013-01-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR PACKAGED INTEGRALLY-GEARED CENTRIFUGAL AIR COMPRESSORS | REF.:TPIT-MIDOR-T-00522/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1013-01-0-CRS_2 | 17/10/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR PACKAGED INTEGRALLY-GEARED CENTRIFUGAL AIR COMPRESSORS | REF.:T-00522/PMC-E-0030/PMC-T-00098
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1020-01-1-CRS_0 | 02/03/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR COMPRESSORS | REF:T-0836/MIDOR-TPIT-E-2016-03-10_14-12
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1020-01-1-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR RECIPROCATING COMPRESSORS | REF.:TPIT-MIDOR-T-00836/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1020-01-1-CRS_2 | 09/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR RECIPROCATING COMPRESSORS | REF.:TPIT-MIDOR-T-00836/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1020-01-1-CRS_3 | 17/10/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR RECIPROCATING COMPRESSORS | REF.:T-00836/PMC-E-0030/PMC-T-00098
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1031-01-0-CRS_0 | 02/03/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR COMPRESSORS | REF:T-0836/MIDOR-TPIT-E-2016-03-10_14-12
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1031-01-0-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR ROTARY-TYPE POSITIVE DISPLACEMENT COMPRESSORS | REF.:TPIT-MIDOR-T-00836/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1031-01-0-CRS_2 | 09/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR ROTARY-TYPE POSITIVE DISPLACEMENT COMPRESSORS | REF.:TPIT-MIDOR-T-00836/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1040-01-0-CRS_0 | 25/03/16 | CLIENT COMMENTS TO GENERAL SPECIFICATIONS FOR CENTRIFUGAL FANS | REF:T-1222/MIDOR-TPIT-E-2016-03-27_11-28 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01287/2544-00-JSS-1040-01-0-CRS-REPLY_0 | 25/03/16
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1040-01-0-CRS-REPLY_0 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SPECIFICATIONS FOR CENTRIFUGAL FANS | REF: 2544-00-JSS-1040-01-0-CRS_0/E01287
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1040-01-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO GENERAL SPECIFICATIONS FOR CENTRIFUGAL FANS | REF:T-0992/MIDOR-TPIT-E-2016-03-15_11-07 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01160/2544-00-JSS-1040-01-A-CRS-REPLY_0 | 18/03/16
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1040-01-A-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATIONS FOR CENTRIFUGAL FANS | REF:T-00992/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1040-01-A-CRS_2 | 09/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATIONS FOR CENTRIFUGAL FANS | REF:T-00992/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1040-01-A-CRS-REPLY_0 | 18/03/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SPECIFICATIONS FOR CENTRIFUGAL FANS | REF:2544-00-JSS-1040-01-A-CRS_0/E-1160
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1061-01-0-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR SPECIAL-PURPOSE OIL SYSTEMS | REF.:TPIT-MIDOR-T-00836/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1061-02-1-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR GENERAL PURPOSE OIL SYSTEM | REF.:TPIT-MIDOR-T-00836/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1111-01-1-CRS_0 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICARION FOR GENERAL PURPOSE STEAM TURBINE | REF.:TPIT-MIDOR-T-00512/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1111-01-1-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICARION FOR GENERAL PURPOSE STEAM TURBINE | REF.:TPIT-MIDOR-T-00512/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1112-01-2-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SPECIAL PURPOSE STEAM TURBINE | REF:T-0551/MIDOR-TPIT-E-2016-03-17_13-47 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01163 | 21/03/16
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1112-01-2-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR SPECIAL PURPOSE STEAM TURBINES | REF.:TPIT-MIDOR-T-00551/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1112-01-2-CRS_2 | 09/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR SPECIAL PURPOSE STEAM TURBINES | REF.:TPIT-MIDOR-T-00551/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1112-01-3-CRS_0 | 11/01/16 | CLIENT COMMENTS TO SPECIAL PURPOSE STEAM TURBINE | REF:T-2526/MIDOR-T-0155 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1112-01-3-CRS_1 | 20/01/16 | CLIENT COMMENTS TO SPECIAL PURPOSE STEAM TURBINE | REF:T-2526/TPIT-E-2586/MIDOR-T-0165 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-1112-01-3-CRS-REPLY_0 | 18/01/16 | TPIT-REPLY TO CLIENT COMMENTS TO SPECIAL PURPOSE STEAM TURBINE | REF:T-2526/MIDOR-T-0155/TPIT-E-2586 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1300-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1300-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1300-01-A-CRS_1 | 17/04/16 | CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | REF 2544-00-JSS-1300-01-A-CRS-REPLY_0
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1300-01-A-CRS_2 | 03/05/16 | CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1300-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | REF: E-1353/2544-00-JSS-1300-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | TPIT-MIDOR-E-01438/2544-00-JSS-1300-01-A-CRS_1 | 17/04/16
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1300-01-A-CRS-REPLY_1 | 19/04/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR PIPING MATERIAL | REF: 2544-00-JSS-1300-01-A-CRS_1
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR VALVES (GATE GLOBE CHECK) | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1310-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-01-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR VALVES (GATE GLOBE CHECK) | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR VALVES (GATE GLOBE CHECK) | REF: E-1353/2544-00-JSS-1310-01-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-04-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTERFLY VALVES | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1310-04-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-04-A-CRS_1 | 14/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTERFLY VALVES | REF:T-1192/2544-00-JSS-1310-04-A-CRS-REP | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1310-04-A-CRS-REPLY_1 | 19/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-04-A-CRS_2 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTERFLY VALVES | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-04-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTERFLY VALVES | REF: E-1353/2544-00-JSS-1310-04-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1310-04-A-CRS_1 | 14/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-04-A-CRS-REPLY_1 | 19/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTERFLY VALVES | REF: T-1192/2544-00-JSS-1310-04-A-CRS_1
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-06-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR PLUG VALVES | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1310-06-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-06-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR PLUG VALVES | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-06-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR PLUG VALVES | REF: E-1353/2544-00-JSS-1310-06-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-08-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BALL VALVES | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1310-08-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-08-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BALL VALVES | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1310-08-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BALL VALVES | REF: E-1353/2544-00-JSS-1310-08-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1320-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR PIPES | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1320-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1320-01-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR PIPE | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1320-01-A-CRS_2 | 25/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR PIPE | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1320-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR PIPES | REF: E-1353/2544-00-JSS-1320-01-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1328-01-A-CRS_0 | 09/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR GLASS REINFORCED PLASTIC PIPING | REF:T-1233/MIDOR-TPIT-E-2016-04-11_06-27 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-1355/2544-00-JSS-1328-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1328-01-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR GLASS REINFORCED PLASTIC PIPING | REF.:TPIT-MIDOR-T-01233/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1328-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR GLASS REINFORCED PLASTIC PIPING | REF: E-1355/2544-00-JSS-1328-01-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1330-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1330-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1330-01-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1330-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BUTTWELDING FITTINGS | REF: E-1353/2544-00-JSS-1330-01-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1340-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR FORGED FITTINGS | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1340-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1340-01-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR FORGED FITTINGS | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1340-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR FORGED FITTINGS | REF: E-1353/2544-00-JSS-1340-01-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1350-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR FLANGES BLANKS AND DRIP RINGS | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1350-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1350-01-A-CRS_1 | 11/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR FLANGES BLANKS AND DRIP RINGS | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1350-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR FLANGES BLANKS AND DRIP RINGS | REF: E-1353/2544-00-JSS-1350-01-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1360-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR GASKETS | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1360-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1360-01-A-CRS_1 | 12/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR GASKETS | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1360-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR GASKETS | REF: E-1353/2544-00-JSS-1360-01-A-CRS_0
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1370-01-A-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BOLTING | REF:T-1192/MIDOR-TPIT-E-2016-04-08_14-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01353/2544-00-JSS-1370-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1370-01-A-CRS_1 | 12/05/16 | CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BOLTING | REF.:TPIT-MIDOR-T-01192/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-1370-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DETAILED SUPPLY SPECIFICATION FOR BOLTING | REF: E-1353/2544-00-JSS-1370-01-A-CRS_0
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1382-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO JOB SUPPLY SPECIFICATION FOR POLYURETHANE PIPING SUPPORTS | REF.:TPIT-MIDOR-T-01501/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1383-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO JOB SUPPLY SPECIFICATION FOR ROAD AND SPRING HANGERS | REF.:TPIT-MIDOR-T-01549/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1383-01-A-CRS_0 | 14/04/16 | CLIENT COMMENTS TO UNIT 00 JOB SUPPLY SPECIFICATION FOR ROAD AND SPRING HANGERS | REF:T-1431/MIDOR-TPIT-E-2016-04-14_14-30 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01395/2544-00-JSS-1383-01-A-CRS-REPLY_0 | 14/04/16
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1383-01-A-CRS-REPLY_0 | 14/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 JOB SUPPLY SPECIFICATION FOR ROAD AND SPRING HANGERS | REF: E-01395/2544-00-JSS-1383-01-A-CRS_0
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1384-01-1-CRS_0 | 10/05/16 | CLIENT COMMENTS TO JOB SUPPLY SPECIFICATION FOR SLIDING PLATES | REF.:TPIT-MIDOR-T-01549/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1384-01-A-CRS_0 | 17/04/16 | CLIENT COMMENTS TO UNIT 00 JOB SUPPLY SPECIFICATION FOR SLIDING PLATES | REF: TPIT-MIDOR-T-01405 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01438/2544-00-JSS-1384-01-A-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1384-01-A-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 JOB SUPPLY SPECIFICATION FOR SLIDING PLATES | REF: T-01405/2544-00-JSS-1384-01-A-CRS_0
CRS | MIDOR | 00 | PIPING | 2544-00-JSS-1386-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO JOB SUPPLY SPECIFICATION FOR DYNAMIC PIPING SUPPORTS | REF.:TPIT-MIDOR-T-01501/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1511-01-1-CRS_0 | 10/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FOR INTEGRATED CONTROL AND SAFETY SYSTEM | REF.:TPIT-MIDOR-T-01203/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1511-01-1-CRS-REPLY_0 TPIT-MIDOR-E-02147 | 20/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1511-01-1-CRS_1 | 23/09/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FOR INTEGRATED CONTROL AND SAFETY SYSTEM | REF.:T-01203/MIDOR-TPIT-T-00048
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1511-01-1-CRS-REPLY_0 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR INTEGRATED CONTROL AND SAFETY SYSTEM | REF.: T-MIDOR-T-01203/TPIT-MIDOR-E-02147 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1511-01-1-CRS_1 MIDOR-TPIT-T-00048 (CLOSED) | 23/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-01-0-CRS_0 | 30/03/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FIRE & GAS DETECTION SYSTEM | REF: TPIT-MIDOR-E-01246
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-02-0-CRS_0 | 11/04/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FIRE & GAS DETECTION SYSTEM | REF: TPIT-MIDOR-T-01389 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1515-02-0-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-02-0-CRS_1 | 10/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FIRE AND GAS DETECTION SYSTEM | REF.:TPIT-MIDOR-T-01389/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1515-02-0-CRS-REPLY_1 TPIT-MIDOR-E-02147 | 20/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-02-0-CRS_2 | 12/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FIRE AND GAS DETECTION SYSTEM | REF.:TPIT-MIDOR-T-01389/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-02-0-CRS_3 | 12/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FIRE AND GAS DETECTION SYSTEM | REF.:T-01389/MIDOR-TPIT-T-00048
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-02-0-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FIRE & GAS DETECTION SYSTEM | REF:T-01389 -2544-00-JSS-1515-02-0-CRS_0
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-02-0-CRS-REPLY_1 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FIRE AND GAS DETECTION SYSTEM | REF.: T-MIDOR-T-01389/TPIT-MIDOR-E-02147 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1515-02-0-CRS_3 MIDOR-TPIT-T-00048 (CLOSED) | 23/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-03-0-CRS_0 | 10/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY MACHINERY MONITORING SYSTEM (MMS) | REF.:TPIT-MIDOR-T-01219/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-03-1-CRS_0 | 25/08/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY MACHINERY MONITORING SYSTEM (MMS) | REF.:T-02421/MIDOR-TPIT-T-00027
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-03-1-CRS_1 | 25/08/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY MACHINERY MONITORING SYSTEM (SPC) | REF.:MIDOR-TPIT-T-00108
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-03-1-CRS-REPLY_0 | 06/10/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY MACHINERY MONITORING SYSTEM (MMS) | REF.:T-02421/TPIT-MIDOR-E-02226
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1515-03-A-CRS_0 | 02/03/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY MMS | REF:T-0846/MIDOR-TPIT-E-2016-03-03_07-33
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1531-01-A-CRS_0 | 19/07/17 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY OF TEMPORARY ACCESS CONTROL AND PERSONNEL ON BOARD SYSTEM | REF:MIDOR-TPIT-T-00368 - OFFER FROM EPC | CLOSED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1541-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR CONTROL VALVE | REF.:TPIT-MIDOR-T-01271/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1541-01-0-CRS_1 | 12/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FOR CONTROL VALVE | REF.:TPIT-MIDOR-T-01271/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1541-01-0-CRS-REPLY_0 | 19/07/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1541-01-0-CRS-REPLY_0 | 19/07/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FOR CONTROL VALVE | REF.: 2544-00-JSS-1541-01-0-CRS_1
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1543-01-0-CRS_0 | 06/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ON-OFF VALVES | REF.:TPIT-MIDOR-T-01271/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1543-01-0-CRS-REPLY_1 TPIT-MIDOR-E-02147 | 20/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1543-01-0-CRS_1 | 12/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ON-OFF VALVES | REF.:TPIT-MIDOR-T-01271/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1543-01-0-CRS-REPLY_0 | 19/07/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1543-01-0-CRS_2 | 22/09/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ON-OFF VALVES | REF.:MIDOR-TPIT-T-00045
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1543-01-0-CRS-REPLY_0 | 19/07/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ON-OFF VALVES | REF.: 2544-00-JSS-1543-01-0-CRS_1
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1543-01-0-CRS-REPLY_1 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ON-OFF VALVES | REF.: T-MIDOR-T-01271/TPIT-MIDOR-E-02147 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1543-01-0-CRS_2 CLOSED | 22/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1545-01-0-CRS_0 | 09/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR PSV VALVES | REF.:TPIT-MIDOR-T-01283/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1545-01-0-CRS-REPLY_1 TPIT-MIDOR-E-02147 | 20/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1545-01-0-CRS_1 | 13/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR PSV VALVES | REF.:TPIT-MIDOR-T-01283/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1545-01-0-CRS-REPLY_0 | 19/07/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1545-01-0-CRS_2 | 22/09/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR PSV VALVES | REF.:MIDOR-TPIT-T-00045
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1545-01-0-CRS-REPLY_0 | 19/07/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR PSV VALVES | REF.: 2544-00-JSS-1545-01-0-CRS_1
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1545-01-0-CRS-REPLY_1 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FOR PSV VALVES | REF.: T-MIDOR-T-01283/TPIT-MIDOR-E-02147 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1545-01-0-CRS_2 CLOSED | 22/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1546-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR PRIMARY FLOW ELEMENTS | REF.:TPIT-MIDOR-T-01310/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1546-01-0-CRS_1 | 13/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR PRIMARY FLOW ELEMENTS | REF.:TPIT-MIDOR-T-01310/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1546-01-0-CRS-REPLY_0 | 19/07/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1546-01-0-CRS-REPLY_0 | 19/07/16 | TPIT REPLY TO CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR PRIMARY FLOW ELEMENTS | REF.: 2544-00-JSS-1546-01-0-CRS_1
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1547-01-0-CRS_0 | 03/06/16 | CLIENT COMMENTS TO JSS FOR FLOW METER | REF.:TPIT-MIDOR-T-01437/PMC-MIDOR-E-0033
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1552-02-0-CRS_0 | 09/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR NUCLEAR LEVEL INSTRUMENTS | REF.:TPIT-MIDOR-T-01250/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1552-02-0-CRS-REPLY_0 TPIT-MIDOR-E-02147 | 20/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1552-02-0-CRS_1 | 13/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR NUCLEAR LEVEL INSTRUMENTS | REF.:TPIT-MIDOR-T-01250/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1552-02-0-CRS_2 | 22/09/16 | CLIENT COMMENTS JOB JOB SPECIFICATION FOR SUPPLY FOR NUCLEAR LEVEL INSTRUMENTS | REF.:MIDOR-TPIT-T-00045
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1552-02-0-CRS-REPLY_0 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY FOR NUCLEAR LEVEL INSTRUMENTS | REF.: T-MIDOR-T-01250/TPIT-MIDOR-E-02147 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1552-02-0-CRS_2 CLOSED | 22/08/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1553-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ELECTRONIC TRANSMITTERS | REF.:TPIT-MIDOR-T-01271/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1553-01-0-CRS_1 | 13/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ELECTRONIC TRANSMITTERS | REF.:TPIT-MIDOR-T-01271/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-JSS-1585-01-0-CRS_0 | 09/05/16 | CLIENT COMMENTS JOB SPECIFICATION FOR SUPPLY FOR ANALYSER SYSTEMS AND ANLYZER SHELTERS | REF.:TPIT-MIDOR-T-01250/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1621-01-0-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR ELECTRICAL POWER AND CONTROL CABLES | REF.:TPIT-MIDOR-T-0019/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1621-01-0-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1621-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR ELECTRICAL POWER AND CONTROL CABLES | REF.:TPIT-MIDOR-T-019/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1621-01-0-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR ELECTRICAL POWER AND CONTROL CABLES | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1621-01-0-CRS_1 (CLOSE) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1641-01-0-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR 3-PHASE MEDIUM VOLTAGE OIL IMMERSED TYPE POWER TRANSFORMERS | REF.:TPIT-MIDOR-T-0226/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1641-01-0-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1641-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR 3-PHASE MEDIUM VOLTAGE OIL IMMERSED TYPE POWER TRANSFORMERS | REF.:TPIT-MIDOR-T-226/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1641-01-0-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR 3-PHASE MEDIUM VOLTAGE OIL IMMERSED TYPE POWER TRANSF | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1641-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1652-01-0-CRS_0 | 09/05/16 | CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR MEDIUM VOLTAGE SWITCHGEARS | REF.:TPIT-MIDOR-T-0226/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1652-01-0-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1652-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR 3-PHASE MEDIUM VOLTAGE OIL IMMERSED TYPE POWER TRANSFORMERS | REF.:TPIT-MIDOR-T-226/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1652-01-0-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR MEDIUM VOLTAGE SWITCHGEARS | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1652-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1654-01-0-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR LOW VOLTAGE SWITCHGEARS | REF.:TPIT-MIDOR-T-0226/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1654-01-0-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1654-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR LOW VOLTAGE SWITCHGEARS | REF.:TPIT-MIDOR-T-226/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1654-01-0-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE SWITCHGEARS | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1654-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1656-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR POWER FACTOR CORRECTION SYSTEMS | REF.:TPIT-MIDOR-T-1430/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1656-01-0-CRS-REPLY_0 | 21/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1656-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR POWER FACTOR CORRECTION SYSTEMS | REF:TPIT-MIDOR-T-1430/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1656-01-0-CRS-REPLY_0 | 21/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY RULES FOR POWER FACTOR CORRECTION SYSTEMS | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1656-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1656-01-A-CRS_0 | 24/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR CAPACITOR BANK | REF.:TPIT-MIDOR-T-00019
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1657-01-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR LOW VOLTAGE | REF.:TPIT-MIDOR-T-00682 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1657-01-0-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1657-01-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR LOW VOLTAGE DISTRIBUTION BOARDS | REF.:TPIT-MIDOR-T-00682/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1657-01-0-CRS-REPLY_1 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1657-01-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR LOW VOLTAGE DISTRIBUTION BOARDS | REF:TPIT-MIDOR-T-0682/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1657-01-0-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSS FOR LOW VOLTAGE DISTRIBUTION BOARDS | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1657-01-0-CRS-REPLY_1 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE DISTRIBUTION BOARDS | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1657-01-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1661-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR ELECTRICAL MONITORING AND CONTROL SYSTEM | REF.:TPIT-MIDOR-T-00855/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1661-01-0-CRS-REPLY_0 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1661-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR ELECTRICAL MONITORING AND CONTROL SYSTEM | REF:TPIT-MIDOR-T-0855/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1661-01-0-CRS-REPLY_0 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS GENERAL SUPPLY RULES FOR ELECTRICAL MONITORING AND CONTROL SYSTEM (ECMS) | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1661-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1671-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR A.C.U.P.S. STYSTEM | REF.:TPIT-MIDOR-T-00682/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1671-01-0-CRS-REPLY_0 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1671-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPC FOR A.C.U.P.S. STYSTEM | REF:TPIT-MIDOR-T-0682/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1671-01-0-CRS-REPLY_0 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR A.C. U.P.S. SYSTEM | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1671-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1672-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR D.C. U.P.S. SYSTEM | REF.:TPIT-MIDOR-T-00682/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1672-01-0-CRS-REPLY_0 | 21/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1672-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR D.C. U.P.S. SYSTEM | REF:TPIT-MIDOR-T-0682/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1672-01-0-CRS-REPLY_0 | 21/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR D.C. U.P.S. SYSTEM | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1672-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1682-01-0-CRS_0 | 31/05/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR ELECTRICAL HEAT TRACING SYSTEM | REF.:T-01550/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1682-01-0-CRS_1 | 31/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR ELECTRICAL HEAT TRACING SYSTEM | REF.:TPIT-MIDOR-T-01550/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1682-01-0-CRS-REPLY_0 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1682-01-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY RULES FOR ELECTRICAL HEAT TRACING SYSTEM | REF:TPIT-MIDOR-T-1550/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1682-01-0-CRS-REPLY_0 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY RULES FOR ELECTRICAL HEAT TRACING SYSTEM | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1682-01-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1682-01-0-CRS-REPLY_1 | 28/11/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY RULES FOR ELECTRICAL HEAT TRACING SYSTEM | REF.: MIDOR-T-00092/TPIT-E-02460
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-0-CRS_0 | 30/03/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.:00682/MIDOR-TPIT-E-2016-03-31_13-20 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01996/2544-00-JSS-1684-01-0-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-0-CRS_1 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.:TPIT-MIDOR-T-01550/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1684-01-0-CRS-REPLY_1 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF:TPIT-MIDOR-T-0682/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-0-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.:E-1996/2544-00-JSS-1684-01-0-CRS_0 | OWNER RESPONSE REQUIRED | 29/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-0-CRS-REPLY_1 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1684-01-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-A-CRS_3 | 24/04/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.: TPIT-MIDOR-E-01461 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01650/2544-00-JSS-1684-01-A-CRS-REPLY_3 | 23/05/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-A-CRS_4 | 29/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.: 2544-00-JSS-1684-01-A-CRS-REPLY_3 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01698/2544-00-JSS-1684-01-A-CRS-REPLY_4 | 30/05/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-A-CRS-REPLY_3 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.: E-1650/2544-00-JSS-1684-01-A-CRS_3 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-05-29_14-56/2544-00-JSS-1684-01-A-CRS_4 | 29/05/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1684-01-A-CRS-REPLY_4 | 30/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR CATHODIC PROTECTION | REF.: E-1698/2544-00-JSS-1684-01-A-CRS_4
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-01-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR LOW VOLTAGE | REF.:TPIT-MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1691-01-0-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-01-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF.:TPIT-MIDOR-T-0019/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1691-01-0-CRS-REPLY_1 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-01-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF:TPIT-MIDOR-T-0019/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-01-0-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSS FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-01-0-CRS-REPLY_1 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1691-01-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-02-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR LOW VOLTAGE | REF.:TPIT-MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1691-02-0-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-02-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS NON SPARKING TYPE | REF.:TPIT-MIDOR-T-0019/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1691-02-0-CRS-REPLY_1 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-02-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS NON SPARKING TYPE | REF:TPIT-MIDOR-T-0019/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-02-0-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSS LOW VOLTAGE 3-PHASE INDUCTION MOTORS NON SPARKING TYPE | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-02-0-CRS-REPLY_1 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS NON SPARKING | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1691-02-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-03-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR LOW VOLTAGE | REF.:TPIT-MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1691-03-0-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-03-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF.:TPIT-MIDOR-T-0019/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1691-03-0-CRS-REPLY_1 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-03-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF:TPIT-MIDOR-T-0019/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-03-0-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSS LOW VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1691-03-0-CRS-REPLY_1 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1691-03-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-01-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR MEDIUM VOLTAGE | REF.:TPIT-MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1692-01-0-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-01-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF.:TPIT-MIDOR-T-0019/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1692-01-0-CRS-REPLY_1 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-01-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF:TPIT-MIDOR-T-0019/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-01-0-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSS MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-01-0-CRS-REPLY_1 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS JSS MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS TEFC TYPE | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1692-01-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-02-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR MEDIUM VOLTAGE | REF.:TPIT-MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1692-02-0-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-02-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR MEDIUM VOLTAGE 3-PHASE INDUCTION MOTOR NON SPARKING TYPTE | REF.:TPIT-MIDOR-T-0019/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1692-02-0-CRS-REPLY_1 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-02-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS NON SPARKING TYPE | REF:TPIT-MIDOR-T-0019/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-02-0-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSS MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS NON SPARKING TYPE | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-02-0-CRS-REPLY_1 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS JSS MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS NON SPARKING TYPE | REF.: 2544-DR-TPIT-UOP-0037 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1692-02-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-03-0-CRS_0 | 17/03/16 | CLIENT COMMENTS TO UNIT 00 JSS FOR MEDIUM VOLTAGE | REF.:TPIT-MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1692-03-0-CRS-REPLY_0 | 01/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-03-0-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF.:TPIT-MIDOR-T-0019/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1692-03-0-CRS-REPLY_1 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-03-0-CRS_2 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF:TPIT-MIDOR-T-0019/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-03-0-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS JSS MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF.COMT JSS & JSD TO BE FINALIZED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1692-03-0-CRS-REPLY_1 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS JSS MEDIUM VOLTAGE 3-PHASE INDUCTION MOTORS FLAME PROOF TYPE | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1692-03-0-CRS_2 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1693-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE VARIABLE FREQUENCY DRIVES | REF.:TPIT-MIDOR-T-0698/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1693-01-0-CRS-REPLY_0 | 22/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1693-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE VARIABLE FREQUENCY DRIVES | REF:TPIT-MIDOR-T-0698/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1693-01-0-CRS-REPLY_0 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR LOW VOLTAGE VARIABLE FREQUENCY DRIVES | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-1693-01-0-CRS_1 (CLSOED) | 27/07/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1694-01-A-CRS_0 | 19/10/17 | CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR HIGH VOLTAGE VARIABLE FREQUENCY DRIVES | REF:T-2673/MIDOR-TPIT-T-00411 | CLOSED |  | 2544-00-JSS-1694-01-A-CRS-REPLY_0 / TPIT-MIDOR-E-03491 | 16/11/17
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1694-01-A-CRS_1 | 2018-02-12 | CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR HIGH VOLTAGE VARIABLE FREQUENCY DRIVES | REF:T-2673/MIDOR-TPIT-T-00436 | CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-JSS-1694-01-A-CRS-REPLY_0 | 16/11/17 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR HIGH VOLTAGE VARIABLE FREQUENCY DRIVES | REF:T-2673/MIDOR-T-00411/TPIT-E-03491 | CLOSED
CRS | MIDOR | 00 | CIVIL | 2544-00-JSS-1800-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS GENERAL SUPPLY REULES FOR STEEL STRUCTURE | REF:T-00259/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-1820-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | CIVIL | 2544-00-JSS-1800-01-0-CRS-REPLY_0 | 07/07/16 | CLIENT COMMENTS GENERAL SUPPLY REULES FOR STEEL STRUCTURE | REF:T-00259/PMC-MIDOR-E-0030/MOM-00066_1 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00066_1 DTD 07/07/2016 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-1820-01-0-CRS_0 | 31/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY OF EQUIPMENT LADDERS AND PLATFORMS | RIF.: TPIT-MIDOR T-01082
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-1820-01-0-CRS_1 | 20/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY OF EQUIPMENT LADDERS AND PLATFORMS | REF.:TPIT-MIDOR-T-01082/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-1820-01-0-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 GENERAL SUPPLY REULES FOR STEEL STRUCTURE | REF.:MIDOR-T-00259/TPIT-MIDOR-E-02166
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-2520-01-0-CRS_0 | 28/04/16 | CLIENT COMMENTS GENERAL SUPPLY RULES FOR FIXED AND FLOATING ROOF TANK | REF.:TPIT-MIDOR-T-01080/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-2520-01-0-CRS_1 | 26/05/16 | CLIENT COMMENTS GENERAL SUPPLY RULES FOR FIXED AND FLOATING ROOF TANK | REF.:TPIT-MIDOR-T-01080/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-2520-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02166 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-2520-01-0-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS UNIT 00 GENERAL SUPPLY RULES FOR FIXED AND FLOATING ROOF TANK | REF.:MIDOR-T-01080/TPIT-MIDOR-E-02166
CRS | MIDOR | 00 | PVHE | 2544-00-JSS-2520-01-A-CRS-REPLY_0 | 01/07/16 | TPIT REPLY TO CLIENT COMMENTS GENERAL SUPPLY RULES FOR FIXED AND FLOATING ROOF TANK | REF.: MIDOR-TPIT-E-2015-11-18_21-19
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-2620-01-0-CRS_0 | 31/05/16 | CLIENT COMMENTS TO MECHANICAL EQUIPMENT LUBRICANTS | REF.:TPIT-MIDOR-T-01600/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-2620-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02242 | 07/10/16
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-2620-01-0-CRS_1 | 11/10/16 | CLIENT COMMENTS TO MECHANICAL EQUIPMENT LUBRICANTS | REF:TPIT-MIDOR-T-1600/E-02242/MIDOR-T-82 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-2620-01-0-CRS-REPLY_0 | 07/10/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL EQUIPMENT LUBRICANTS | REF:TPIT-MIDOR-T-1600/TPIT-MIDOR-E-02242
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-2620-01-A-CRS_0 | 23/04/16 | CLIENT COMMENTS TO MECHANICAL EQUIPMENT LUBRICANTS | REF.T-1433/MIDOR-TPIT-E-2016-04-24_10-23 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01482/2544-00-JSS-2620-01-A-CRS-REPLY_0 | 27/04/16
CRS | MIDOR | 00 | MACHINERY | 2544-00-JSS-2620-01-A-CRS-REPLY_0 | 27/04/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL EQUIPMENT LUBRICANTS | REF. E-1482/2544-00-JSS-2620-01-A-CRS_0
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4100-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR PACKAGE UNIT | REF.:TPIT-MIDOR-T-0086/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-4100-01-0-CRS-REPLY_0 TPIT-MIDOR-E-02178 | 28/09/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4100-01-0-CRS-REPLY_0 | 28/09/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR PACKAGE UNIT | REF.:T-0086/TPIT-MIDOR-E-02178
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4123-01-0-CRS_0 | 10/05/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR EMERGENCY DIESEL GENERATORS | REF.:TPIT-MIDOR-T-0732/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-4123-01-0-CRS-REPLY_0 | 22/07/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4123-01-0-CRS_1 | 27/07/16 | CLIENT COMMENTS TO UNIT 00 GENERAL SUPPLY SPECIFICATION FOR EMERGENCY DIESEL GENERATORS | REF:TPIT-MIDOR-T-0732/MIDOR-TPIT-T-00007
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4123-01-0-CRS-REPLY_0 | 22/07/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SUPPLY SPECIFICATION FOR EMERGENCY DIESEL GENERATORS | REF.: 2544-DR-TPIT-UOP-0037 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-4123-01-0-CRS_1 (CLOSED) | 27/07/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4261-01-0-CRS_0 | 05/06/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR MECHANICAL AGITATORS | REF.:TPIT-MIDOR-T-01848 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-4261-01-0-CRS-REPLY_0 | 06/06/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4261-01-0-CRS_1 | 08/06/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR MECHANICAL AGITATORS | REF.T-1848/MIDOR-TPIT-E-2016-06-08_20-34 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02232 (CLOSED) | 06/10/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4261-01-0-CRS-REPLY_0 | 06/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 SPECS FOR MECHANICAL AGITATOR | REF.:01848/TPIT-MIDOR-E-01730 | OWNER RESPONSE REQUIRED |  | 2544-00-JSS-4261-01-0-CRS_1 / MIDOR-TPIT-E-2016-06-08_20-34 | 08/06/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4261-01-A-CRS_0 | 10/04/16 | CLIENT COMMENTS TO UNIT 00 SPECS FOR MECHANICAL AGITATOR | REF.:01253/MIDOR-TPIT-E-2016-04-12_07-41 | TPIT RESPONSE REQUIRED |  | 2544-00-JSS-4261-01-A-CRS-REPLY_0 TPIT-MIDOR-E-01592 | 17/05/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4261-01-A-CRS_1 | 05/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR MECHANICAL AGITATORS | REF.:TPIT-MIDOR-T-01253/PMC-MIDOR-E-0030 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01730 2544-00-JSS-4261-01-A-CRS-REPLY_0 | 06/06/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4261-01-A-CRS_2 | 10/05/16 | CLIENT COMMENTS TO GENERAL SPECIFICATION FOR MECHANICAL AGITATORS | REF.:TPIT-MIDOR-T-01253/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | PACKAGES | 2544-00-JSS-4261-01-A-CRS-REPLY_0 | 17/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 SPECS FOR MECHANICAL AGITATOR | REF.:01253/MIDOR-TPIT-E-2016-04-12_07-41
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-6300-02-0-CRS_0 | 29/04/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR WELDING AND NDE OF PRESSURE VESSELS AND HEAT EXCHANGERS | REF.:TPIT-MIDOR-T-0038/PMC-MIDOR-E-0030 |  |  | 2544-00-JSS-6300-02-0-CRS-REPLY_0 TPIT-MIDOR-E-02463 | 26/11/16
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-6300-02-0-CRS-REPLY_0 | 29/11/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR WELDING AND NDE OF PRESSURE VESSELS AND HEAT EXCHANGERS | REF.:T-0038/PMC-E-0030/TPIT-E-02463
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-6300-02-3-CRS_0 | 13/03/17 | CLIENT COMMENTS TO JOB SPECIFICATION FOR WELDING AND NDE OF PRESSURE VESSELS AND HEAT EXCHANGERS | REF.:T-2564/MIDOR-TPIT-T-00213 | CLOSED |  | APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-6300-03-0-CRS_0 | 29/04/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR MATERIALS IN SOUR SERVICES | REF.:TPIT-MIDOR-T-0038/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-6300-04-0-CRS_0 | 04/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR SUPPLY POSITIVE ALLOY MATERIAL IDENTIFICATION OF EQUIPMENT AND PIPING | REF.:TPIT-MIDOR-T-0038/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | MATERIAL TECHNOLOGY | 2544-00-JSS-6300-05-1-CRS_0 | 04/05/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR WELDING AND NDE STORAGE TANKS | REF.:TPIT-MIDOR-T-00837/PMC-MIDOR-E-0030
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ML-0150-101-A-CRS_0 | 03/05/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR STEAM BOILER OBE PURPOSE | REF:T-1485/MIDOR-TPIT-E-2016-05-03_18-16
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-ML-0150-101-A-CRS-REPLY_0 | 02/03/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR STEAM BOILER | REF: MOM-00082/E-02709/T-01485 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0110-001-B-CRS_0 | 04/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR FIRED HEATERS | REF:T-0539/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0110-R01-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR FIRED HEATER REVAMPING | REF:T-0675/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0113-301-1-CRS_0 | 05/05/17 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR REFORMER PACKAGE (TECHNICAL PROPOSAL) | REF:T-02591/MIDOR-TPIT-T-00306 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0127-401-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INCINERATOR STEAM SUPERHEATER | REF.: MIDOR-TPIT-T-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0150-101-A-CRS_1 | 22/03/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0150-101 AND ITB | REF:T-0271/MIDOR-TPIT-E-2016-03-22_22-10 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01375/2544-00-MR-0150-101-A-CRS-REPLY_1 | 07/04/16
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0150-101-A-CRS_2 | 04/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR AUXILIARY STEAM BOILER | REF:T-0271/MIDOR-TPIT-E-2016-07-31_16-44 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0150-101-A-CRS-REPLY_0 | 18/03/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0150-101 | REF: MIDOR-TPIT-E-2015-12-31_07-33 | OWNER RESPONSE REQUIRED |  | 2544-00-MR-0150-101-A-CRS_1 | 22/03/16
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0150-101-A-CRS-REPLY_1 | 07/04/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0150-101 AND ITB | REF: E-01375/2544-00-MR-0150-101-A-CRS_1
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0167-401-A-CRS_0 | 24/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INCINERATOR | REF:MIDOR-TPIT-T-00133 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0168-401-A-CRS_0 | 21/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR THERMAL REACTOR REQUISITION | REF.:MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0172-401-A-CRS_0 | 06/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR STACK | REF.: MIDOR-TPIT-T-00077 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0172-401-A-CRS_1 | 14/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR STACK | REF.: MIDOR-TPIT-T-00097 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0182-101-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR FOR DERRICK SUPPORTED ELEVATED FLARE | REF.T-00892/MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0191-401-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO MR FOR THERMAL REACTOR BURNER | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-MR-0191-402-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO MR FOR INCINERATOR BURNERS | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0210-101-B-CRS_0 | 02/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR DEMINERALIZATION AND ULTRAFILTRATION PACKAGE | REF:T-1497/MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0310-102-A-CRS_0 | 01/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-102 | REF:MIDOR-TPIT-T-00138 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0310-201-B-CRS_0 | 10/06/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-201 | REF:T-1888/MIDOR-TPIT-E-2016-06-16_10-27 | TPIT RESPONSE REQUIRED |  | 2544-00-MR-0310-201-B-CRS-REPLY_0 | 17/10/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0310-201-B-CRS_1 | 13/06/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-201 | REF:T-1888/MIDOR-TPIT-E-2016-06-13_13-06 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0310-201-B-CRS_2 | 02/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-201 | REF:T-1088/MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED |  | 2544-00-MR-0310-201-B-CRS-REPLY_0 | 17/10/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0310-201-B-CRS-REPLY_0 | 17/10/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-201 | REF: T-1088/2544-00-MR-0310-201-B-CRS_1 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00105 DTD 08/02/2017
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0411-303-A-CRS_0 | 05/12/16 | CLIENT COMMENTS TO MR FOR LOW ALLOY REACTORS | REF.: MIDOR-TPIT-T-00145 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0411-402-A-CRS_0 | 05/12/16 | CLIENT COMMENTS TO MR FOR SULPHUR REACTORS | REF.: MIDOR-TPIT-T-00145 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0470-101-A-CRS_0 | 06/09/16 | CLIENT COMMENTS TO MR FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF.: MIDOR-TPIT-T-00024 | TPIT RESPONSE REQUIRED |  | 2544-00-MR-0470-101-A-CRS-REPLY_0/TPIT-MIDOR-E-2171 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0470-101-A-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MR FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF.: E-2171/2544-00-MR-0470-101-A-CRS_0 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0511-001-B-CRS_0 | 20/06/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0232/MIDOR-TPIT-E-2016-07-31_16-44 | TPIT RESPONSE REQUIRED |  | 2544-00-MR-0511-001-B-CRS-REPLY_0 TPIT-MIDOR-MOM-00083 | 10/08/16
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0511-001-B-CRS-REPLY_0 | 10/08/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0232/TPIT-MIDOR-MOM-00083
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0511-002-B-CRS_0 | 28/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR MAIN SHOP ASSEMBLED COLUMNS | REF:MIDOR-TPIT-T-00135 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0570-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR PROPRIETARY INTERNAL FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0233/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0570-002-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INTERNALS FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0159/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0570-003-A-CRS_0 | 24/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INTERNALS FOR INTERNAL SHOP ASSEMBLED COLUMNS | REF:MIDOR-TPIT-T-00135
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0570-R02-A-CRS_0 | 25/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INTERNALS FOR EXISTING COLUMNS REVAMP | REF:MIDOR-TPIT-T-00107 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-001-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:TPIT-MIDOR-T-01043/PMC-MIDOR-E-0052
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-001-B-CRS_1 | 26/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:ED-0019-M-T-0162/M-T-013/MOM-00091 | CLOSED |  | CLOSED WITH 2544-TPIT-MIDOR-MOM-00091 DTD 07/07/2017
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-001-B-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:E-2023/2544-00-MR-0610-001-B-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00091 DTD 07/07/2017
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-002-C-CRS_0 | 14/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR SHELL AND TUBE HEAT EXCHANGERS | REF:MIDOR-TPIT-T-00127 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-103-B-CRS_0 | 22/06/16 | CLIENTE COMMENTS TO MATERIAL REQUISITION FOR HIGH PERFORMANCE TUBES FOR HEAT EXCHANGERS | REF.:T-808/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-103-B-CRS-REPLY_0 | 21/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:T-00808/MOM-00079 |  |  | INCLUDES ALL MR APPL_DOC
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-104-A-CRS_0 | 24/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR VAPORIZER | REF:MIDOR-TPIT-T-00133 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0610-403-A-CRS_0 | 31/08/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR SULPHUR CONDENSERS | REF:ED-0025/MIDOR-TPIT-T-00017 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0630-001-D-CRS_0 | 28/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INTERNALS FOR HAIRPIN HEAT EXCHANGERS | REF:MIDOR-TPIT-T-00135
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0661-102-A-CRS_0 | 05/12/16 | CLIENT COMMENTS TO MR FOR PLATE & FRAME HEAT EXCHANGERS | REF.: MIDOR-TPIT-T-00145 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0661-401-A-CRS_0 | 05/12/16 | CLIENT COMMENTS TO MR FOR PLATE HEAT EXCHANGERS | REF.: MIDOR-TPIT-T-00145 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0710-001-B-CRS_0 | 27/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-00566/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0710-001-B-CRS-REPLY_0 | 27/01/17 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/MIDOR-T-00020/MOM-00097
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0710-R01-B-CRS_0 | 07/10/16 | CLIENT COMMENTS TO MR 0710-R01_B CRS FOR MOTOR AND FANS FOR EXISTING AIR COOLER (REVAMPING) | MIDOR-TPIT-T-00075
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0811-002-C-CRS_0 | 28/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INTERNALS FOR PRESSURE VESSELS | REF:MIDOR-TPIT-T-00135
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0811-101-B-CRS_0 | 26/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR HP PRESSURE VESSELS | REF:ED-0019-M-T-00103/MIDOR-TPIT-T-00013 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0811-101-B-CRS-REPLY_0 | 30/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR HP PRESSURE VESSELS | REF:T-00103/M-TPIT-T-13/T-MIDOR-E-02195 | CLOSED |  | CLOSED WITH 2544-00-TPIT-MIDOR-MOM-00086 DTD 09/02/2017
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0811-R01-B-CRS_0 | 14/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR MISCELLANEA COMPONENTS (REVAMPING) | REF: MIDOR-TPIT-T-00125 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-0813-402-A-CRS_0 | 24/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR SULPHUR SEALS | REF:MIDOR-TPIT-T-00133 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0836-001-B-CRS_0 | 09/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR SILENCERS | REF: MIDOR-TPIT-T-00144 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0841-001-A-CRS_0 | 24/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR FILTERS | REF:MIDOR-TPIT-T-00133 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0844-101-B-CRS_0 | 09/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR COALESCERS | REF: MIDOR-TPIT-T-00144 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0844-R01-A-CRS_0 | 09/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR COALESCERS (REVAMPING) | REF: MIDOR-TPIT-T-00144 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0845-001-A-CRS_0 | 11/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR DEAERATOR | REF: MIDOR-TPIT-T-00084 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0846-101-A-CRS_0 | 24/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR BACKWASH FILTERS | REF:MIDOR-TPIT-T-00133 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0846-R01-A-CRS_0 | 01/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0846-R01-A-CRS_0 | REF:MIDOR-TPIT-T-00138 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0851-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | REF: T-00157/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0852-001-B-CRS_0 | 09/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR EJECTORS | REF: MIDOR-TPIT-T-00144 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-0853-001-A-CRS_0 | 09/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR DESUPERHEATERS | REF: MIDOR-TPIT-T-00144 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0910-001-A-CRS_0 | 10/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR CENTRIFUGAL PUMPS | REF:TPIT-MIDOR-T-00081 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0910-001-A-CRS_1 | 18/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR CENTRIFUGAL PUMPS | REF:TPIT-MIDOR-T-00081/102 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0910-402-A-CRS_0 | 30/06/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR MATERIAL REQUISITION FOR VERTICAL SULPHUR PUMPS (2544-00-MR-0910-402) | REF:ED-0032/MIDOR-TPIT-T-00022 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0910-402-A-CRS_1 | 30/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR MATERIAL REQUISITION FOR VERTICAL SULPHUR PUMPS (2544-00-MR-0910-402) | REF:MIDOR-TPIT-T-00136 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0910-402-A-CRS-REPLY_0 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR VERTICAL SULPHUR PUMPS | REF.: TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0920-001-ATT-1-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO ATT TO MR FOR RECIPROCATING PUMPS | REF:T-01013/MIDOR-TPIT-T-00040
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0920-001-B-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR RECIPROCATING PUMPS | REF:T-01013/MIDOR-TPIT-T-00040
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0931-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MR FOR PROPORTIONING PUMPS | REF:T-00257/MIDOR-TPIT-T-00064 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-0940-402-A-CRS_0 | 27/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-00566/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1011-101-A-CRS_0 | 19/03/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSORS | REF:T-0173/MIDOR-TPIT-E-2016-03-22_22-38
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1011-101-A-CRS_1 | 19/03/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSORS | REF:T-0173/MIDOR-TPIT-E-2016-03-22_22-38
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1011-101-A-CRS_2 | 19/03/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSORS | REF:T-0173/MIDOR-TPIT-E-2016-03-22_22-38
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1020-001-A-CRS-REPLY_0 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION INQUIRY FOR RECIPROCATING COMPRESSORS | REF: TPIT-MIDOR-E-02148 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1020-301-B-CRS-REPLY_0 | 23/05/17 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR RECIPROCATING COMPRESSORS FOR AUXILIARY SERVICE | REF: T-2228/TPIT-MIDOR MOM-00137 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1031-101-A-CRS_1 | 17/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION ROTARY SCREW COMPRESSOR | REF:MIDOR-TPIT-T-00102 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1040-102-A-CRS_0 | 05/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR AIR BLOWERS | REF:MIDOR-TPIT-T-00143 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1040-402-A-CRS_1 | 25/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR AIR BLOWERS | REF:MIDOR-TPIT-T-00109 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-MR-1040-402-A-CRS-REPLY_1 | 04/04/17 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR COMBUSTION AIR BLOWERS | REF: TPIT-MIDOR MOM-00139 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1511-001-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-1511-001_A | REF.:00231/PMC-MIDOR-E-0028
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1511-002-A-CRS_0 | 2018-05-28 | CLIENT COMMENTS SCHNEIDER DCS OFFER AND MATERIAL REQUISITION | REF.:T-02899/MIDOR-T-00471 | CLOSED |  | TPIT-MIDOR-E-03689 CRS TPIT REPLY ATTACHED TO TBT 1511-02_0 | 2018-06-12
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1511-002-A-CRS-REPLY_0 | 2018-06-12 | TPIT RESPONSE TO CLIENT COMMENTS SCNEIDER DCS OFFER AND MATERIAL REQUISITION | REF.:T-2899/MIDOR-471/TPIT-E-3689/T-2908 | OWNER RESPONSE REQUIRED |  | CRS TPIT REPLY ATTACHED TO ML-TBT-1511-02_0
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1515-002-2-CRS_0 | 06/04/17 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-1515-02_2 | REF.:MIDOR-TPIT-T-00258 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1515-002-2-CRS_1 | 30/05/17 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR FIRE & GAS DETECTION SYSTEM- SAFCO OFFER | REF.:MIDOR-TPIT-T-00337 SAFCO OFFER | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1515-003-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-1515-003_A | REF.:00859/PMC-MIDOR-E-0028 | TPIT RESPONSE REQUIRED |  | 2544-00-MR-1515-003-A-CRS-REPLY_0 TPIT-MIDOR-E-02048 | 05/08/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1515-003-A-CRS_1 | 14/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-1515-003_A | REF.:MIDOR-TPIT-T-00032
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1515-003-A-CRS_4 | 13/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-1515-003_A | REF.:MIDOR-TPIT-T-00087
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1515-003-A-CRS-REPLY_0 | 05/08/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-1515-003 | REF: TPIT-MIDOR-E-02048 | OWNER RESPONSE REQUIRED |  | 2544-00-MR-1515-003-A-CRS_1 (CLOSED) MIDOR-TPIT-T-00032 | 14/09/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-MR-1531-01-A-CRS_0 | 13/07/17 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR TEMPORARY ACCESS CONTROL & PERSONNEL ON BOARD SYSTEM | REF.:MIDOR-TPIT-T-00364 OFFER FROM EPC | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-MR-1621-01-A-CRS_0 | 2018-02-19 | CLIENT COMMENTS TO MR ELECTRICAL CABLE | REF.: MIDOR-TPIT-T-00442 | CLOSED |  | CLOSED WITH MIDOR-TPIT-T-00442 | 2016-05-02
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-MR-1671-01-A-CRS_0 | 2018-02-19 | CLIENT COMMENTS TO MR ELECTRICAL AC UPS SYSTEM | REF.: MIDOR-TPIT-T-00442 | CLOSED |  | CLOSED WITH MIDOR-TPIT-T-00442 | 2016-05-02
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-MR-1672-01-A-CRS_0 | 2018-02-19 | CLIENT COMMENTS TO MR ELECTRICAL DC UPS SYSTEM | REF.: MIDOR-TPIT-T-00442 | CLOSED |  | CLOSED WITH MIDOR-TPIT-T-00442 | 2016-05-02
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-MR-1682-01-A-CRS_1 | 14/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR ELECTRICAL HEAT TRACING SYSTEM | REF.: MIDOR-TPIT-T-00094
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-MR-1684-01-A-CRS_0 | 18/08/16 | CLIENT COMMENTS TO MR FOR CATHODIC PROTECTION SYSTEM (OBE) | REF.: MIDOR-TPIT-T-00006 | OWNER RESPONSE REQUIRED |  | TPIT-MIDOR-E-02087 / 2544-00-MR-1684-01-A-CRS-REPLY_0 | 02/09/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-MR-1684-01-A-CRS_1 | 13/09/16 | CLIENT COMMENTS TO MR FOR CATHODIC PROTECTION SYSTEM (OBE) | REF.: MIDOR-TPIT-T-00031 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02162 | 23/09/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-MR-1684-01-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MR FOR CATHODIC PROTECTION SYSTEM (OBE) | REF.: 2544-00-MR-1684-01-A-CRS_0
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-MR-1900-001-A-CRS_0 | 02/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR FIREFIGHTING EQUIPMENT | REF:MIDOR-TPIT-T-00140 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-2510-102-A-CRS_0 | 05/12/16 | CLIENT COMMENTS TO MR FOR FRP TANK | REF.: MIDOR-TPIT-T-00145 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-MR-2520-101-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-2520-101 | REF: TPIT-MIDOR-00413/TPIT-MIDOR-E-01523
CRS | MIDOR | 00 | PVHE | 2544-00-MR-2520-101-B-CRS_0 | 24/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR TANKS ASSEMBLED ON SITE | REF:MIDOR-TPIT-T-00105
CRS | MIDOR | 00 | PVHE | 2544-00-MR-2520-101-B-CRS-REPLY_1 | 02/02/17 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION FOR STORAGE TANKS ASSEMBLED ON SITE | REF: T-00561/TPIT-MIDOR MOM-00136 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-MR-2520-402-A-CRS_0 | 05/12/16 | CLIENT COMMENTS TO MR FOR TANK | REF.: MIDOR-TPIT-T-00145 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4065-001-A-CRS_0 | 23/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR BRIDGE CRANES | REF:MIDOR-TPIT-T-00132 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4110-101-A-CRS_0 | 06/10/17 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR MODULAR LPG TREATMENT UNIT | REF:T-02710/MIDOR-TPIT-T-00406
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4111-001-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR PSA UNIT | REF:T-00417/MIDOR-TPIT-T-00042
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4117-101-A-CRS_0 | 10/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR LIN STORAGE PACKAGE | REF: MIDOR-TPIT-T-00084 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4123-01-A-CRS_1 | 14/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR ELECTRICITY DIESEL GENERATOR | REF: MIDOR-TPIT-T-00094 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4123-01-A-CRS_2 | 15/02/17 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR EMERGENCY DIESEL GENERATOR | REF: MIDOR-TPIT-T-00177 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4141-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR DESALTER PACKAGES | REF:T-0174/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4151-101-B-CRS_0 | 11/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR REFRIGERATION PACKAGE | REF:MIDOR-TPIT-T-00083 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4151-101-B-CRS_1 | 11/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR REFRIGERATION PACKAGE | REF:MIDOR-TPIT-T-00104 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4171-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR INSTRUMENT AIR DRYING PACKAGE | REF: T-00255/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4234-101-A-CRS_0 | 24/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR WATER FILTRATION PACKAGE | REF:MIDOR-TPIT-T-00133 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4261-001-A-CRS_0 | 18/11/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR MECHANICAL AGITATORS | REF:MIDOR-TPIT-T-00129 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4263-001-A-CRS_0 | 09/12/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR STATIC MIXERS | REF: MIDOR-TPIT-T-00144 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-MR-4300-402-A-CRS_0 | 10/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR SULPHUR SOLIDIFICATION PACKAGE | REF: T-00255/MIDOR-TPIT-T-00056/00081 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-0000-02-B-CRS_0 | 11/08/16 | CLIENT COMMENTS TO SPLIT OF SCOPE OF WORK (DIRECT AND INDERECT) | REF.:T-02419/MIDOR-TPIT-00003 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02903 / 2544-00-MS-0000-02-B-CRS-REPLY_0 | 05/09/16
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-0000-02-B-CRS-REPLY_0 | 05/09/16 | TPIT REPLY TO CLIENT COMMENTS TO SPLIT OF SCOPE OF WORK (DIRECT AND INDERECT) | REF.2544-00-MS-0000-02-B-CRS_0/T-00003
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-0000-02-D-CRS_0 | 05/10/17 | CLIENT COMMENTS TO SPLIT OF SCOPE OF WORK (DIRECT AND INDERECT) | REF.:T-02706/MIDOR-TPIT-T-00405 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | START UP | 2544-00-MS-1393-16-A-CRS_0 | 01/09/17 | CLIENT COMMENTS TO JOB COMMISSIONING GUIDELINE FOR TIGHTNESS TEST OF PIPING AND EQUIPMENT WITH NITROGEN AND HELIUM | REF.T-1831\MIDOR-TPIT-T-00383 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | START UP | 2544-00-MS-1593-02-A-CRS_0 | 31/07/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR START-UP LOOP FOLDER MANAGEMENT | REF.T-1880\MIDOR-TPIT-E-2016-07-31_15-29 | TPIT RESPONSE REQUIRED |  | 2544-00-MS-1593-02-A-CRS-REPLY_0/TPIT-MIDOR-E-02210 | 16/09/16
CRS | MIDOR | 00 | START UP | 2544-00-MS-1593-02-A-CRS_1 | 03/11/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR START-UP LOOP FOLDER MANAGEMENT |  | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-MS-1593-02-A-CRS-REPLY_0 | 16/09/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB SPECIFICATION FOR START-UP LOOP FOLDER MANAGEMENT | REF.T-1880/2544-00-MS-1593-02-A-CRS_0 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-MS-1593-03-A-CRS_0 | 31/07/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR START-UP FUNCTIONAL TEST MANAGEMENT | REF.T-1880\MIDOR-TPIT-E-2016-07-31_15-29 | TPIT RESPONSE REQUIRED |  | 2544-00-MS-1593-03-A-CRS-REPLY_0/TPIT-MIDOR-E-02210 | 16/09/16
CRS | MIDOR | 00 | START UP | 2544-00-MS-1593-03-A-CRS_1 | 03/11/16 | CLIENT COMMENTS TO JOB SPECIFICATION FOR START-UP FUNCTIONAL TEST MANAGEMENT |  | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-MS-1593-03-A-CRS-REPLY_0 | 16/09/16 | TPIT REPLY TO CLIENT COMMENTS TO JOB SPECIFICATION FOR START-UP FUNCTIONAL TEST MANAGEMENT | REF.T-1880/2544-00-MS-1593-03-A-CRS_0 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-6800-02-C-CRS_0 | 14/08/16 | CLIENT COMMENTS TO TECHNICAL SPECIFICATION FOR MECHANICAL ERECTION | REF.:T-02444/MIDOR-TPIT-00003
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-6850-51-0-CRS_0 | 17/10/17 | CLIENT COMMENTS TO JOB CONSTRUCTION SPECIFICATION FOR MACHINERY AND AIR COOLERS INSTALLATION | REF.:T-00308/MIDOR-TPIT-00408 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-6850-51-0-CRS_1 | 2018-02-22 | CLIENT COMMENTS TO TECHNICAL SPECIFICATIONS FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:T-0308\MIDOR-TPIT-T-00447 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-6850-51-0-CRS-REPLY_0 | 2018-01-30 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL SPECIFICATIONS FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:T-0308\TPIT-MIDOR-E-03582
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-8265-02-A-CRS_0 | 02/08/16 | CLIENT COMMENTS TO TECHNICAL SPECIFICATION FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:T-2325/MIDOR-TPIT-E-2016-08-03_12-37
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-8265-02-A-CRS_1 | 19/10/17 | CLIENT COMMENTS TO TECHNICAL SPECIFICATION FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:T-232/MIDOR-TPIT-T-00409 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-MS-8265-02-A-CRS-REPLY_0 | 09/08/16 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL SPECIFICATIONS FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:E-2062/2544-00-MS-8265-02-A-CRS_1
CRS | MIDOR | 00 | START UP | 2544-00-MS-9000-02-B-CRS_0 | 21/07/16 | CLIENT COMMENTS TO TECHNICAL SPECIFICATIONS FOR SUBCONTRACTORS ASSISTANT | REF:T-2247/MIDOR-TPIT-E-2016-07-22_18-51 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02044/2544-00-MS-9000-02-B-CRS-REPLY_0 | 01/08/16
CRS | MIDOR | 00 | START UP | 2544-00-MS-9000-02-B-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL SPECIFICATIONS FOR SUBCONTRACTORS ASSISTANT | REF:E-2044/2544-00-MS-9000-02-B-CRS_0
CRS | MIDOR | 00 | PROCESS | 2544-00-NM-121-A-CRS_FINAL WO UNIT 11 | 27/07/17 | CLIENT APPROVED TO LICENSED UNITS EQUIPMENT VERFICATION REPORT | REF:T-20321 | CLOSED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-NM-1530-06-A-CRS_0 | 24/05/17 | CLIENT COMMENTS TO TIE IN LIST TELECOM SYSTEMS | REF.T-2610\MIDOR-TPIT-T-00329 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-NM-1530-06-A-CRS_1 | 13/07/17 | CLIENT COMMENTS TO TIE IN LIST TELECOM SYSTEMS | REF.T-2610\MDR-TPIT-T-00329/361 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-NM-1650-02-A-CRS_0 | 27/07/16 | CLIENT COMMENTS TO ELECTRICAL INTERFACE POINT LIST | REF.T-2127\MIDOR-TPIT-E-2016-07-27_20-45 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02033/2544-00-NM-1650-02-A-CRS-REPLY_0 | 03/08/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-NM-1650-02-A-CRS-REPLY_0 | 03/08/16 | TPIT REPLY TO CLIENT COMMENTS TO ELECTRICAL INTERFACE POINT LIST | REF.E-2033/2544-00-NM-1650-02-A-CRS_0
CRS | MIDOR | 00 | BUILDINGS | 2544-00-NM-2000-01-D-CRS_0 | 23/07/16 | CLIENT COMMENTS TO BUILDING LIST | REF.T-2230\MIDOR-TPIT-E-2016-07-24_07-48
CRS | MIDOR | 00 | BUILDINGS | 2544-00-NM-2000-02-A-CRS_0 | 11/08/16 | CLIENT COMMENTS TO BUILDINGS TIE-IN LIST | REF.:T-02386/MIDOR-TPIT-00003 | TPIT RESPONSE REQUIRED |  | 2544-00-NM-2000-02-A-CRS-REPLY_0 TPIT-MIDOR-E-02236 | 12/09/16
CRS | MIDOR | 00 | BUILDINGS | 2544-00-NM-2000-02-A-CRS_1 | 17/10/16 | CLIENT COMMENTS TO BUILDINGS TIE-IN LIST | REF.:T-02386/MIDOR-TPIT-00003/94 | TPIT RESPONSE REQUIRED |  | 2544-00-NM-2000-02-A-CRS-REPLY_1 TPIT-MIDOR-T-00094 | 17/10/16
CRS | MIDOR | 00 | BUILDINGS | 2544-00-NM-2000-02-A-CRS_2 | 18/10/16 | CLIENT COMMENTS TO BUILDINGS TIE-IN LIST | REF.:T-02386/MIDOR-TPIT-T3/94/100
CRS | MIDOR | 00 | BUILDINGS | 2544-00-NM-2000-02-A-CRS-REPLY_0 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO BUILDINGS TIE-IN LIST | REF.:T-02386/TPIT-MIDOR-E-02236
CRS | MIDOR | 00 | PACKAGES | 2544-00-NM-2121-101-A-CRS_0 | 20/04/17 | CLIENT COMMENT TO LABORATORY EQUIPMENT LIST FOR REVAMPING | REF. TPIT-T-02575/MIDOR-T-00276 |  |  | 2544-00-NM-2121-101-A-CRS-REPLY_0 TPIT-MIDOR-E-02984 | 23/05/17
CRS | MIDOR | 00 | PACKAGES | 2544-00-NM-2121-101-A-CRS-REPLY_0 | 23/05/17 | TPIT REPLY TO CLIENT COMMENT TO LABORATORY EQUIPMENT LIST FOR REVAMPING | REF.T-02575/MIDOR-T-00276/TPIT-E-2984 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-NM-2121-101-B-CRS_0 | 23/06/17 | CLIENT COMMENT TO LABORATORY EQUIPMENT LIST FOR REVAMPING | REF. TPIT-T-02627/MIDOR-T-00355 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-A-CRS_0 | 29/06/16 | CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:T-2066/MIDOR-TPIT-E-2016-06-29_10-54 | TPIT RESPONSE REQUIRED |  | 2544-00-NM-9904-A-CRS-REPLY_0 | 01/07/16
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-A-CRS_1 | 19/07/16 | CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:T-2066/MIDOR-TPIT-E-2016-07-19_12-00 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01981/2544-00-NM-9904-A-CRS-REPLY_1 | 25/07/16
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-A-CRS_2 | 28/07/16 | CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:T-2066/MIDOR-TPIT-E-2016-07-31_15-27
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-A-CRS-REPLY_0 | 01/07/16 | TPIT REPLY TO CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:E-1898/2544-00-NM-9904-A-CRS_0
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-A-CRS-REPLY_1 | 25/07/16 | TPIT REPLY TO CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:E-1981/2544-00-NM-9904-A-CRS_1 | OWNER RESPONSE REQUIRED |  | 2544-00-NM-9904-A-CRS_2 / MIDOR-TPIT-E-2016-07-31_15-27 | 28/07/16
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-B-CRS-REPLY_0 | 04/08/16 | TPIT REPLY TO CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:E-2057/2544-00-NM-9904-B-CRS_0
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-C-CRS_0 | 04/08/16 | CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:T-2393/MIDOR-TPIT-E-2016-08-04_15-01 | TPIT RESPONSE REQUIRED |  | 2544-00-NM-9904-C-CRS-REPLY_0 TPIT-MIDOR-E-02056 | 05/08/16
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-C-CRS_1 | 07/08/16 | CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:T-2393/MIDOR-TPIT-E-2016-08-07_13-30 | TPIT RESPONSE REQUIRED |  | 2544-00-NM-9904-C-CRS-REPLY_1 TPIT-MIDOR-E-02055 | 08/08/16
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-C-CRS-REPLY_0 | 05/08/16 | TPIT REPLY TO CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:E-2056/2544-00-NM-9904-C-CRS_0
CRS | MIDOR | 00 | START UP | 2544-00-NM-9904-C-CRS-REPLY_1 | 08/08/16 | TPIT REPLY TO CLIENT COMMENTS TO SPECIAL ACTIVITIES LIST | REF:E-2055/2544-00-NM-9904-C-CRS_1
CRS | MIDOR | 00 | PLANNING | 2544-00-PLG-311-A-CRS_0 | 06/06/16 | CLIENT COMMENTS TO UNIT 00 EPC LEVEL 3 SCHEDULE (PRELIMINARY) | REF:T-1924/MIDOR-TPIT-E-2016-06-10_17-23
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-PP-118-A-CRS_0 | 25/04/16 | CLIENT COMMENTS TO UNIT 00 - PERMITTING PLAN | REF: TPIT-MIDOR-T-01446 | TPIT RESPONSE REQUIRED |  | 2544-00-PP-118-A-CRS-REPLY_0 TPIT-MIDOR-E-01512 | 02/05/16
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-PP-118-A-CRS-REPLY_0 | 02/05/16 | TPIT REPLY TO CLIENT COMMENTS PERMITTING PLAN | REF: 2544-00-PP-118-A-CRS_0/E-01512
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-PP-120-A-CRS_0 | 01/06/16 | CLIENT COMMENTS TO AS BUILT DOCUMENTATION PROCEDURE | REF:T-1885/MIDOR-TPIT-E-2016-06-01_13-23 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01824/2544-00-PP-120-A-CRS-REPLY_0 | 17/06/16
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-PP-120-A-CRS_1 | 01/06/16 | CLIENT COMMENTS TO AS BUILT DOCUMENTATION PROCEDURE | REF:T-1885/MIDOR-TPIT-E-2016-06-01_14-36 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01825 | 17/06/16
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-PP-120-A-CRS_2 | 01/06/16 | CLIENT COMMENTS TO AS BUILT DOCUMENTATION PROCEDURE | REF:T-1885/MIDOR-TPIT-E-2016-06-02_08-32 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01826 | 17/06/16
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-PP-120-A-CRS-REPLY_0 | 17/06/16 | TPIT REPLY TO CLIENT COMMENTS TO AS BUILT DOCUMENTATION PROCEDURE | REF:E-1824/2544-00-PP-120-A-CRS_0
CRS | MIDOR | 00 | PIPING | 2544-00-PP-126-0-CRS_0 | 24/03/16 | CLIENT COMMENTS TO UNIT 00 - ACCESS&MAINTENANCE FOR UNIT | REF:T-1311/MIDOR-TPIT-E-2016-04-11_06-30 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-1371/2544-00-PP-126-0-CRS-REPLY_0 | 13/04/16
CRS | MIDOR | 00 | PIPING | 2544-00-PP-126-0-CRS-REPLY_0 | 13/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - ACCESS & MAINTENANCE FOR UNIT | REF: E-1371/2544-00-PP-126-0-CRS-REPLY_0
CRS | MIDOR | 00 | PIPING | 2544-00-PP-127-0-CRS_0 | 28/05/16 | CLIENT COMMENTS TO PIPING TIE-INS PROCEDURE | RE T-01300/MIDOR-TPIT-E-2016-05-31_13-57
CRS | MIDOR | 00 | PIPING | 2544-00-PP-127-0-CRS-REPLY_0 | 16/10/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING TIE-INS PROCEDURE | REF:T-01300/TPIT-MIDOR-E-02509
CRS | MIDOR | 00 | PIPING | 2544-00-PP-127-1-CRS_0 | 09/06/16 | CLIENT COMMENTS TO PIPING TIE-INS PROCEDURE | REF:T-1919/MIDOR-TPIT-E-2016-06-10_10-51 | TPIT RESPONSE REQUIRED |  | 2544-00-PP-127-1-CRS-REPLY_0 TPIT-MIDOR-E-02239 | 04/10/16
CRS | MIDOR | 00 | PIPING | 2544-00-PP-127-1-CRS-REPLY_0 | 04/10/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING TIE-INS PROCEDURE | REF:T-1919/TPIT-MIDOR-E-02239
CRS | MIDOR | 00 |  | 2544-00-PP-202-2-CRS_0 | 2018-04-18 | CLIENT COMMENTS TO PROCESS HAZARD ANALYSIS (PHA) PROCEDURE | REF:T-02893/ MIDOR-TPIT-T-00469 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENT
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-PP-202-A-CRS_0 | 06/06/16 | CLIENT COMMENTS TO PROCESS HAZARD ANALYSIS (PHA) PROCEDURE | REF: MIDOR-TPIT-T-00015 | TPIT RESPONSE REQUIRED |  | 2544-00-PP-202-A-CRS-REPLY _0 TPIT-MIDOR-E-02170 | 27/09/16
CRS | MIDOR | 00 | HSE DESIGN | 2544-00-PP-202-A-CRS-REPLY _0 | 27/09/16 | TPIT REPLY CLIENT COMMENTS TO PROCESS HAZARD ANALYSIS (PHA) PROCEDURE | REF:MIDOR-TPIT-T-0015/TPIT-MIDOR-E-02170
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-PP-811-0-CRS_0 | 28/07/17 | CLIENT COMMENTS TO PREPARATION OF CONS,PRECOM QUALITY DOSSIER | REF:T-0224/MDR-TPIT-T-00374 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-PP-814-A-CRS_0 | 16/03/16 | CLIENT COMMENTS TO PROCEDURE FOR PIPING ACTIVITIES MANAGEMENT WITH EASY PIPING | REF:T-1055/MIDOR-TPIT-E-2016-03-16_22-08 | TPIT RESPONSE REQUIRED |  | 2544-00-PP-814-A-CRS-REPLY_0 | 17/03/16
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-PP-814-A-CRS-REPLY_0 | 16/03/16 | TPIT REPLY TO CLIENT COMMENTS TO PROCEDURE FOR PIPING ACTIVITIES MANAGEMENT WITH EASY PIPING | REF: 2544-00-PP-814-A-CRS_0/E-01139
CRS | MIDOR | 00 |  | 2544-00-PP-817_0-CRS_0 | 2018-03-02 | CLIENT COMMENT TO ENERGY ISOLATION- LOCK OUT AND TAG OUT PROCEDURE | REF.: T-2715/MIDOR-0449 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 |  | 2544-00-PP-817_A-CRS_0 | 2018-02-15 | CLIENT COMMENT TO ENERGY ISOLATION- LOCK OUT AND TAG OUT PROCEDURE | REF.: T-1930/MIDOR-0444 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 |  | 2544-00-PP-818_A-CRS_0 | 2018-02-19 | CLIENT COMMENT TO SITE HSE TRAINING PLAN | REF.: T-1930/MIDOR-00444 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 |  | 2544-00-PP-859_A-CRS_0 | 2018-02-19 | CLIENT COMMENT TO SITE STRUCTRUE WORKING PLATFORMS AND GRATING REMOVAL | REF.: T-1930/MIDOR-00444 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 |  | 2544-00-PP-860_A-CRS_0 | 2018-02-19 | CLIENT COMMENT TO SITE TRAFFIC PLAN | REF.: T-1930/MIDOR-00444 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 | START UP | 2544-00-PP-901-A-CRS_0 | 02/08/16 | CLIENT COMMENTS TOPRECOMMISSIONING,COMMISSIONING, START-UP AND INITIAL OPERATION EXECUTION PLAN | REF:T-2280/MIDOR-TPIT-E-2016-08-02_12-19 |  |  | 2544-00-PP-901-A-CRS-REPLY_0 | 08/08/16
CRS | MIDOR | 00 | START UP | 2544-00-PP-901-A-CRS_1 | 04/05/17 | CLIENT COMMENTS TOPRECOMMISSIONING,COMMISSIONING, START-UP AND INITIAL OPERATION EXECUTION PLAN | REF:T-2280/MIDOR-TIPIT-T-00300 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 | START UP | 2544-00-PP-901-A-CRS-REPLY_0 | 08/08/16 | TPIT REPLY TO CLIENT COMMENTS TO PRECOMMISSIONING COMMISSIONING STAR-UP AND INITIAL OPERATION EXECUTION PLAN | REF: MIDOR-TPIT-E-2016-08-02_12-19
CRS | MIDOR | 00 | START UP | 2544-00-PP-903-A-CRS_0 | 18/03/16 | CLIENT COMMENTS TO UNIT 00 - HANDOVER PROCEDURE | REF:T-1006/MIDOR-TPIT-E-2016-03-18_21-41 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01384/2544-00-PP-903-A-CRS-REPLY_0 | 30/03/16
CRS | MIDOR | 00 | START UP | 2544-00-PP-903-A-CRS-REPLY_0 | 30/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - HANDOVER PROCEDURE | REF: E-01384/2544-00-PP-903-A-CRS_0
CRS | MIDOR | 00 | START UP | 2544-00-PP-903-B-CRS_0 | 08/05/16 | CLIENT COMMENTS TO UNIT 00 - HANDOVER PROCEDURE | REF:T-1598/MIDOR-TPIT-E-2016-05-08_11-43 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01885 / 2544-00-PP-903-B-CRS-REPLY_0 | 31/05/16
CRS | MIDOR | 00 | START UP | 2544-00-PP-903-B-CRS-REPLY_0 | 31/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - HANDOVER PROCEDURE | REF: E-01885/2544-00-PP-903-B-CRS_0
CRS | MIDOR | 00 | START UP | 2544-00-PP-903-C-CRS_0 | 29/08/17 | CLIENT COMMENTS TO HANDOVER PROCEDURE | REF:T-2032/MIDOR-TPIT-T-00381 | CLOSED |  | APPROVED/CLOSED PROCEDURE
CRS | MIDOR | 00 | START UP | 2544-00-PP-910-A-CRS_0 | 04/09/16 | CLIENT COMMENTS TO CONSTR. PRECOM. COMMISSIONING START-UP INITIAL OPERATION AND PERFORMANCE TEST SPLIT OF WORK AND RESP. | REF:T-2457/MIDOR-TPIT-T-00019 | TPIT RESPONSE REQUIRED |  | 2544-00-PP-910-A-CRS-REPLY_0 TPIT-MIDOR-E-02152 | 16/09/16
CRS | MIDOR | 00 | START UP | 2544-00-PP-910-A-CRS_1 | 29/08/17 | CLIENT COMMENTS TO CONSTR,PRECOMM,COMMISS,START-UP,INITIAL OP. AND PERFORM TEST SPLIT OF WORK AND RESPONSABILITY | REF:T-2457/MIDOR-TPIT-T-00381 | CLOSED |  | APPROVED/CLOSED PROCEDURE
CRS | MIDOR | 00 | START UP | 2544-00-PP-910-A-CRS-REPLY_0 | 16/09/16 | TPIT REPLY TO CLIENT COMMENTS TO CON.PRECOM. COM.START-UP INITIAL OPERATION AND PERFORMANCE TEST SPLIT OF WORK AND RESP. | REF:T-2457/TPIT-MIDOR-E-02152
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-1766/MIDOR-TPIT-E-2016-05-28_22-27 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01884 / 2544-00-PP-919-A-CRS-REPLY_0 | 15/06/16
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-A-CRS_1 | 28/05/16 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-1766/MIDOR-TPIT-E-2016-05-28_22-28 |  |  | TPIT-MIDOR-E-02099 / 2544-00-PP-919-A-CRS-REPLY_1 | 07/09/16
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-A-CRS_2 | 13/03/17 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND... | REF:E-2099/MIDOR-TPIT-T-00215 | CLOSED |  | APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-A-CRS-REPLY_0 | 15/06/16 | TPIT REPLY TO CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMM.,COMMISSIONING AND START UP REQU. AND PROCED. | REF:E-1884/2544-00-PP-919-A-CRS_0
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-A-CRS-REPLY_1 | 07/09/16 | TPIT REPLY TO CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND... | REF:E-2099/2544-00-PP-919-A-CRS_1 | CLOSED |  | 2544-00-PP-919-A-CRS_0 - MIDOR-TPIT-T-00215 APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-B-CRS_0 | 19/07/16 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-2211/MIDOR-TPIT-E-2016-07-27_16-49
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-B-CRS_1 | 30/07/16 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-2211/MIDOR-TPIT-E-2016-07-31_17-34
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-C-CRS_0 | 14/11/16 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-2469/MIDR-TIPIT-T-00124 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-C-CRS_1 | 24/02/17 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-2469//MIDR-TIPIT-T-00189 |  |  | 2544-00-PP-919-C-CRS-REPLY_1 TPIT-MIDOR-E-02749 | 09/03/17
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-C-CRS_2 | 28/03/17 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-2469//MIDR-TIPIT-T-00238 |  |  | 2544-00-PP-919-C-CRS-REPLY_2 TPIT-MIDOR-E-2823 | 30/03/17
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-C-CRS_3 | 04/04/17 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMM PROCED. | REF:T-2469//TPIT-E-2823/MIDOR-T-00249 | CLOSED
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-C-CRS-REPLY_1 | 09/03/17 | TPIT REPLY TO CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMM PROCED. | REF:T-2469//MIDR-T-00189/TPIT-E-2749 |  |  | 2544-00-PP-919-C-CRS_2 MIDOR-TPIT-T-00238 | 28/03/17
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-C-CRS-REPLY_2 | 30/03/17 | TPIT REPLY TO CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMM PROCED. | REF:T-2469//MIDR-T-00238/TPIT-E-2823 |  |  | 2544-00-PP-919-C-CRS_3 MIDOR-TPIT-T-00249 APPROVED CLOSED | 04/04/17
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-D-CRS_0 | 04/05/17 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING,COMMISSIONING AND START UP REQU. AND PROCED. | REF:T-2585/MIDR-TIPIT-T-00298 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-PP-919-D-CRS_1 | 18/09/17 | CLIENT COMMENTS TO TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING AND COMMISSIONING | REF:T-2585/MIDR-TIPIT-T-00400 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | START UP | 2544-00-PP-923-A-CRS_0 | 23/07/16 | CLIENT COMMENTS TO TRAINING PLAN | REF.T-2233\MIDOR-TPIT-E-2016-07-24_07-47
CRS | MIDOR | 00 | START UP | 2544-00-PP-923-A-CRS_1 | 27/07/16 | CLIENT COMMENTS TO TRAINING PLAN | REF.: 2544-00-PP-923-A-CRS-REPLY_0
CRS | MIDOR | 00 | START UP | 2544-00-PP-923-A-CRS-REPLY_0 | 26/07/16 | TPIT REPLY TO CLIENT COMMENTS TO TRAINING PLAN | REF:E-1987/2544-00-PP-923-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-00-PP-923-A-CRS_1/MIDOR-TPIT-E-2016-07-27_16-52 | 27/07/16
CRS | MIDOR | 00 | MACHINERY | 2544-00-PTS-0910-402-A-CRS-REPLY_0 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPEFCIFICATION FOR SUPPLY FOR VERTICAL SULPHUR PUMPS | REF.: TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-QCP-1600-51-A-CRS_0 | 07/03/16 | CLIENT COMMENTS TO UNIT 00 - QUALITY CONTROL PLAN | REF:T-0805/MIDOR-TPIT-E-2016-03-05_08-20
CRS | MIDOR | 00 | START UP | 2544-00-QCP-6800-51-A-CRS_0 | 06/03/16 | CLIENT COMMENTS TO UNIT 00 - QUALITY CONTROL PLAN | REF:T-0842/MIDOR-TPIT-E-2016-03-08_22-00 | TPIT RESPONSE REQUIRED |  | 2544-00-QCP-6800-51-A-CRS-REPLY_0 TPIT-MIDOR-E-01531 | 06/05/16
CRS | MIDOR | 00 | START UP | 2544-00-QCP-6800-51-A-CRS-REPLY_0 | 06/05/16 | TPIT REPLY TO CLIENT UNIT 00 - QUALITY CONTROL PLAN | REF: 2544-00-QCP-6800-51-A-CRS_0/E-0842
CRS | MIDOR | 00 | START UP | 2544-00-QCP-6800-51-C-CRS_0 | 2018-01-29 | CLIENT COMMENTS TO QUALITY CONTROL PLAN UNIT 00 | REF:T-2833/MIDOR-TPIT-T-00433 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-RFQ-0270-101-A-CRS_0 | 10/10/16 | CLIENT COMMENTS TO MATERIAL REQUISITION (RFQ) FOR API SEPARATORS, DAF PACK & SLUGE BELT PRESS | REF: MIDOR -TPIT-T-00078 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-RFQ-0470-R02-0-CRS_0 | 14/09/16 | CLIENT COMMENTS TO REQUEST FOR QUOTATION FOR INTERNALS FOR EXISTING REACTORS (REVAMPING) | MIDOR-TPIT-T-00035
CRS | MIDOR | 00 | PVHE | 2544-00-RFQ-0570-R02-A-CRS-REPLY_1 | 02/02/17 | TPIT REPLY TO CLIENT COMMENTS TO INTERNALS FOR EXISTING COLUMNS (REVAMPING) | REF.:MOM-00133 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-RFQ-0710-R01-B-CRS-REPLY_0 | 22/05/17 | TPIT REPLY TO CLIENT COMMENTS TO REQUEST FOR QUOTATION FOR MOTOR AND FANS EXISTING AIRCOOLERS | REF: TPIT-MIDOR MOM-00134 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-RFQ-0811-R01-B-CRS-REPLY_0 | 06/07/17 | TPIT REPLY TO CLIENT COMMENTS TO REQUEST FOR QUOTATION FOR MISCELLANEA COMPONENTS (REVAMPING) | REF: TPIT-MIDOR MOM-00135 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-RFQ-0910-002-A-CRS_0 | 30/09/16 | CLIENT COMMENTS TO MR FOR SUBMIERSIBLE PUMPS | REF.: MIDOR-TPIT-T-00064
CRS | MIDOR | 00 | MACHINERY | 2544-00-RFQ-0910-R01-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO CENTRIFUGAL PUMPS (IMPELLERS) | REF.: MIDOR-TPIT-T-00029
CRS | MIDOR | 00 | MACHINERY | 2544-00-RFQ-0910-R03-A-CRS_0 | 08/09/16 | CLIENT COMMENTS TO CENTRIFUGAL PUMPS HIGH SPEED (REVAMP) | REF.: MIDOR-TPIT-T-00022 | CLOSED |  | TPIT-MIDOR-MOM-00129 - APPROVED/CLOSED | 27/02/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-RFQ-0910-R03-A-CRS-REPLY_0 | 27/02/17 | CLIENT COMMENTS TO CENTRIFUGAL PUMPS HIGH SPEED (REVAMP) | REF.:TPIT-MIDOR-MOM-00129 | CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-RFQ-0932-101-B-CRS_0 | 02/12/16 | CLIENT COMMENTS TO MR FOR PROGRESSIVE CAVITY PUMPS | REF.: MIDOR-TPIT-T-00141 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | MACHINERY | 2544-00-RFQ-0940-101-A-CRS_0 | 26/05/16 | CLIENT COMMENTS TO MR FOR PROPORTIONING PUMPS | REF.: MIDOR-TPIT-T-00064
CRS | MIDOR | 00 | MACHINERY | 2544-00-RFQ-1040-402-A-CRS_0 | 30/06/16 | CLIENT COMMENTS TO MR FOR AIR BLOWRS 2544-00-MR-1040-402_A | REF.: MIDOR-TPIT-T-00034
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-RFQ-1530-01-A-CRS_0 | 03/10/16 | CLIENT COMMENTS TO MR FOR COMMUNICATION SYSTEMS | REF.: MIDOR-TPIT-T-00065
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-RFQ-1682-01-A-CRS_0 | 13/09/16 | CLIENT COMMENTS TO RFQ 1682-01 FOR ELECTRICAL HEAT TRACING SYSTEM | MIDOR-TPIT-T-00028 | OWNER RESPONSE REQUIRED |  | TPIT-MIDOR-E-02144 | 20/09/16
CRS | MIDOR | 00 | PROCESS | 2544-00-RFQ-2630-01-A-CRS_0 | 26/09/16 | CLIENT COMMENTS TO RFQ 2630-001 FOR INERT CERAMIC BALL | MIDOR-TPIT-T-00073 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-RFQ-4046-001-C-CRS_0 | 30/03/17 | CLIENT COMMENTS TO RFQ 4046-001 FOR DOSING SYSTEM | MIDOR-TPIT-T-00244 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-RFQ-4046-R01-A-CRS_0 | 14/03/17 | CLIENT COMMENTS TO RFQ 4046-R01 FOR DOSING SYSTEM (REVAMPING) | MIDOR-TPIT-T-00224 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-RFQ-4118-01-A-CRS_0 | 26/09/16 | CLIENT COMMENTS TO RFQ 4118-001 FOR FUEL GAS PREAPARATION SYSTEMS | MIDOR-TPIT-T-00074 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-RFQ-4123-01-A-CRS_0 | 01/09/16 | CLIENT COMMENTS TO RFQ 4123-001 FOR EMERGENCY DIESEL GENERATOR | MIDOR-TPIT-T-00057 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-RR-801-0-CRS_0 | 08/06/16 | CLIENT COMMENTS TO UNIT 00 CONSTRUCTABILITY WORKSHOP REPORT | REF:T-1955/MIDOR-TPIT-E-2016-06-10_16-36 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-L-00037 | 10/06/16
CRS | MIDOR | 00 | CONSTRUCTION | 2544-00-RR-801-0-CRS_1 | 08/06/16 | CLIENT COMMENTS TO UNIT 00 CONSTRUCTABILITY WORKSHOP REPORT | REF:T-1955/MIDOR-TPIT-E-2016-06-10_16-36 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-L-00037 | 10/06/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-RT-1500-02-B-CRS_0 | 06/04/17 | CLIENT COMMENT TO SITE SURVEY REPORT FOR DCS EQUIPMENTS | REF. T-2572/MIDOR-TPIT-T-00258 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-RT-1500-02-B-CRS_1 | 30/05/17 | CLIENT COMMENT TO SITE SURVEY REPORT FOR DCS EQUIPMENTS | REF. T-2572/MDR-TPIT-T-258/337 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-RT-1500-06-A-CRS_0 | 28/09/17 | CLIENT COMMENT TO SITE SURVEY REPORT FOR COMMUNICATION EQUIPMENTS SPARE AVAILABILITY | REF. T-2717/MDR-TPIT-T-00402 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-RT-1600-01-A-CRS_0 | 16/03/17 | CLIENT COMMENT TO CRS FOR ELECTRICAL POWER CONSUMPTION FROM UPS | REF:T-02531/MIDORT-T-00222 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-SOW-9000-02-B-CRS_0 | 04/04/17 | CLIENT COMMENT TO RESPONSIBILITY MATRIX FOR SUBCONTRACTOR SOW COMMISSIONING | REF. T-2291/MIDOR-T-00250 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-SOW-9000-02-B-CRS_1 | 11/05/17 | CLIENT COMMENT TO RESPONSIBILITY MATRIX FOR SUBCONTRACTOR SOW COMMISSIONING | REF. T-2291/TPIT-E-0906/MIDOR-T-00331 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-SOW-9000-02-B-CRS_2 | 30/08/17 | CLIENT COMMENT TO RESPONSIBILITY MATRIX FOR SUBCONTRACTOR SOW COMMISSIONING | REF. T-2291/MIDOR-T-00382 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | START UP | 2544-00-SOW-9000-02-B-CRS-REPLY_0 | 03/05/17 | TPIT REPLY TO CLIENT COMMENT TO RESPONSIBILITY MATRIX FOR SUBCONTRACTOR SOW COMMISSIONING | REF. T-2291/MIDOR-T-00250/TPIT-E-0906 |  |  | 2544-00-SOW-9000-02-B-CRS_1/ MIDOR-TPIT-T-00311 REVIEWED WITH COMMENTS | 11/05/17
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0110-001-B-CRS_0 | 04/07/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR FIRED HEATERS | REF:T-0539/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0110-R01-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR FIRED HEATER REVAMPING | REF:T-0675/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0127-401-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR INCINERATOR STEAM SUPERHEATER | REF.: MIDOR-TPIT-T-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0150-101-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR AUXILIARY STEAM BOILER | REF:T-0271/MIDOR-TPIT-E-2016-07-31_16-44 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0150-101-A-CRS-REPLY_0 | 02/03/17 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR AUXILIARY STEAM BOILERS | REF: MOM-00082/E-02709/T-00271 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0168-401-A-CRS_0 | 21/07/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR THERMAL REACTOR REQUISITION | REF.:MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0172-401-A-CRS_0 | 06/10/16 | CLIENT COMMENTS TO TO PARTICULAR TECHNICAL SPECIFICATION FOR STACK | REF.: MIDOR-TPIT-T-00077 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0172-401-A-CRS_1 | 14/10/16 | CLIENT COMMENTS TO TO PARTICULAR TECHNICAL SPECIFICATION FOR STACK | REF.: MIDOR-TPIT-T-00097 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0182-101-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR DERRICK SUPPORTED ELEVATED FLARE | REF.T-00892/MIDOR-TPIT-0021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0191-401-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR THERMAL REACTOR BURNER | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SP-0191-402-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR INCINERATOR BURNERS | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-0210-101-B-CRS_0 | 02/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR DEMINERALIZATION AND ULTRAFILTRATION PACKAGE | REF:T-1497/MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-0310-201-B-CRS_0 | 02/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR COOLING TOWERS | REF: MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED |  | 2544-00-SP-0310-201-B-CRS-REPLY_0 | 17/10/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-0310-201-B-CRS-REPLY_0 | 17/10/16 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR COOLING TOWERS | REF:T-1888/2544-00-SP-0310-201-B-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00105 DTD 08/02/2017
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0411-101-A-CRS_0 | 09/06/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR LOW ALLOY REACTORS | REF:T-0045/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0411-101-A-CRS-REPLY_0 | 21/09/16 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR LOW ALLOY REACTORS | REF:T-0045/TPIT-MIDOR-MOM-00078
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0470-101-A-CRS_0 | 06/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF.: MIDOR-TPIT-T-00024 | TPIT RESPONSE REQUIRED |  | 2544-00-SP-0470-101-A-CRS-REPLY_0/TPIT-MIDOR-E-2171 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0470-101-A-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF.: E-2171/2544-00-SP-0470-101-A-CRS_0 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0511-001-A-CRS_0 | 20/06/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0232/MIDOR-TPIT-E-2016-07-31_16-44 | TPIT RESPONSE REQUIRED |  | 2544-00-SP-0511-001-A-CRS-REPLY_0 TPIT-MIDOR-MOM-00083 | 10/08/16
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0511-001-A-CRS-REPLY_0 | 10/08/16 | TPIT REPLY CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0232/TPIT-MIDOR-MOM-00083
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0570-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR PROPRIETARY INTERNAL FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0233/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0570-002-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR INTERNALS FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-0159/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0610-001-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:TPIT-MIDOR-T-01043/PMC-MIDOR-E-0052
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0610-001-B-CRS_1 | 26/07/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR HIGH PRESSURE AND SPECIAL MATERIAL SHELL AND TUBE H.E. | REF:ED-0019-M-T-0162/MIDOR-TPIT-T-00013 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0610-001-B-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TOCLIENT COMMENTS TO PART. TECHNICAL SPECIFICATION FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:E-2023/2544-00-SP-0610-001-B-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00091 DTD 07/07/2017
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0610-103-B-CRS_0 | 22/06/16 | CLIENTE COMMENTS TO PARTICULAR TECHNICAL SPC FOR HIGH PERFORMANCE TUBES FOR HEAT EXCHANGERS | REF.:T-808/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0610-403-A-CRS_0 | 31/08/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR SULPHUR CONDENSERS | REF:ED-0025/MIDOR-TPIT-T-00017 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0710-001-B-CRS_0 | 27/07/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-00566/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-SP-0710-001-B-CRS-REPLY_0 | 27/01/17 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/MIDOR-T-00020/MOM-00097
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-0851-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR VACUUM UNIT PACKAGE | REF: T-00157/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SP-0910-402-A-CRS_0 | 30/06/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR VERTICAL SULPHUR PUMPS (2544-00-MR-0910-402) | REF:ED-0032/MIDOR-TPIT-T-00022 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SP-0920-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR RECIPROCATING PUMPS | REF:T-01013/MIDOR-TPIT-T-00040
CRS | MIDOR | 00 | MACHINERY | 2544-00-SP-0931-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SP FOR PROPORTIONING PUMPS | REF:T-00257/MIDOR-TPIT-T-00064 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SP-1013-201-A-CRS_0 | 17/06/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR INTEGRALLY GEARED COMPRESSOR 41-K-04-N | REF:T-00312/MIDOR-TPIT-T-00022
CRS | MIDOR | 00 | MACHINERY | 2544-00-SP-1020-001-A-CRS_0 | 10/06/16 | CLIENT COMMENTS TO SP RECIPROCATING COMPRESSORS | REF:T-0145/PMC-MIDOR-E-0059 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SP-1031-101-A-CRS_0 | 26/05/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR ROTARY SCREW COMPRESSORS | REF:T-1073/MIDOR-TPIT-T-00012 | CLOSED |  | 2544-00-SP-1031-101-0-CRS-REPLY_0 TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-SP-1031-101-A-CRS-REPLY_0 | 23/12/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR ROTARY SCREW COMPRESSORS | REF:T-1073/MIDOR-T-0012/TPIT-E-2539 | CLOSED |  | TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | PROCESS | 2544-00-SP-1040-402-A-CRS-REPLY_0 | 04/04/17 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR COMBUSTION AIR BLOWERS | REF: TPIT-MIDOR MOM-00139 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PROCESS | 2544-00-SP-1040-402-A-CRS-REPLY_1 | 04/04/17 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR COMBUSTION AIR BLOWERS | REF: TPIT-MIDOR MOM-00139 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-SP-1515-003-A-CRS_0 | 02/03/16 | CLIENT COMMENTS TO EXTENT OF SUPPLY FOR MMS | REF:T-0859/MIDOR-TPIT-E-2016-03-03_07-33
CRS | MIDOR | 00 | PVHE | 2544-00-SP-2520-101-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR STORAGE TANKS ASSEMBLED ON SITE | REF: TPIT-MIDOR-00413/TPIT-MIDOR-E-01523
CRS | MIDOR | 00 | PVHE | 2544-00-SP-2520-101-A-CRS-REPLY_1 | 02/02/17 | TPIT REPLY TO CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR STORAGE TANKS ASSEMBLED ON SITE | REF: T-00413/TPIT-MIDOR MOM-00136 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-4110-101-A-CRS_0 | 06/10/17 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR MODULAR LPG TREATMENT UNIT (UNIT 25) | REF:T-02710/MIDOR-TPIT-T-00406
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-4123-01-A-CRS_0 | 01/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR ELECTRICITY DIESEL GENERATOR | REF:MIDOR-TPIT-T-00057
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-4141-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR DESALTER PACKAGES | REF:T-0174/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | PACKAGES | 2544-00-SP-4171-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPC FOR INSTRUMENT AIR DRYING PACKAGE | REF: T-00255/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-0-CRS_0 | 23/07/16 | CLIENT COMMENTS TO SPARE PARTS PHILOSOPHY | REF:T-2212/MIDOR-TPIT-E-2016-07-24_07-48
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-1-CRS_0 | 24/08/17 | CLIENT COMMENTS TO SPARE PARTS PHILOSOPHY | REF: T-02615/MDR-TPIT-T-00379 | CLOSED |  | 2544-00-SP-9200-01-1-CRS-REPLAY_0 | 05/12/17
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-1-CRS-REPLAY_0 | 05/12/17 | CLIENT COMMENTS TO SPARE PARTS PHILOSOPHY | REF: T-02615/MDR-T-00379/TPIT-E-03519 | CLOSED
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-A-CRS_0 | 21/03/16 | CLIENT COMMENTS TO SPARE PARTS PHILOSOPHY | REF: TPIT-MIDOR-T-00210 | TPIT RESPONSE REQUIRED |  | 2544-00-SP-9200-01-A-CRS-REPLY_0 | 25/03/16
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-A-CRS-REPLY_0 | 25/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - SPARE PARTS PHILOSOPHY | REF:MIDOR-E-2016-01-03_13-42/TPIT-E-1279
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-B-CRS_0 | 19/04/16 | CLIENT COMMENTS TO SPARE PARTS PHILOSOPHY | REF: TPIT-MIDOR-T-01392
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-B-CRS_1 | 20/04/16 | CLIENT COMMENTS TO SPARE PARTS PHILOSOPHY | REF: TPIT-MIDOR-T-01392
CRS | MIDOR | 00 | START UP | 2544-00-SP-9200-01-B-CRS_2 | 24/04/16 | CLIENT COMMENTS TO SPARE PARTS PHILOSOPHY | REF: TPIT-MIDOR-T-01392
CRS | MIDOR | 00 | START UP | 2544-00-SP-9901-01-A-CRS_0 | 21/03/16 | CLIENT COMMENTS TO MAINTENANCE PHILOSOPHY | REF: TPIT-MIDOR-T-00211 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01331/2544-00-SP-9901-01-A-CRS-REPLY_0 | 07/04/16
CRS | MIDOR | 00 | START UP | 2544-00-SP-9901-01-A-CRS-REPLY_0 | 29/03/16 | TPIT REPLY TO CLIENT COMMENTS TO MAINTENANCE PHILOSOPHY | REF: TPIT-MIDOR-T-00211
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0110-001-A-CRS_0 | 04/07/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR FIRED HEATERS | REF:T-0158/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0110-R01-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR FIRED HEATER REVAMPING | REF:T-0675/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0127-401-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR INCINERATOR STEAM SUPERHEATER | REF.: MIDOR-TPIT-T-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0150-101-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR AUXILIARY STEAM BOILER | REF:T-0271/MIDOR-TPIT-E-2016-07-31_16-44 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0150-101-A-CRS-REPLY_0 | 02/03/17 | TPIT REPLY TO CLIENT COMMENTS TO SCOPE OF SUPPLY STEAM BOILERS | REF: MOM-00082/E-02709/T-00271 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0168-401-A-CRS_0 | 21/07/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR THERMAL REACTOR REQUISITION | REF.:MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0172-401-A-CRS_0 | 06/10/16 | CLIENT COMMENTS TO TO SR FOR STACK | REF.: MIDOR-TPIT-T-00077 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0172-401-A-CRS_1 | 14/10/16 | CLIENT COMMENTS TO TO SR FOR STACK | REF.: MIDOR-TPIT-T-00097 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0182-101-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO SCOPE OF WORK FOR DERRICK SUPPORTED ELEVATED FLARE | REF.T-00892/MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0191-401-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR THERMAL REACTOR BURNER | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-SR-0191-402-A-CRS_0 | 09/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR INCINERATOR BURNERS | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | PACKAGES | 2544-00-SR-0210-101-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR DEMINERALIZATION AND ULTRAFILTRATION PACKAGE | REF:T-1497/MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-SR-0310-201-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR COOLING TOWERS | REF: T-00216/MIDOR-TPIT-T-00021
CRS | MIDOR | 00 | PVHE | 2544-00-SR-0610-001-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:TPIT-MIDOR-T-01043/PMC-MIDOR-E-0052
CRS | MIDOR | 00 | PVHE | 2544-00-SR-0610-001-B-CRS_1 | 26/07/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:ED-0019-M-T-0162/MIDOR-TPIT-T-00013 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-SR-0610-001-B-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO SCOPE OF SUPPLY FOR HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:E-2023/2544-00-SR-0610-001-B-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00091 DTD. 7/07/2017
CRS | MIDOR | 00 | PVHE | 2544-00-SR-0610-403-A-CRS_0 | 31/08/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR SULPHUR CONDENSERS | REF:ED-0025/MIDOR-TPIT-T-00017 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-SR-0851-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR VACUUM UNIT PACKAGE | REF: T-00157/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-0910-402-A-CRS_0 | 27/06/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR VERTICAL SULPHUR PUMPS (2544-00-MR-0910-402) | REF:ED-0032/MIDOR-TPIT-T-00022 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-0910-402-A-CRS-REPLY_0 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO SCOPE OF SUPPLY FOR VERTICAL SULPHUR PUMPS | REF.: TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-0920-001-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR RECIPROCATING PUMPS | REF:T-01013/MIDOR-TPIT-T-00040
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-0931-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR PROPORTIONING PUMPS | REF:T-00257/MIDOR-TPIT-T-00064 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-1011-101-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR CENTRIFUGAL COMPRESSORS | REF:T-0173/MIDOR-TPIT-E-2016-03-07_08-16
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-1013-201-A-CRS_0 | 17/06/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR API 672 INTEGRALLY GEARED AIR COMPRESSORS | REF:T-00312/MIDOR-TPIT-T-00022
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-1020-001-A-CRS_0 | 10/06/16 | CLIENT COMMENTS TO SR RECIPROCATING COMPRESSORS | REF:T-0145/PMC-MIDOR-E-0059 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-1020-301-A-CRS-REPLY_0 | 23/05/17 | TPIT REPLY TO CLIENT COMMENTS TO SCOPE OF SUPPLY FOR RECIPROCATING COMPRESSORS FOR AUXILIARY SERVICE | REF: T-2214/TPIT-MIDOR MOM-00137 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-1031-101-A-CRS_0 | 26/05/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR ROTARY SCREW COMPRESSORS | REF:T-1073/MIDOR-TPIT-T-00012 | CLOSED |  | 2544-00-TSR1031-101-0-CRS-REPLY_0 TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-1031-101-A-CRS-REPLY_0 | 23/12/16 | TPIT REPLY TO CLIENT COMMENTS TO SCOPE OF SUPPLY FOR ROTARY SCREW COMPRESSORS | REF:T-1073/MIDOR-TPIT-T-00012 | CLOSED |  | TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-SR-1040-402-A-CRS-REPLY_0 | 04/04/17 | TPIT REPLY TO CLIENT COMMENTS TO SCOPE OF SUPPLY FOR COMBUSTION AIR BLOWERS | REF: TPIT-MIDOR MOM-00139 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PACKAGES | 2544-00-SR-4110-101-A-CRS_0 | 06/10/17 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR MODULAR LPG TREATMENT UNIT (UNIT 25) | REF:T-02710/MIDOR-TPIT-T-00406
CRS | MIDOR | 00 | PACKAGES | 2544-00-SR-4123-01-A-CRS_0 | 01/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR ELECTRICITY DIESEL GENERATOR | REF:MIDOR-TPIT-T-00057
CRS | MIDOR | 00 | PACKAGES | 2544-00-SR-4141-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR DESALTER PACKAGES | REF:T-0174/MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | PACKAGES | 2544-00-SR-4171-201-A-CRS_0 | 15/09/16 | CLIENT COMMENTS TO SCOPE OF SUPPLY FOR INSTRUMENT AIR DRYING PACKAGE | REF: T-00255/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-STC-1691-00-B-CRS_0 | 17/04/16 | CLIENT COMMENTS TO GROUNDING SYSTEM INSTALLATION STANDARDS | REF:T-1441/MIDOR-TPIT-E-2016-04-17_05-53 |  |  | TPIT-MIDOR-E-01452/2544-00-STC-1691-00-B-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-STC-1691-00-B-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO GROUNDING SYSTEM INSTALLATION STANDARDS | REF: E-1452/2544-00-STC-1691-00-B-CRS_0
CRS | MIDOR | 00 | PIPING | 2544-00-STD-1380-01-2-CRS_0 | 11/04/16 | CLIENT COMMENTS TO DESIGN SPECIFICATION FOR PIPING DESIGN II - STANDARD DESIGN DRAWINGS | REF T-1356/MIDOR-TPIT-E-2016-04-11_15-01 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01439/2544-00-STD-1380-01-2-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 00 | PIPING | 2544-00-STD-1380-01-2-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DESIGN SPECIFICATION FOR PIPING DESIGN II - STANDARD DESIGN DRAWINGS | REF E-01439/2544-00-STD-1380-01-2-CRS_0
CRS | MIDOR | 00 | PIPING | 2544-00-STD-1380-02-2-CRS_0 | 11/04/16 | CLIENT COMMENTS TO DESIGN SPECIFICATION FOR STEAM TRACING STANDARD DRAWINGS | T-1356/MIDOR-TPIT-E-2016-04-11_15-01 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01439/2544-00-STD-1380-02-2-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 00 | PIPING | 2544-00-STD-1380-02-2-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DESIGN SPECIFICATION FOR STEAM TRACING STANDARD DRAWINGS | REF E-01439/2544-00-STD-1380-02-2-CRS_0
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT 0910-R03-0-CRS_0 | 08/09/16 | CLIENT COMMENTS TO TBT CENTRIFUGAL PUMPS HIGH SPEED (REVAMP) | REF.: MIDOR-TPIT-T-00022 | CLOSED |  | TPIT-MIDOR-MOM-00129 - APPROVED/CLOSED | 27/02/17
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0110-001-B-CRS_0 | 04/07/16 | CLIENT COMMENTS TO TBT FOR FIRED HEATERS | REF:T-1532/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0110-R01-B-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR FIRED HEATER REVAMPING | REF:TPIT-MDOR-T-02073-MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0127-401-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR INCINERATOR STEAM SUPERHEATER | REF.: MIDOR-TPIT-T-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0150-101-A-CRS-REPLY_0 | 02/03/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION AUXILIARY STEAM BOILERS | REF: MOM-00082/E-02709 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0150-101-B-CRS_0 | 03/05/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR STEAM BOILER | REF:T-1485/MIDOR-TPIT-E-2016-05-03_18-16
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0150-101-B-CRS_1 | 12/07/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR STEAM BOILER | REF:T-1485/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0150-101-B-CRS-REPLY_0 | 02/03/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION AUXILIARY STEAM BOILERS | REF: MOM-00082/E-02709/T-01485 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0168-401-0-CRS_0 | 12/07/16 | CLIENT COMMENTS TO MATERIAL REQUISITION FOR THERMAL REACTOR REQUISITION | REF.: T-2156/MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0182-101-A-CRS_0 | 02/09/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR DERRICK SUPPORTED ELEVATED FLARE | REF.T-00892/MIDOR-TPIT-00021
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0191-401-0-CRS_0 | 09/09/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR THERMAL REACTOR BURNER | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | HEATERS AND BOILERS | 2544-00-TBT-0191-402-0-CRS_0 | 09/09/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR INCINERATOR BURNERS | REF.: MIDOR-TPIT-T-00026
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-0210-101-0-CRS_0 | 02/09/16 | CLIENT COMMENTS TO TBT FOR DEMINERALIZATION AND ULTRAFILTRATION PACKAGE | REF:T-2170/MIDOR-TPIT-T-00021 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-0310-201-0-CRS_0 | 02/09/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION COOLING TOWER PACKAGE UNIT 47 | REF.: T-02389/TPIT-MIDOR-T-00021 | OWNER RESPONSE REQUIRED |  | 2544-00-TBT-0310-201-0-CRS-REPLY_0 | 17/10/16
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-0310-201-0-CRS-REPLY_0 | 17/10/16 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION COOLING TOWER PACKAGE UNIT 47 | REF: T-2389/2544-00-TBT-0310-201-0-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00105 DTD 08/02/2017
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0411-101-0-CRS_0 | 11/07/16 | CLIENT COMMENTS TO TBT FOR LOW ALLOY REACTORS | REF:MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0411-101-0-CRS-REPLY_0 | 21/09/19 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR LOW ALLOY REACTORS | REF:ID-478/TPIT-MIDOR-MOM-00078
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0411-101-0-CRS-REPLY_0 | 2019-09-21 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR LOW ALLOY REACTORS | REF:ID-478/TPIT-MIDOR-MOM-00078
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0470-101-0-CRS_0 | 06/09/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF.: MIDOR-TPIT-T-00024 | TPIT RESPONSE REQUIRED |  | 2544-00-TBT-0470-101-0-CRS-REPLY_0/TPIT-MIDOR-E-2171 | 26/09/16
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0470-101-0-CRS-REPLY_0 | 26/09/16 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS | REF.:E-2171/2544-00-TBT-0470-101-A-CRS_0 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0470-R02-0-CRS_0 | 14/09/16 | CLIENT COMMENTS TO TBT FOR INTERNALS FOR REACTORS (REVAMP) | T-01944/MIDOR-TPIT-T-00035
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0511-001-1-CRS_0 | 04/07/16 | CLIENT COMMENTS TO TBT FOR MAIN SHOP ASSEMBLED COLUMNS | REF:ED-019/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0511-001-2-CRS_0 | 12/09/17 | CLIENT COMMENTS TO TBT FOR MAIN SHOP ASSEMBLED COLUMNS (UNIT 05, 08, 20) | REF:T-2655/MIDOR-TPIT-T-00394 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0570-001-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR PROPRIETARY INTERNAL FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-01944/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0570-002-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-01944/MIDOR-TPIT-T-00046
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0570-002-1-CRS_0 | 18/09/17 | CLIENT COMMENTS TO TBT FOR INTERNALS OF MAIN SHOP ASSEMBLED COLUMNS (U-08 & U-20) | REF:T-02655/MIDOR-TPIT-T-00398 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0570-R02-0-CRS-REPLY_0 | 02/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR INTERNALS FOR EXISTING COLUMNS (REVAMPING) | REF.:MOM-00133 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0570-R02-1-CRS_0 | 18/09/17 | CLIENT COMMENTS TO TBT FOR INTERNALS FOR EXISTING COLUMNS (REVAMPING) | REF:T-02653/MIDOR-TPIT-T-00398 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0610-001-1-CRS_0 | 25/08/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR SHELL AND TUBE HEAT EXCHANGERS | REF:ED-0019-M-T-02296/MIDOR-TPIT-T-00013 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0610-001-1-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO FOR TECHNICAL BID TABULATION HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:E-2023/2544-00-TBT-0610-001-B-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00091 DTD 07/07/2017
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0610-001-2-CRS_0 | 11/09/17 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR HP & SPECIAL SHELL AND TUBE HEAT EXCHANGERS (UNIT 05, 08, 18, 20) | REF:T-02655/MIDOR-TPIT-T-00394 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0610-103-0-CRS_0 | 29/06/16 | CLIENTE COMMENTS TO TBT FOR HIGH PERFORMANCE TUBES FOR HEAT EXCHANGERS | REF.:ED-19/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0610-403-0-CRS_0 | 31/08/16 | CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR SULPHUR CONDENSERS | REF:ED-0025/MIDOR-TPIT-T-00017 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0710-001-0-CRS_0 | 06/09/16 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-02160/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0710-001-0-CRS-REPLY_0 | 27/01/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:T-2160/MIDOR-TPIT-T-00020/MOM-00097
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0710-001-1-CRS_0 | 11/09/17 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS (UNIT 05, 18, 20 ,46) | REF:T-02655/MIDOR-TPIT-T-00394 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0710-R01-0-CRS-REPLY_0 | 22/05/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR MOTOR AND FANS EXISTING AIRCOOLERS | REF: TPIT-MIDOR MOM-00134 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0810-001-0-CRS-REPLY_0 | 27/01/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR HP PRESSURE VESSELS | REF:E-00805/MIDOR-TPIT-T-00013/MOM-00086 | CLOSED |  | APPROVED/CLOSED WITH TPIT-MIDOR-MOM-00086 DTD 09/02/2017
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0811-101-0-CRS_0 | 29/07/16 | CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR HIGH PRESSURE VESSELS | REF:ED-0019/MIDOR-TPIT-T-00013 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-0811-R01-0-CRS-REPLY_0 | 06/07/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR MISCELLANEA COMPONENTS (REVAMPING) | REF: TPIT-MIDOR MOM-00135 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-0851-001-1-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR VACUUM UNIT PACKAGE | REF: T-02203/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0910-402-0-CRS_0 | 07/07/16 | CLIENT COMMENTS TO TBT FOR SULPHUR PUMP | REF:ED-0032/T-02158/MIDOR-TPIT-T-00022 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0910-402-0-CRS-REPLY_0 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR VERTICAL SULPHUR PUMPS | REF.: T-2158/TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0910-402-0-CRS-REPLY_1 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR VERTICAL SULPHUR PUMPS | REF.: T-2158/TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0910-R01-0-CRS_0 | 09/09/16 | CLIENT COMMENTS TO 2544-00-TBT-0910-R01_0 CENTRIFUGAL PUMPS (REVAMP) | REF.: MIDOR-TPIT-T-00029
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0910-R01-0-CRS_1 | 16/09/16 | CLIENT COMMENTS TO 2544-00-TBT-0910-R01_0 CENTRIFUGAL PUMPS (REVAMP) | REF:T-2204/MIDOR-TPIT-E-2016-09-19_07-36
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0910-R02-0-CRS_0 | 31/08/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR CENTRIFUGAL PUMPS (REVAMPING GABBIONETA) (O.B.E. PURPOSE) | REF:T-2202/MIDOR-TPIT-T-00012
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0910-R03-0-CRS-REPLY_0 | 27/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT CENTRIFUGAL PUMPS HIGH SPEED (REVAMP) | REF.: TPIT-MIDOR-MOM-00129 | CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0920-001-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR RECIPROCATING PUMPS | REF:T-01945/MIDOR-TPIT-T-00040
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0920-001-1-CRS_0 | 05/09/17 | CLIENT COMMENTS TO TBT FOR RECIPROCATING PUMPS | REF:T-02658/MIDOR-TPIT-T-00385 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-0931-201-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR PROPORTIONING PUMPS | REF:T-02392/MIDOR-TPIT-T-00064 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1011-102-0-CRS_0 | 15/10/16 | CLIENT COMMENTS TO TABULATIONS FOR WET GAS COMPRESSOR | REF:ID-00738/MIDOR-E-2016-10-17_10-37
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1011-102-0-CRS-REPLY_0 | 02/12/16 | TPIT REPLY TO CLIENT COMMENTS TO TABULATIONS FOR WET GAS COMPRESSOR | REF:ID-00738/TPIT-MIDOR-MOM-00122 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1013-201-0-CRS_0 | 19/06/16 | CLIENT COMMENTS TO TABULATIONS FOR OBE PURPOSE - INTEGRALLY GEARED AIR COMPRESSOR | REF:T-1739/MIDOR-TPIT-E-2016-06-19_10-42
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1013-201-0-CRS_1 | 01/07/16 | CLIENT COMMENTS TO TBT FOR INTEGRALLY-GEARED AIR COMPRESSOR | REF:T-01739/MIDOR-TPIT-T-00022 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1013-201-0-CRS-REPLY_0 | 21/06/16 | TPIT REPLY TO CLIENT COMMENTS TO TABULATIONS FOR OBE PURPOSE - INTEGRALLY GEARED AIR COMPRESSOR | REF:E-1847/2544-00-TBT-1013-201-0-CRS_0
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1020-301-0-CRS-REPLY_0 | 23/05/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR RECIPROCATING COMPRESSORS FOR AUXILIARY SERVICE | REF: T-2512/TPIT-MIDOR MOM-00137 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1031-101-0-CRS_0 | 18/08/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ROTARY SCREW COMPRESSOR MR 1031-101 (O.B.E. PURPOSE) | REF:T-2271/MIDOR-TPIT-T-00012 | CLOSED |  | 2544-00-TBT-1031-101-0-CRS-REPLY_0 TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1031-101-0-CRS-REPLY_0 | 23/12/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ROTARY SCREW COMPRESSOR MR 1031-101 (O.B.E. PURPOSE) | REF:T-2271/MIDOR-T-0012/TPIT-E-2539 | CLOSED |  | TPIT-MIDOR-MOM-00121 APPROVED /CLOSED | 04/04/17
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1040-402-0-CRS_0 | 30/06/16 | CLIENT COMMENTS TO TBT FOR AIR BLOWRS | REF.: MIDOR-TPIT-T-00034
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1040-402-0-CRS-REPLY_0 | 04/04/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID EVALUATION FOR COMBUSTION AIR BLOWERS | REF: T-2159/TPIT-MIDOR MOM-00139 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | MACHINERY | 2544-00-TBT-1040-402-0-CRS-REPLY_1 | 04/04/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID EVALUATION FOR COMBUSTION AIR BLOWERS | REF: T-2159/TPIT-MIDOR MOM-00139 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1511-01-0-CRS_0 | 29/08/16 | CLIENT COMMENTS TO TBT 1511-01 ICSS TECHNICAL TABULATION | REF:T-2387/MIDOR-TPIT-T-00076
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1511-01-0-CRS_3 | 07/04/17 | CLIENT (PMC) COMMENTS TO TBT 1511-01 ICSS TECHNICAL TABULATION | REF:T-2387/MIDOR-TPIT-T-00263
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1511-01-0-CRS_4 | 02/06/17 | CLIENT (PMC) COMMENTS TO ICSS TECHNICAL TABULATION AND HONEYWELL REVISED OFFER | REF:T-2387/MIDOR-TPIT-T-00341 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1511-01-0-CRS-REPLY_0 | 16/10/16 | TPIT REPLY TO CLIENT COMMENTS TO TBT 1511-01 ICSS TECHNICAL TABULATION | REF:T-2387/MIDOR-T-00076/TPIT-E-02510 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1511-01-2-CRS_0 | 22/12/17 | CRS FOR TBT FOR ICSS | REF:T-2793/MIDOR-TPIT-T-00429 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1515-002-1-CRS_3 | 2018-07-24 | CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR F&G | REF:T-2858/MID-443/TPIT-E-3629/MID-473 | CLOSED |  | APPROVED/CLOSD | 2018-07-24
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1515-02-0-CRS_0 | 2018-02-19 | CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR F&G | REF:T-2858/MIDOR-TPIT-T-00443 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1515-02-1-CRS_2 | 2018-03-13 | CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR F&G | REF:T-2858/MIDOR-00443/00455 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1515-03-0-CRS_0 | 20/09/16 | CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR MMS | REF:T-2387/MIDOR-TPIT-T-00061 | TPIT RESPONSE REQUIRED |  | 2544-00-TBT-1515-03-0-CRS-REPLY_0/TPIT-MIDOR-E-02212 | 03/10/16
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1515-03-0-CRS_1 | 05/10/16 | CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR MMS | REF:T-2387/MIDOR-TPIT-T-00071
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1515-03-0-CRS-REPLY_0 | 03/10/16 | TPIT REPLY TO CLIENT COMMENTS TO PRELIMINARY TECHNICAL BID TABULATION FOR MMS | REF:E-2212/2544-00-TBT-1515-03-0-CRS_0
CRS | MIDOR | 00 | INSTRUMENTATION | 2544-00-TBT-1531-01-0-CRS_0 | 04/04/16 | CLIENT COMMENTS TO TEMPORARY ACCESS CONTROL SYSTEM TECHNICAL TABULATION | REF:MIDOR-TPIT-T-00245 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1611-01-B-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR GROUNDING AND LIGHTING MATERIAL | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1611-01-B-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR GROUNDING AND LIGHTNING MATERIAL | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1620-01-C-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR POWER MATERIAL | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1620-01-C-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ELECTRICAL POWER MATERIALS | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1621-01-B-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR ELECTRICAL POWER AND CONTROL CABLES | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1621-01-B-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ELECTRICAL POWER AND CONTROL CABLES | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1622-01-B-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR ELECTRICAL CONDUIT | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1622-01-B-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ELECTRICAL CONDUIT | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1623-01-B-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR ELECTRICAL CABLE TRAYS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1623-01-B-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ELECTRICAL CABLE TRAYS | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1630-01-A-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR LIGHTINGH MATERIALS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1630-01-A-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR LIGHTING MATERIALS | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1641-01-A-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR POWER TRANSFORMERS & NEUTRAL GROUNDING RESISTORS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1641-01-A-CRS_1 | 18/09/17 | CLIENT COMMENTS TO TBT FOR POWER TRANSFORMERS & NEUTRAL GROUNDING RESISTORS | REF: MIDOR-TPIT-T-00398 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1652-01-B-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR MEDIUM VOLTAGE SWITCHGEARS & CAPACITORS BANKS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1652-01-B-CRS_1 | 18/09/17 | CLIENT COMMENTS TO TBT FOR MEDIUM VOLTAGE SWITCHGEARS & CAPACITOR BANKS | REF: MIDOR-TPIT-T-00398 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1654-01-A-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR LOW VOLTAG SWITHCHGEARS &BUS DUCTS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1654-01-A-CRS_1 | 18/09/17 | CLIENT COMMENTS TO TBT FOR LOW VOLTAGE SWITCHGEARS & BUS DUCTS | REF: MIDOR-TPIT-T-00398 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1661-01-A-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR MONITORING AND CONTROL SYSTEM EMCS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1661-01-A-CRS_1 | 18/09/17 | CLIENT COMMENTS TO TBT FOR ELECTRICAL MONITORING AND CONTROL SYSTEM EMCS | REF: MIDOR-TPIT-T-00398 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1671-01-B-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR AC UPS SYSTEMS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1671-01-B-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR AC UPS SYSTEMS | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1672-01-B-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR DC UPS SYSTEMS | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1672-01-B-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR DC UPS SYSTEMS | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1682-01-A-CRS_0 | 11/01/17 | CLIENT COMMENTS TO PRELIMINARY TBT FOR ELECTRICAL HEAT TRACING SYSTEM | REF: MIDOR-TPIT-T-00157 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1682-01-A-CRS-REPLY_0 | 17/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ELECTRICAL HEAT TRACING SYSTEM | REF: E-02672 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | ELECTRICAL | 2544-00-TBT-1684-01-A-CRS_0 | 06/09/17 | CLIENT COMMENTS TO CATHODIC PROTECTION SYSTEM | REF: MIDOR-TPIT-T-00389 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PVHE | 2544-00-TBT-2520-001-0-CRS-REPLY_1 | 02/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR STORAGE TANKS ASSEMBLED ON SITE | REF: T-02160/TPIT-MIDOR MOM-00136 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4110-101-0-CRS_0 | 12/01/18 | CLIENT COMMENTS TO TBT MODULAR LPG TREATMENT UNIT 25 OBE PURPOSE | REF:T-2822/MIDOR-TPIT-T-00431 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4110-101-0-CRS_1 | 2018-02-19 | CLIENT COMMENTS TO TBT MODULAR LPG TREATMENT UNIT 25 OBE PURPOSE | REF:T-2822/MIDOR-TPIT-T-00444 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4110-101-1-CRS_0 | 2018-03-28 | CLIENT COMMENTS TOTBT FOR MODULAR LPG TREATEMENT UNIT (UNIT 25) OBE PURPOSE | REF:E-03653/MIDOR-TPIT-T-00466 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4110-101-1-CRS_1 | 2018-05-24 | CLIENT COMMENTS TOTBT FOR MODULAR LPG TREATEMENT UNIT (UNIT 25) OBE PURPOSE | REF:E-03653/MIDOR-T-466/MIDOR-T-470 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4111-001-0-CRS_0 | 09/09/16 | CLIENT COMMENTS TO TBT FOR PSA | REF:T-02096/MIDOR-TPIT-T-00042
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4141-201-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TBT FOR DESALTER PACKAGES | REF:TPIT-MDOR-T-02461-MIDOR-TPIT-T-00041
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4171-101-1-CRS_0 | 22/09/17 | CLIENT COMMENTS TO TBT FOR INSTRUMENT AIR DRYING PACKAGE | REF: T-02633/MIDOR-TPIT-T-00401 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4171-201-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR INSTRUMENT AIR DRYING PACKAGE | REF: T-00696/MIDOR-TPIT-T-00056 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PACKAGES | 2544-00-TBT-4234-101-0-CRS_0 | 22/09/17 | CLIENT COMMENTS TO TBT FOR WATER FILTRATION PACKAGE | REF: T-02659/MIDOR-TPIT-T-00401 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-TN-00023-1-CRS_0 | 30/07/16 | CLIENT COMMENTS TO TN FOR INSULATION AND FIREPROOFING DETAILS | REF:E-1953/MIDOR-TPIT-E-2016-07-31_08-09 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02021 / 2544-00-TN-00023-1-CRS-REPLY_0 | 01/08/16
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-TN-00023-1-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO TN FOR INSULATION AND FIREPROOFING DETAILS | REF.: 2544-00-TN-00023-1-CRS_0
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-TN-00026-1-CRS_1 | 21/04/16 | CLIENT COMMENTS TO TN FOR ASME STAMP APPLICABILITY | REF:T-1433/MIDOR-TPIT-E-2016-04-21_11-04 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 00 | PROJECT MANAGEMENT | 2544-00-TN-00026-1-CRS-REPLY_1 | 21/04/16 | TPIT REPLY TO CLIENT COMMENTS TO TN FOR ASME STAMP APPLICABILITY | REF:T-1433/T-E-16-04-21_11-04/E-1460
CRS | MIDOR | 01 | PROCESS | 2544-01-NM-0020-01-A-CRS_0 | 16/06/16 | CLIENT COMMENTS TO UNIT 01 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF:TPIT-MIDOR-T-01153/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02098 / 2544-01-NM-0020-01-A-CRS-REPLY_0 | 06/09/16
CRS | MIDOR | 01 | PROCESS | 2544-01-NM-0020-01-A-CRS-REPLY_0 | 06/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 01 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF: 2544-06-NM-0020-01-A-CRS_0
CRS | MIDOR | 02 | PROCESS | 2544-02-CN-0009-02-A-CRS_0 | 12/06/16 | CLIENT COMMENTS TO UNIT 02 - INTERLOCK DESCRIPTION | REF:T-1926/MIDOR-TPIT-E-2016-06-12_13-37 | TPIT RESPONSE REQUIRED |  | 2544-02-CN-0009-02-A-CRS-REPLY_0 TPIT-MIDOR-E-01801 | 14/06/16
CRS | MIDOR | 02 | PROCESS | 2544-02-CN-0009-02-A-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02 - INTERLOCK DESCRIPTION | REF:2544-02-CN-0009-02-A-CRS_0/-E-01801
CRS | MIDOR | 02 | PIPING | 2544-02-DW-0051-01-01-B-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 02-03-04 - HDT NAPTHA SPLITTER CATALYTIC REFORMING ZONE - PG DETAILED PLOT PLAN | REF:T-1274/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-0288/02889 2544-02-DW-0051-01-01-B-CRS-REPLY | 08/06/16
CRS | MIDOR | 02 | PIPING | 2544-02-DW-0051-01-01-B-CRS_1 | 26/09/16 | CLIENT COMMENTS TO UNIT 02-03-04 - HDT NAPTHA SPLITTER CATALYTIC REFORMING ZONE - PG DETAILED PLOT PLAN | REF:T-1274/MIDOR-TPIT-T-00051
CRS | MIDOR | 02 | PIPING | 2544-02-DW-0051-01-01-B-CRS-REPLY_0 | 06/08/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02-03-04 - HDT NAPTHA SPLITTER CATALYTIC REFORMING ZONE - PG DETAILED PLOT PLAN | E-2088/89-02-DW-0051-01-01-B-CRS_0/MOM65 | OWNER RESPONSE REQUIRED |  | 2544-02-DW-0051-01-B-CRS_1 MIDOR-TPIT-T-00051 (CLOSED) | 26/09/16
CRS | MIDOR | 02 | PIPING | 2544-02-DW-0051-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02-03-04 - HDT NAPTHA SPLITTER CATALYTIC REFORMING ZONE - PG DETAILED PLOT PLAN | REF.:T-1274/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 02 | INSTRUMENTATION | 2544-02-DW-1572-01-01-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 02 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1991/MIDOR-TPIT-E-2016-06-15_02-36
CRS | MIDOR | 02 | INSTRUMENTATION | 2544-02-DW-1572-01-01-B-CRS_1 | 06/02/17 | CLIENT COMMENTS TO UNIT 02 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1991/MIDOR-TPIT-T-00173
CRS | MIDOR | 02 | INSTRUMENTATION | 2544-02-DW-1572-01-01-B-CRS_2 | 16/02/17 | CLIENT COMMENTS TO UNIT 02 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1991/M-T-00173/T-E-2653/M-T-178
CRS | MIDOR | 02 | INSTRUMENTATION | 2544-02-DW-1572-01-01-B-CRS-REPLY_0 | 23/06/16 | TPIT-REPLY TO CLIENT COMMENTS TO UNIT 02 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1991/TPIT-MIDOR-E-01855
CRS | MIDOR | 02 | INSTRUMENTATION | 2544-02-DW-1572-01-01-B-CRS-REPLY_1 | 10/02/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1991/TPIT-MIDOR-T-173/TPIT-E-2653
CRS | MIDOR | 02 | INSTRUMENTATION | 2544-02-NM-1511-01-A-CRS_0 | 28/02/17 | CLIENT COMMENTS TO UNIT 02 IO LIST | REF.:00397/MIDOR-TPIT-T-00193
CRS | MIDOR | 02 | PVHE | 2544-02-SP-0570-01-PB-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 02 PROCESS DATA SHEET FOR STRIPPER - TRAYS AND INTERNALS 02-IT-01 | REF:T-1897/MIDOR-TPIT-E-2016-06-10_10-51 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01770 TPIT REPLY | 10/06/16
CRS | MIDOR | 02 | MACHINERY | 2544-02-SP-0910-03-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO UNIT 02 FOR STRIPPER REFLUX PUMP 02-P-04 | REF.:TPIT-MIDOR-T-01185 | CLOSED |  | 2544-02-SP-0910-03-PA-CRS-REPLY_0 MIDOR-TPIT-E-02542 | 23/12/17
CRS | MIDOR | 02 | MACHINERY | 2544-02-SP-0910-03-PA-CRS_1 | 20/04/17 | CLIENT COMMENTS TO UNIT 02 FOR STRIPPER REFLUX PUMP 02-P-04 | REF.:T-01185/TPIT-E-02542/MIDOR-T-00275 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 02 | MACHINERY | 2544-02-SP-0910-03-PA-CRS_2 | 10/07/17 | CLIENT COMMENTS TO DATA SHEET FOR STRIPPER REFLUX PUMP 02-P-04 | REF.:T-01185/TPIT-E-02542/MDR-T-275/359 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 02 | MACHINERY | 2544-02-SP-0910-03-PA-CRS-REPLY_0 | 23/12/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02 FOR STRIPPER REFLUX PUMP 02-P-04 | REF.:T-01185/TPIT-E-02542 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 03 | MACHINERY | 2544-03-SP-0910-01-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR 03-P-01-A/B NAPHTHA | REF:T-1108/MIDOR-TPIT-E-2016-03-28_21-39
CRS | MIDOR | 03 | MACHINERY | 2544-03-SP-0910-01-PA-CRS_1 | 20/04/17 | CLIENT COMMENTS TO DATA SHEET FOR 03-P-01-A/B NAPHTHA | REF:T-1108/TPIT-E-02542/MIDOR-TPIT-T-284 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 03 | MACHINERY | 2544-03-SP-0910-01-PA-CRS-REPLY_0 | 23/12/16 | CLIENT COMMENTS TO DATA SHEET FOR 03-P-01-A/B NAPHTHA | REF:T-1108/TPIT-E-02542 | CLOSED |  | 2544-03-SP-0910-01-PA-CRS_1 MIDOR-TPIT-T-00284 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 04 | PROCESS | 2544-04-CN-0009-02-A-CRS_0 | 12/06/16 | CLIENT COMMENTS TO UNIT 04 - INTERLOCK DESCRIPTION | REF:T-1927/MIDOR-TPIT-E-2016-06-12_13-52 | TPIT RESPONSE REQUIRED |  | 2544-04-CN-0009-02-A-CRS-REPLY_0 TPIT-MIDOR-E-01799 | 14/06/16
CRS | MIDOR | 04 | PROCESS | 2544-04-CN-0009-02-A-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 04 - INTERLOCK DESCRIPTION | REF:2544-04-CN-0009-02-A-CRS_0/-E-01799
CRS | MIDOR | 04 | PROCESS | 2544-04-NM-0020-01-B-CRS_0 | 21/06/16 | CLIENT COMMENTS TO UNIT 04 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE - REVAMPED PLATFORM | REF:TPIT-MIDOR-T-01590/PMC-MIDOR-E-0063
CRS | MIDOR | 04 | MACHINERY | 2544-04-SP-0910-02-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO UNIT 04 - PROCESS D/S | REF:T-1182/MIDOR-TPIT-E-2016-03-27_22-18
CRS | MIDOR | 04 | MACHINERY | 2544-04-SP-0910-02-PA-CRS_1 | 20/04/17 | CLIENT COMMENTS TO UNIT 04 - PROCESS D/S | REF:T-1182/TPIT-E-02542/MIDOR-TPIT-T-284 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 04 | MACHINERY | 2544-04-SP-0910-02-PA-CRS-REPLY_0 | 23/12/16 | CLIENT COMMENTS TO UNIT 04 - PROCESS D/S | REF:T-1182/TPIT-E-02542 | CLOSED |  | 2544-04-SP-0910-02-PA-CRS_1 MIDOR-TPIT-T-00284 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 05 | PIPING | 2544-05-DW-0051-01-01-C-CRS_0 | 20/05/16 | CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | REF:T-1667/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02088/02089 2544-05-DW-0051-01-01-C-CRS-REPLY_0 | 10/06/16
CRS | MIDOR | 05 | PIPING | 2544-05-DW-0051-01-01-C-CRS_1 | 06/06/16 | CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | REF:TPIT-MIDOR-T-1667 | TPIT RESPONSE REQUIRED |  | 2544-05-DW-0051-01-01-C-CRS-REPLY_1 TPIT-MIDOR-E-02088/MOM-0065 | 08/07/16
CRS | MIDOR | 05 | PIPING | 2544-05-DW-0051-01-01-C-CRS_2 | 11/01/17 | CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | REF: T-1667/T-E/2088/MOM-0065/M-T-00160
CRS | MIDOR | 05 | PIPING | 2544-05-DW-0051-01-01-C-CRS-REPLY_0 | 10/06/16 | TPIT REPLY TO CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | E2088/2089-2544-05-DW-0051-01-01-C-CRS_0
CRS | MIDOR | 05 | PIPING | 2544-05-DW-0051-01-01-C-CRS-REPLY_1 | 08/07/16 | TPIT REPLY TO CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | REF: T-1667/TPIT-MIDOR-E-02088/MOM-0065
CRS | MIDOR | 05 |  | 2544-05-DW-0051-01-01-D-CRS_0 | 2018-03-06 | CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | REF:TPIT-2861/MIDOR-00451 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 05 |  | 2544-05-DW-0051-01-01-D-CRS_1 | 2018-04-05 | CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | REF:TPIT-2861/MIDOR-00451 | CLOSED |  | APPROVED CLOSED
CRS | MIDOR | 05 | PIPING | 2544-05-DW-0051-01-C-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO BLOCK P - ZONE PF - UNIT 05-06-12-16-39 - DETAILED PLOT PLAN | REF.:T-1667/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 05 | HSE DESIGN | 2544-05-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 05-06-12-16-39 FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-0402/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0510-02-PA-CRS_0 | 12/04/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR LPG STRIPPER 05-T-52 | REF:T-1377/MIDOR-TPIT-E-2016-04-13_12-28
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0510-05-PA-CRS_0 | 28/04/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR NET GAS SCRUBBER 05-T-02 | REF:TPIT-MIDOR-T-01499 | TPIT RESPONSE REQUIRED |  | 2544-05-SP-0510-05_PA-CRS-REPLY_0 TPIT-MIDOR-E-01793 | 13/06/16
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0510-05-PA-CRS-REPLY_0 | 13/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET FOR NET GAS SCRUBBER 05-T-02 | REF.T-01499-22544-05-SP-0510-05-PA-CRS_0
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0570-02-PA-CRS_0 | 12/04/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR LPG STRIPPER TRAYS 6 INTERNALS 05-IT-52 | REF:T-1377/MIDOR-TPIT-E-2016-04-13_12-28 | TPIT RESPONSE REQUIRED |  | 2544-05-SP-0570-02-PA-CRS-REPLY_0 TPIT-MIDOR-E-01791 | 13/06/16
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0570-02-PA-CRS-REPLY_0 | 13/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET FOR LPG STRIPPER TRAYS 6 INTERNALS 05-IT-52 | REF.T-01377-2544-05-SP-0570-02-PA-CRS_0
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0570-04-PA-CRS_0 | 12/04/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR DEISOHEXANIZER - TRAYS & INTERNALS 05-IT-03 | REF:T-1377/MIDOR-TPIT-E-2016-04-13_12-28 |  |  | 2544-05-SP-0570-04-PA-CRS-REPLY_0 TPIT-MIDOR-E-01791/02555 | 13/06/16
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0570-04-PA-CRS_1 | 04/01/17 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET FOR LPG STRIPPER TRAYS 6 INTERNALS 05-IT-52 | REF.T-1377/TPIT-E-2555/MIDOR-TPIT-T-197
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0570-04-PA-CRS-REPLY_0 | 04/01/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET FOR LPG STRIPPER TRAYS 6 INTERNALS 05-IT-52 | REF.T-01377/TPIT-MIDOR E-02555 |  |  | 2544-05-SP-0570-04-PA-CRS_1 - TPIT-MIDOR-T-00197 | 01/03/17
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-06-PA-CRS_0 | 09/03/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATASHEET 05-E-08 | REF:T-0618/MIDOR-TPIT-E-2016-03-09_22-23
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-06-PA-CRS-REPLY_0 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS D/S | REF.E-01291-2544-05-SP-0610-06-PA-CRS_0
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-11-PA-CRS_0 | 08/03/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATASHEET 05-E-51 | REF:T-0822/MIDOR-TPIT-E-2016-03-08_22-06
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-12-PA-CRS_0 | 09/03/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATASHEET 05-E-10 | REF:T-0618/MIDOR-TPIT-E-2016-03-09_22-23 | TPIT RESPONSE REQUIRED |  | 2544-05-SP-0610-12-PA-CRS-REPLY_0 | 04/04/16
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-12-PA-CRS-REPLY_0 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS D/S | REF.E-01291-2544-05-SP-0610-12-PA-CRS_0
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-17-PA-CRS_0 | 09/03/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATASHEET 05-E-60 | REF:T-0618/MIDOR-TPIT-E-2016-03-09_22-23 | TPIT RESPONSE REQUIRED |  | 2544-05-SP-0610-17-PA-CRS-REPLY_0 | 04/04/16
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-17-PA-CRS-REPLY_0 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS D/S | REF.E-01291-2544-05-SP-0610-17-PA-CRS_0
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-18-PA-CRS_0 | 09/03/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATASHEET 05-E-61 | REF:T-0618/MIDOR-TPIT-E-2016-03-09_22-23 | TPIT RESPONSE REQUIRED |  | 2544-05-SP-0610-18-PA-CRS-REPLY_0 | 04/04/16
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-18-PA-CRS-REPLY_0 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS D/S | REF.E-01291-2544-05-SP-0610-18-PA-CRS_0
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-19-PA-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR STABILIZER NET GAS CHILLER 05-E-62 | REF:T-1671/MIDOR-TPIT-E-2016-05-22_19-13 | TPIT RESPONSE REQUIRED |  | 2544-05-SP-0610-19-PA-CRS-REPLY_0 TPIT-MIDOR-E-01792 | 13/06/16
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-19-PA-CRS-REPLY_0 | 13/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET FOR STABILIZER NET GAS CHILLER 05-E-62 | REF.T-01671/2544-05-SP-0610-19-PA-CRS_0
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0610-20-PA-CRS_0 | 08/03/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATASHEET 05-E-64 | REF:T-0822/MIDOR-TPIT-E-2016-03-08_22-06
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0710-02-PB-CRS_0 | 19/05/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR STABILIZER CONDENSER 05-E-12 | REF:T-1636/MIDOR-TPIT-E-2016-05-21_01-13 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01834/2544-05-SP-0710-02-PB-CRS-REPLY_0 | 20/06/16
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0710-02-PB-CRS_1 | 07/03/17 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR STABILIZER CONDENSER 05-E-12 | REF:E-1834/MIDOR-TPIT-T-00206 |  |  | 2544-05-SP-0710-02-PB-CRS-REPLY_1 - MIDOR-TPIT-E-02744 | 08/03/17
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0710-02-PB-CRS_2 | 30/05/17 | CLIENT COMMENTS TO DATA SHEET FOR 05-E-12 | REF.:T-1636/MIDOR-TPIT-00336 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0710-02-PB-CRS-REPLY_0 | 20/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR STABILIZER CONDENSER 05-E-12 | REF:T-01636/TPIT-MIDOR-E-02555 |  |  | 2544-05-SP-0710-02-PB-CRS_1 - MIDOR-TPIT-T-00206 | 07/03/17
CRS | MIDOR | 05 | PVHE | 2544-05-SP-0710-02-PB-CRS-REPLY_1 | 08/03/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR STABILIZER CONDENSER 05-E-12 | REF:E-1834/MIDOR-T-00206/TPIT-E-2744 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0810-02-PA-CRS_0 | 23/05/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR STABILIZER RECEIVER - 05-V-06 | REF:T-1723/MIDOR-TPIT-E-2016-05-24_09-56
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0810-02-PA-CRS-REPLY_0 | 01/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR STABILIZER RECEIVER - 05-V-06 | REF:E-1725/2544-05-SP-0810-02-PA-CRS_0
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0810-03-PA-CRS_0 | 01/06/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR DRUM - DEISOPENTANIZER FEED SURGE DRUM 05-V-51 | REF:T-1790/MIDOR-TPIT-E-2016-06-01_11-00 |  |  | 2544-05-SP-0810-03-PA-CRS-REPLY_0 - TPIT-MIDOR E-02555 | 04/01/17
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0810-03-PA-CRS_1 | 01/03/17 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR DRUM - DEISOPENTANIZER FEED SURGE DRUM 05-V-51 | REF:T-1790/TPITE-2555/MIDOR-TPIT/T-00197 | CLOSED |  | APPROVED
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0810-03-PA-CRS-REPLY_0 | 04/01/17 | TPIT REPLY TO CLIENT COMMENTS TO PROCESS DATA SHEET FOR DRUM - DEISOPENTANIZER FEED SURGE DRUM 05-V-51 | REF:T-1790/TPIT-MIDOR-E-02555 |  |  | 2544-05-SP-0810-03-PA-CRS_0 - MIDOR-TPIT-T-00197 APPROVED/CLOSED | 01/03/17
CRS | MIDOR | 05 | MACHINERY | 2544-05-SP-0910-11-PB-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET | REF:T-1003/MIDOR-TPIT-E-2016-03-15_06-50
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0940-01-PA-CRS_0 | 25/05/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR CHLORIDE INJECTION PUMPS - 05-P-55 A/B | REF:T-1757/MIDOR-TPIT-E-2016-05-26_23-35
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0940-01-PA-CRS_1 | 27/05/16 | CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR CHLORIDE INJECTION PUMPS - 05-P-55 A/B | REF:T-1757/MIDOR-TPIT-E-2016-05-28_22-30 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01833/2544-05-SP-0940-01-PA-CRS-REPLY_0 | 20/06/16
CRS | MIDOR | 05 | PROCESS | 2544-05-SP-0940-01-PA-CRS-REPLY_0 | 20/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 PROCESS DATA SHEET FOR CHLORIDE INJECTION PUMPS - 05-P-55 A/B | REF:E-1833/2544-05-SP-0940-01-PA-CRS_1
CRS | MIDOR | 07 | PIPING | 2544-07-DW-0051-01-01-B-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 07 - KEROSENE HYDROTREATER ZONE PH - DETAILED PLOT PLAN | REF:T-1272/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02088/02089 2544-07-DW-0051-01-01-B-CRS-REPLY_0 | 10/06/16
CRS | MIDOR | 07 | PIPING | 2544-07-DW-0051-01-01-B-CRS_1 | 26/09/16 | CLIENT COMMENTS TO UNIT 07 - KEROSENE HYDROTREATER ZONE PH - DETAILED PLOT PLAN | REF:T-1272/MIDOR-TPIT-T-00051 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 07 | PIPING | 2544-07-DW-0051-01-01-B-CRS-REPLY_0 | 10/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 07 - KEROSENE HYDROTREATER ZONE PH - DETAILED PLOT PLAN | E-2088/89-2544-07-DW-0051-01-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-07-DW-0051-01-01-B-CRS_1 MIDOR-TPIT-T-00051 (CLOSED) | 26/09/16
CRS | MIDOR | 07 | PIPING | 2544-07-DW-0051-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 07 - KEROSENE HYDROTREATER ZONE PH - DETAILED PLOT PLAN | REF.:T-1272/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 07 | ELECTRICAL | 2544-07-DW-1622-01-01-A-CRS_0 | 08/03/16 | CLIENT COMMENTS TO UNIT 07 MAIN CABLE ROUTING | REF:T-0805/MIDOR-TPIT-E-2016-03-05_08-20 | TPIT RESPONSE REQUIRED |  | 2544-07-DW-1622-01-01-A-CRS-REPLY_0 | 17/03/16
CRS | MIDOR | 07 | ELECTRICAL | 2544-07-DW-1622-01-01-A-CRS-REPLY_0 | 17/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 07 MAIN CABLE ROUTING | REF:E-1211/2544-07-DW-1622-01-01-A-CRS_0
CRS | MIDOR | 07 | ELECTRICAL | 2544-07-DW-1622-01-01-B-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 07 MAIN CABLE ROUTING | REF:T-1435/MIDOR-TPIT-E-2016-04-17_05-51 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01992 / 2544-07-DW-1622-01-01-B-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 07 | ELECTRICAL | 2544-07-DW-1622-01-01-B-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 07 MAIN CABLE ROUTING | REF:E-1992/2544-07-DW-1622-01-01-B-CRS_0
CRS | MIDOR | 07 | ELECTRICAL | 2544-07-DW-1622-01-01-C-CRS_0 | 19/05/16 | CLIENT COMMENTS TO UNIT 07 MAIN CABLE ROUTING | REF:T-1729/MIDOR-TPIT-E-2016-05-11_19-34 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01994/2544-07-DW-1622-01-01-C-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 07 | ELECTRICAL | 2544-07-DW-1622-01-01-C-CRS_1 | 16/01/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 07 MAIN CABLE ROUTING | REF:E-1992/MIDOR-TPIT-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 07 | ELECTRICAL | 2544-07-DW-1622-01-01-C-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 07 MAIN CABLE ROUTING | REF:E-1992/2544-07-DW-1622-01-01-C-CRS_0
CRS | MIDOR | 07 | HSE DESIGN | 2544-07-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 07 - KEROSENE HYDROTREATER FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-0759/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 07 | HSE DESIGN | 2544-07-DW-1950-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 07 - KEROSENE HYDROTREATER FIRE AND GAS DETECTION LAYOUT | REF: TPIT-MIDOR-T-0759/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 07 | PROCESS | 2544-07-NM-0020-01-B-CRS_0 | 23/06/16 | CLIENT COMMENTS TO UNIT 07 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE - KERO HDT | REF:TPIT-MIDOR-T-01533/PMC-MIDOR-E-0063
CRS | MIDOR | 07 | PROCESS | 2544-07-NM-2100-01-A-CRS_0 | 13/06/16 | CLIENT COMMENTS TO TEST METHODS AND SAMPLE SCHEDULE FOR UNIT-07 | REF:T-1890/MIDOR-TPIT-E-2016-06-13_16-55 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01817/2544-07-NM-2100-01-A-CRS_0 | 15/06/16
CRS | MIDOR | 07 | PROCESS | 2544-07-NM-2100-01-A-CRS-REPLY_0 | 15/06/16 | TPIT REPLY TO CLIENT COMMENTS TO TEST METHODS AND SAMPLE SCHEDULE FOR UNIT-07 | REF:E-1817/2544-07-NM-2100-01-A-CRS_0
CRS | MIDOR | 07 | PVHE | 2544-07-SP-0470-01-PA-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 07 PROCESS DATA SHEET FOR REACTOR INTERNALS ITEM 07-IR-01 | REF:T-1613/MIDOR-TPIT-E-2016-05-09_09-24
CRS | MIDOR | 07 | MACHINERY | 2544-07-SP-0910-03-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO UNIT 07 - PROCESS D/S | REF:T-1107/MIDOR-TPIT-E-2016-03-27_22-15
CRS | MIDOR | 07 | MACHINERY | 2544-07-SP-0910-03-PA-CRS_1 | 20/04/17 | CLIENT COMMENTS TO UNIT 07 - PROCESS D/S | REF:T-1107/TPIT-E-02542/MIDOR-TPIT-T-284 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 07 | MACHINERY | 2544-07-SP-0910-03-PA-CRS-REPLY_0 | 23/12/16 | CLIENT COMMENTS TO UNIT 07 - PROCESS D/S | REF:T-1107/TPIT-E-02542 | CLOSED |  | 2544-07-SP-0910-03-PA-CRS_1 MIDOR-TPIT-T-00284 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 08 | PIPING | 2544-08-DW-0051-01-01-C-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF:T-1614/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-08-DW-0051-01-01-C-CRS-REPLY_1 TPIT-MIDOR-E-02088/MOM-0065 | 14/07/16
CRS | MIDOR | 08 | PIPING | 2544-08-DW-0051-01-01-C-CRS_1 | 26/09/16 | CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF:T-1614/MIDOR-TPIT-T-00051
CRS | MIDOR | 08 | PIPING | 2544-08-DW-0051-01-01-C-CRS-REPLY_1 | 14/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF: T-1614/TPIT-MIDOR-E-02088/MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-08-DW-0051-01-01-C-CRS_1 MIDOR-TPIT-T-00051 | 26/09/16
CRS | MIDOR | 08 |  | 2544-08-DW-0051-01-01-D-CRS_1 | 2018-04-05 | CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF:T-02860/MIDOR-00463 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 08 |  | 2544-08-DW-0051-01-01-E-CRS_0 | 2018-03-06 | CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF:T-02860/MIDOR-00451 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 08 | PIPING | 2544-08-DW-0051-01-C-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF.:T-1614/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 08 | PIPING | 2544-08-DW-0051-02-01-C-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF:T-1614/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 08 | PIPING | 2544-08-DW-0051-02-01-C-CRS-REPLY_0 | 20/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF: T-1273/MOM-0065 | OWNER RESPONSE REQUIRED |  | TPI-MIDOR-MOM-00065 | 10/06/16
CRS | MIDOR | 08 |  | 2544-08-DW-0051-02-01-D-CRS_0 | 2018-03-06 | CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF:T-02860/MIDOR-00451
CRS | MIDOR | 08 |  | 2544-08-DW-0051-02-01-D-CRS_1 | 2018-04-05 | CLIENT COMMENTS TO UNIT 08 BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF:T-02860/MIDOR-00463 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 08 | PIPING | 2544-08-DW-0051-02-C-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO BLOCK P - ZONE PC UNIT 08 - HYDROCRACKER - DETAILED PLOT PLAN | REF.:T-1614/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 08 | ELECTRICAL | 2544-08-DW-1622-01-01-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 08 - MAIN CABLE ROUTING | REF:T-0793/MIDOR-TPIT-E-2016-03-05_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01157/2544-08-DW-1622-01-01-A-CRS-REPLY_0 | 18/03/16
CRS | MIDOR | 08 | ELECTRICAL | 2544-08-DW-1622-01-01-A-CRS_1 | 16/01/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 08 - MAIN CABLE ROUTING | REF:T-00793/MIDOR-TPIT-T-00162
CRS | MIDOR | 08 | ELECTRICAL | 2544-08-DW-1622-01-01-A-CRS-REPLY_0 | 18/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 08 - MAIN CABLE ROUTING | REF:2544-08-DW-1622-01-01-A-CRS_0/E-1157
CRS | MIDOR | 08 | ELECTRICAL | 2544-08-DW-1622-01-02-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 00 - MAIN CABLE ROUTING | REF:T-0806/MIDOR-TPIT-E-2016-03-05_08-20 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01158/2544-08-DW-1622-01-02-A-CRS-REPLY_0 | 18/03/16
CRS | MIDOR | 08 | ELECTRICAL | 2544-08-DW-1622-01-02-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 08 - MAIN CABLE ROUTING | REF:T-00793/TPIT-E-1158/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 08 | ELECTRICAL | 2544-08-DW-1622-01-02-A-CRS-REPLY_0 | 18/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 08 - MAIN CABLE ROUTING | REF:2544-08-DW-1622-01-02-A-CRS_0/E-1158
CRS | MIDOR | 08 | HSE DESIGN | 2544-08-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 08 - HYDROCRACKER FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-0758/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 08 | HSE DESIGN | 2544-08-DW-1933-02-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 08 - HYDROCRACKER FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-0758/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 08 | HSE DESIGN | 2544-08-DW-1950-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 08 - HYDROCRACKER FIRE AND GAS DETECTION LAYOUT | REF: TPIT-MIDOR-T-0758/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 08 | HSE DESIGN | 2544-08-DW-1950-02-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 08 - HYDROCRACKER FIRE AND GAS DETECTION LAYOUT | REF: TPIT-MIDOR-T-0758/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 08 | PROCESS | 2544-08-NM-0020-01-A-CRS_0 | 24/06/16 | CLIENT COMMENTS TO UNIT 08 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF:TPIT-MIDOR-T-01207/PMC-MIDOR-E-0063
CRS | MIDOR | 08 | PROCESS | 2544-08-NM-0020-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE - | REF:E-2091/MIDOR-TPIT-E-2016-08-30_13-44
CRS | MIDOR | 08 | PROCESS | 2544-08-NM-0020-01-B-CRS-REPLY_1 | 02/09/17 | TPIT REPLY TO CLIENT COMMENTS TO MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE - | REF:E-2092/MIDTPIT-E-2016-08-30_13-44BIS
CRS | MIDOR | 08 | PIPING | 2544-08-NM-1350-01-A-CRS_0 | 30/08/16 | CLIENT COMMENTS TO UNIT 08 MECHANICAL TIE-IN LIST | REF: TPIT-MIDOR-T-1129/MIDOR-TPIT-T-0008 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02112 / 2544-08-NM-1350-01-A-CRS-REPLY_0 | 12/09/16
CRS | MIDOR | 08 | PIPING | 2544-08-NM-1350-01-A-CRS_1 | 04/10/16 | CLIENT COMMENTS TO UNIT 08 MECHANICAL TIE-IN LIST | REF:TPIT-MIDOR-T-1129/MIDOR-TPIT-T-00069
CRS | MIDOR | 08 | PIPING | 2544-08-NM-1350-01-A-CRS-REPLY_0 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 08 MECHANICAL TIE-IN LIST | REF:E-2112/2544-08-NM-1350-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-08-NM-1350-01-A-CRS_1 MIDOR-TPIT-T-00069 (CLOSED) | 04/10/16
CRS | MIDOR | 08 | PROCESS | 2544-08-SP-0510-05-PA-CRS_0 | 27/04/16 | CLIENT COMMENTS TO UNIT 08 - PROCESS DATA SHEET FOR STRIPPER 08-T-51 | REF:TPIT-MIDOR-T-01481
CRS | MIDOR | 08 | PROCESS | 2544-08-SP-0510-06-PA-CRS_0 | 27/04/16 | CLIENT COMMENTS TO UNIT 08 - PROCESS DATA SHEET FOR PRODUCT FRACTIONATOR 08-T-53 | REF:TPIT-MIDOR-T-01481
CRS | MIDOR | 08 | PVHE | 2544-08-SP-0610-01-PB-CRS_0 | 06/07/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR EFFLUENT MP STEAM GENERATOR - 08-E-26 | REF:TPIT-MIDOR-T-02218 | TPIT RESPONSE REQUIRED |  | 2544-08-SP-0610-01-PB-CRS-REPLY_0 | 02/09/16
CRS | MIDOR | 08 | PVHE | 2544-08-SP-0610-01-PB-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO PROCESS DATA SHEET FOR EFFLUENT MP STEAM GENERATOR - 08-E-26 | REF: 2544-08-SP-0610-01-PB-CRS_0/E-2086 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 08 | PVHE | 2544-08-SP-0610-08-PB-CRS_0 | 06/07/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR PRODUCT FRACTIONATOR BOTTOMS-MP STEAM EXCHANGER - 08-E-77 | REF:TPIT-MIDOR-T-02218
CRS | MIDOR | 08 | MACHINERY | 2544-08-SP-0910-09-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO UNIT 08 FOR KEROSENE PRODUCT PUMPS 08-P-57 A/B | REF.:TPIT-MIDOR-T-01221
CRS | MIDOR | 08 | MACHINERY | 2544-08-SP-0910-09-PA-CRS_1 | 20/04/17 | CLIENT COMMENTS TO UNIT 08 FOR KEROSENE PRODUCT PUMPS 08-P-57 A/B | REF.:T-1221/TPIT-E-2542/MIDOR-TPIT-T-285 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 08 | MACHINERY | 2544-08-SP-0910-09-PA-CRS-REPLY_0 | 23/12/16 | CLIENT COMMENTS TO UNIT 08 FOR KEROSENE PRODUCT PUMPS 08-P-57 A/B | REF.:T-1221/TPIT-E-2542 | CLOSED |  | 2544-08-SP-0910-09-PA-CRS_1 MIDOR-TPIT-T-00285 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 08 | MACHINERY | 2544-08-SP-0910-11-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO UNIT 08 FOR CHARGE PUMPS 08-P-01 A/B | REF.:TPIT-MIDOR-T-01199
CRS | MIDOR | 08 | PACKAGES | 2544-08-SP-4046-01-PA-CRS_0 | 11/07/17 | CLIENT COMMENTS TO MACHINERY DATA SHEET 08-PK-51 | REF:T-00584/MIDOR-TPIT-T-00360 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 0A | HEATERS AND BOILERS | 2544-0A-TBT-0110-001-B-CRS_0 | 04/07/16 | CLIENT COMMENTS TO TBT FOR FIRED HEATERS | REF:T-2173/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0511-001-0-CRS_0 | 04/07/16 | CLIENT COMMENTS TO TBT FOR MAIN SHOP ASSEMBLED COLUMNS | REF:ED-019/MIDOR-TPIT-E-2016-07-31_16-44
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0511-001-1-CRS_0 | 12/09/17 | CLIENT COMMENTS TO TBT FOR MAIN SHOP ASSEMBLED COLUMNS (UNIT 17, 19) | REF:T-2639/MIDOR-TPIT-T-00394 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0570-001-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR PROPRIETARY INTERNAL FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-02057/MIDOR-TPIT-T-00046
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0570-002-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR MAIN SHOP ASSEMBLED COLUMNS | REF:T-02120/MIDOR-TPIT-T-00046
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0610-001-0-CRS_0 | 25/08/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR MR 0610-001 - SP MATERIAL SHELL AND TUBE HEAT EXCHANGER (UNIT 17) | REF:ED-0019-M-T-02296/MIDOR-TPIT-T-00013 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0610-001-0-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO FOR TECHNICAL BID TABULATION HP AND SPECIAL MATERIAL SHELL AND TUBE HEAT EXCHANGERS | REF:E-2023/2544-0A-TBT-0610-001-B-CRS_0 | CLOSED |  | CLOSED WITH TPIT-MIDOR-MOM-00091 DTD 07/07/2017
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0610-001-1-CRS_0 | 11/09/17 | CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR SP MATERIAL SHELL AND TUBE HEAT EXCHANGER (UNIT 17) | REF:T-2654/MIDOR-TPIT-T-00394 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0710-001-0-CRS_0 | 06/09/16 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-02197/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0710-001-0-CRS-REPLY_0 | 27/01/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:T-02197/MIDOR-TPIT-T-00020/MOM-00097
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-0710-001-1-CRS_0 | 12/09/17 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS (UNIT 17, 19) | REF:T-2654/MIDOR-TPIT-T-00394 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 0A | MACHINERY | 2544-0A-TBT-0920-001-0-CRS_0 | 15/09/16 | CLIENT COMMENTS TO TBT FOR RECIPROCATING PUMPS | REF:T-01945/MIDOR-TPIT-T-00040
CRS | MIDOR | 0A | PVHE | 2544-0A-TBT-2520-001-0-CRS-REPLY_1 | 02/02/17 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION FOR ENPPI STORAGE TANKS ASSEMBLED ON SITE | REF: TPIT-MIDOR MOM-00136 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 0B | PVHE | 2544-0B-TBT-0710-001-0-CRS_0 | 06/09/16 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-02459/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 0B | PVHE | 2544-0B-TBT-0710-001-0-CRS-REPLY_0 | 27/01/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:T-02459/MIDOR-TPIT-T-00020/MOM-00097 |  |  | TPIT-MIDOR-MOM -00097 - CLOSED/ APPROVED | 21/01/17
CRS | MIDOR | 0B | PVHE | 2544-0B-TBT-0710-001-1-CRS_0 | 12/09/17 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS (ITEM 21-E-06) | REF:MIDOR-TPIT-T-00394 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 0B | PVHE | 2544-0B-TBT-0710-001-1-CRS_1 | 28/11/17 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS (ITEM 21-E-06) | REF:MIDOR-TPIT-T-00415 | CLOSED
CRS | MIDOR | 0C | CIVIL | 2544-0C-NM-1410-01-A-CRS_0 | 19/10/17 | CLIENT COMMENTS TO TECHNICAL SPECIFICATION FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:T-2769/MIDOR-TPIT-T-00410 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 0C | CIVIL | 2544-0C-NM-1410-01-A-CRS_1 | 14/11/17 | CLIENT COMMENTS TO TECHNICAL SPECIFICATION FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:T-2769/MIDOR-TPIT-T-00412 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 0C |  | 2544-0C-NM-1410-01-A-CRS_2 | 2018-01-16 | CLIENT COMMENTS TO TECHNICAL SPECIFICATION FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS | REF:T-2769/MIDOR-TPIT-T-00432 | CLOSED
CRS | MIDOR | 0C | CONSTRUCTION | 2544-0C-PP-800-A-CRS_0 | 04/10/17 | CLIENT COMMENTS TO SITE ORGANIZATION CHART FOR KT | REF:T-2725/MIDOR-TPIT-T-00404 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 0C | PVHE | 2544-0C-TBT-0710-001-0-CRS_0 | 06/09/16 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:ED-0032/T-02413/MIDOR-TPIT-T-00020 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 0C | PVHE | 2544-0C-TBT-0710-001-0-CRS-REPLY_0 | 21/01/17 | TPIT REPLY TO CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:T-02413/MIDOR-TPIT-T-00020/MOM-00097
CRS | MIDOR | 0C | PVHE | 2544-0C-TBT-0710-001-1-CRS_0 | 17/10/17 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS | REF:T-2712/MIDOR-TPIT-T-00407 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 0C | PVHE | 2544-0C-TBT-0710-001-1-CRS_1 | 15/11/17 | CLIENT COMMENTS TO TBT FOR AIR COOLED HEAT EXCHANGERS (UNIT 22 & 23) | REF:T-2712/MIDOR-TPIT-T-00413 | CLOSED
CRS | MIDOR | 11 | PROCESS | 2544-11-CN-0009-02-A-CRS_0 | 14/06/16 | CLIENT COMMENTS TO UNIT 11 - INTERLOCK DESCRIPTION | REF:T-2020/MIDOR-TPIT-E-2016-06-15_02-33 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01879/2544-11-CN-0009-02-A-CRS-REPLY_0 | 30/06/16
CRS | MIDOR | 11 | PROCESS | 2544-11-CN-0009-02-A-CRS_1 | 15/06/16 | CLIENT COMMENTS TO UNIT 11 - INTERLOCK DESCRIPTION | REF:T-2020/MIDOR-TPIT-E-2016-06-20_12-36 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01880/2544-11-CN-0009-02-A-CRS-REPLY_1 | 30/06/16
CRS | MIDOR | 11 | PROCESS | 2544-11-CN-0009-02-A-CRS-REPLY_0 | 30/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - INTERLOCK DESCRIPTION | REF:E-1879/2544-11-CN-0009-02-A-CRS_0
CRS | MIDOR | 11 | PROCESS | 2544-11-CN-0009-02-A-CRS-REPLY_1 | 30/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - INTERLOCK DESCRIPTION | REF:E-1880/2544-11-CN-0009-02-A-CRS_1
CRS | MIDOR | 11 | ELECTRICAL | 2544-11-DW-1622-01-01-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 11 - ELECTRICAL CABLE ROUTING | REF:T-0807/MIDOR-TPIT-E-2016-03-05_08-20 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01213 2544-11-DW-1622-01-01-A-CRS-REPLY_0 | 23/03/16
CRS | MIDOR | 11 | ELECTRICAL | 2544-11-DW-1622-01-01-A-CRS-REPLY_0 | 23/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - ELECTRICAL CABLE ROUTING | REF:E-1213/2544-11-DW-1622-01-01-A-CRS
CRS | MIDOR | 11 | ELECTRICAL | 2544-11-DW-1622-01-01-B-CRS_0 | 19/05/16 | CLIENT COMMENTS TO UNIT 11 - ELECTRICAL CABLE ROUTING | REF:T-1730/MIDOR-TPIT-E-2016-22-05_19-15 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01995/2544-11-DW-1622-01-01-B-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 11 | ELECTRICAL | 2544-11-DW-1622-01-01-B-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - ELECTRICAL CABLE ROUTING | REF:E-1995/2544-11-DW-1622-01-01-B-CRS
CRS | MIDOR | 11 | ELECTRICAL | 2544-11-DW-1622-01-01-C-CRS_0 | 07/06/16 | CLIENT COMMENTS TO UNIT 11 - ELECTRICAL CABLE ROUTING | REF:TPIT-MIDOR-T-01983 | TPIT RESPONSE REQUIRED |  | 544-11-DW-1622-01-01-C-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 11 | ELECTRICAL | 2544-11-DW-1622-01-01-C-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - ELECTRICAL CABLE ROUTING | REF: 2544-11-DW-1622-01-01-B-CRS
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-01-A-CRS_0 | 01/05/16 | CLIENT COMMENTS TO UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE A | REF.: TPIT-MIDOR-T-01544 | TPIT RESPONSE REQUIRED |  | 2544-11-NM-0003-01-A-CRS-REPLY_0 MAC TPIT-MIDOR-E-01710 | 23/05/16
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-01-A-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE A | REF.: T-01544\TPIT-E-2016-05-11_08-33 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01708/2544-11-NM-0003-01-A-CRS-REPLY_1 | 23/05/16
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-01-A-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE A | REF: E-01544/2544-11-NM-0003-01-A-CRS_0
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-01-A-CRS-REPLY_1 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE A | REF: E-01708/2544-11-NM-0003-01-A-CRS_1
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-02-A-CRS_0 | 01/05/16 | CLIENT COMMENTS TO UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE B | REF.: TPIT-MIDOR-T-01544 | TPIT RESPONSE REQUIRED |  | 2544-11-NM-0003-02-A-CRS-REPLY_0 MAC TPIT-MIDOR-E-01710 | 23/05/16
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-02-A-CRS_1 | 09/05/16 | CLIENT COMMENTS TO UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE B | REF.: T-01544\TPIT-E-2016-05-11_08-33 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01708/2544-11-NM-0003-02-A-CRS-REPLY_1 | 23/05/16
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-02-A-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE B | REF: E-01544/2544-11-NM-0003-02-A-CRS_0
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0003-02-A-CRS-REPLY_1 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 UTILITIES CONSUMPTION SUMMARY DELAYED COKER UNIT - UNIT 11 CASE B | REF: E-01708/2544-11-NM-0003-02-A-CRS_1
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0005-01-A-CRS_0 | 09/05/16 | CLIENT COMMENTS TO EFFLUENT SUMMARY DELYED COKER UNIT - UNIT 11 | REF:T-1543/MIDOR-TPIT-E-2016-05-09_18-27 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01709 /2544-11-NM-0005-01-A-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0005-01-A-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO EFFLUENT SUMMARY DELYED COKER UNIT - UNIT 11 | REF: E-1709/2544-11-NM-0005-01-A-CRS_0
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0013-01-A-CRS_0 | 14/06/16 | CLIENT COMMENTS TO UNIT 11 - CAUSE AND EFFECT DIAGRAM | REF:T-2011/MIDOR-TPIT-E-2016-06-15_02-36 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01879/2544-11-NM-0013-01-A-CRS-REPLY_0 | 30/06/16
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0013-01-A-CRS_1 | 13/07/16 | CLIENT COMMENTS TO UNIT 11 - CAUSE AND EFFECT DIAGRAM | REF:2544-11-NM-0013-01-A-CRS-REPLY_0 |  |  | 2544-11-NM-0013-01-A-CRS-REPLY_0 - MIDOR-TPIT-E-02710 | 28/02/17
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0013-01-A-CRS-REPLY_0 | 30/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - CAUSE AND EFFECT DIAGRAM | REF:E-1879/2544-11-NM-0013-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-11-NM-0013-01-A-CRS_1 MIDOR-TPIT-E-2016-07-14_09-11 | 13/07/16
CRS | MIDOR | 11 | PROCESS | 2544-11-NM-0013-01-A-CRS-REPLY_1 | 28/02/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - CAUSE AND EFFECT DIAGRAM | REF:TPIT-MIDOR-E-02710 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 11 | PIPING | 2544-11-NM-1350-01-A-CRS_0 | 23/03/16 | CLIENT COMMENTS TO MECHANICAL TIE-IN LIST | REF:T-1130/MIDOR-TPIT-E-2016-03-23_20-40
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-01-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-08AR/BN) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-01-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-01-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-08AR/BN) | REF:E-1704/2544-11-SP-0610-01-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-02-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-09AN/BN) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-02-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-02-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-09AN/BN) | REF:E-1704/2544-11-SP-0610-02-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-03-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-10N) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-03-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-03-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-10N) | REF:E-1704/2544-11-SP-0610-03-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-04-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-11N) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-04-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-04-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-11N) | REF:E-1704/2544-11-SP-0610-04-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-05-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-12N) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-05-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-05-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-12N) | REF:E-1704/2544-11-SP-0610-05-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-06-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-14AN/BN) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-06-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-06-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-14AN/BN) | REF:E-1704/2544-11-SP-0610-06-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-07-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-15N) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-07-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-07-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-15N) | REF:E-1704/2544-11-SP-0610-07-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-08-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-17N) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-08-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-08-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-17N) | REF:E-1704/2544-11-SP-0610-08-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-09-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-18AN/BN) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-09-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-09-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-18AN/BN) | REF:E-1704/2544-11-SP-0610-09-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-10-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-24N) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-10-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-10-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-24N) | REF:E-1704/2544-11-SP-0610-10-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-11-PA-CRS_0 | 25/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-30) | REF:T-0840/MIDOR-TPIT-E-2016-03-25_08-22 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01704/2544-11-SP-0610-11-PA-CRS-REPLY_0 | 23/05/16
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-11-PA-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11-E-30) | REF:E-1704/2544-11-SP-0610-11-PA-CRS_0
CRS | MIDOR | 11 | PVHE | 2544-11-SP-0610-12-PA-CRS_0 | 23/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (19-E-26) | REF:T-0887/MIDOR-TPIT-E-2016-03-25_08-18
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-01-PA-CRS_0 | 27/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-03-27_21-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01705/2544-11-SP-0910-01-PA-CRS-REPLY_0 | 10/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-01-PA-CRS_1 | 29/04/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06A/B) | REF:T-00917/MIDOR-TPIT-E-2016-05-1_20-53 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01707/2544-11-SP-0910-01-PA-CRS-REPLY_1 | 23/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-01-PA-CRS_2 | 12/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-06-12_13-32 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01874/2544-11-SP-0910-01-PA-CRS-REPLY_2 | 27/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-01-PA-CRS_3 | 09/07/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-07-10_11-54 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-01-PA-CRS-REPLY_0 | 10/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-1705/2544-11-SP-0910-01-PA-CRS_0
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-01-PA-CRS-REPLY_1 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06A/B) | REF: E-01707/2544-11-SP-0910-01-PA-CRS_1 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-01-PA-CRS_2 / MIDOR-TPIT-E-2016-06-12_13-32 | 12/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-01-PA-CRS-REPLY_2 | 27/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-01874/2544-11-SP-0910-01-PA-CRS_2 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-01-PA-CRS_3 / MIDOR-TPIT-E-2016-07-10_11-54 | 09/07/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PA-CRS_0 | 27/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-03-27_21-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01705/2544-11-SP-0910-02-PA-CRS-REPLY_0 | 10/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PA-CRS_1 | 29/04/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-10A/B) | REF:T-00917/MIDOR-TPIT-E-2016-05-1_20-53 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01707/2544-11-SP-0910-02-PA-CRS-REPLY_1 | 23/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PA-CRS_2 | 12/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-06-12_13-32 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01874/2544-11-SP-0910-02-PA-CRS-REPLY_2 | 27/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PA-CRS_3 | 09/07/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-07-10_11-54 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PA-CRS-REPLY_0 | 10/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-1705/2544-11-SP-0910-02-PA-CRS_0
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PA-CRS-REPLY_1 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-10A/B) | REF: E-01707/2544-11-SP-0910-02-PA-CRS_1 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-02-PA-CRS_2 / MIDOR-TPIT-E-2016-06-12_13-32 | 12/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PA-CRS-REPLY_2 | 27/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-01874/2544-11-SP-0910-02-PA-CRS_2 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-02-PA-CRS_3 / MIDOR-TPIT-E-2016-07-10_11-54 | 09/07/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-02-PB-CRS_0 | 08/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-1896/MIDOR-TPIT-E-2016-06-08_12-46
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-03-PA-CRS_0 | 27/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-03-27_21-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01705/2544-11-SP-0910-03-PA-CRS-REPLY_0 | 10/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-03-PA-CRS_1 | 29/04/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-15A/B) | REF:T-00917/MIDOR-TPIT-E-2016-05-1_20-53 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01707/2544-11-SP-0910-03-PA-CRS-REPLY_1 | 23/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-03-PA-CRS_2 | 12/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-15A/B) | REF:T-0917/MIDOR-TPIT-E-2016-06-12_13-32 | OWNER RESPONSE REQUIRED |  | TPIT-MIDOR-E-01874/2544-11-SP-0910-03-PA-CRS-REPLY_2 | 27/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-03-PA-CRS_3 | 09/07/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-07-10_11-54 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-03-PA-CRS-REPLY_0 | 10/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-1705/2544-11-SP-0910-03-PA-CRS_0
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-03-PA-CRS-REPLY_1 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-15A/B) | REF: E-01707/2544-11-SP-0910-03-PA-CRS_1 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-03-PA-CRS_2 / MIDOR-TPIT-E-2016-06-12_13-32 | 12/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-03-PA-CRS-REPLY_2 | 27/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-01874/2544-11-SP-0910-03-PA-CRS_2 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-03-PA-CRS_3 / MIDOR-TPIT-E-2016-07-10_11-54 | 09/07/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-04-PA-CRS_0 | 27/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-03-27_21-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01705/2544-11-SP-0910-04-PA-CRS-REPLY_0 | 10/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-04-PA-CRS_1 | 29/04/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-16A/B) | REF:T-00917/MIDOR-TPIT-E-2016-05-1_20-53 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01707/2544-11-SP-0910-04-PA-CRS-REPLY_1 | 23/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-04-PA-CRS_2 | 12/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-16A/B) | REF:T-0917/MIDOR-TPIT-E-2016-06-12_13-32 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01874/2544-11-SP-0910-04-PA-CRS-REPLY_2 | 27/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-04-PA-CRS_3 | 09/07/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-07-10_11-54 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-04-PA-CRS-REPLY_0 | 10/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-1705/2544-11-SP-0910-04-PA-CRS_0
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-04-PA-CRS-REPLY_1 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-16A/B) | REF: E-01707/2544-11-SP-0910-04-PA-CRS_1 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-04-PA-CRS_2 / MIDOR-TPIT-E-2016-06-12_13-32 | 12/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-04-PA-CRS-REPLY_2 | 27/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-01874/2544-11-SP-0910-04-PA-CRS_2 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-04-PA-CRS_3 / MIDOR-TPIT-E-2016-07-10_11-54 | 09/07/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PA-CRS_0 | 27/03/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-03-27_21-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01705/2544-11-SP-0910-05-PA-CRS-REPLY_0 | 10/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PA-CRS_1 | 29/04/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-18A/B) | REF:T-00917/MIDOR-TPIT-E-2016-05-1_20-53 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01707/2544-11-SP-0910-05-PA-CRS-REPLY_1 | 23/05/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PA-CRS_2 | 12/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-18A/B) | REF:T-0917/MIDOR-TPIT-E-2016-06-12_13-32 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01874/2544-11-SP-0910-05-PA-CRS-REPLY_2 | 27/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PA-CRS_3 | 09/07/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-0917/MIDOR-TPIT-E-2016-07-10_11-54 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PA-CRS-REPLY_0 | 10/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-1705/2544-11-SP-0910-05-PA-CRS_0
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PA-CRS-REPLY_1 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-18A/B) | REF: E-01707/2544-11-SP-0910-05-PA-CRS_1 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-05-PA-CRS_2 / MIDOR-TPIT-E-2016-06-12_13-32 | 12/06/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PA-CRS-REPLY_2 | 27/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF: E-01874/2544-11-SP-0910-05-PA-CRS_2 | OWNER RESPONSE REQUIRED |  | 2544-11-SP-0910-05-PA-CRS_3 / MIDOR-TPIT-E-2016-07-10_11-54 | 09/07/16
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-05-PB-CRS_0 | 08/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEETS (11P-06/10/15/16/18) | REF:T-1896/MIDOR-TPIT-E-2016-06-08_12-46
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-06-PA-CRS_0 | 17/04/16 | CLIENT COMMENTS TO UNIT 11 - CENTRIFUGAL PUMP DATA SHEET (11-P-04 A/B) | REF:TPIT-MIDOR-T-01444
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-06-PA-CRS_1 | 29/04/16 | CLIENT COMMENTS TO UNIT 11 - CENTRIFUGAL PUMP DATA SHEET (11-P-04 A/B) | REF:TPIT-MIDOR-T-01444
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-07-PA-CRS_0 | 29/04/16 | CLIENT COMMENTS TO UNIT 11 - CENTRIFUGAL PUMP DATA SHEET (11-P-05 A/B) | REF:TPIT-MIDOR-T-01252
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-08-PA-CRS_0 | 17/04/16 | CLIENT COMMENTS TO UNIT 11 - CENTRIFUGAL PUMP DATA SHEET (11-P-07 AB) | REF:TPIT-MIDOR-T-01461
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-08-PA-CRS_1 | 30/04/16 | CLIENT COMMENTS TO UNIT 11 - CENTRIFUGAL PUMP DATA SHEET (11-P-07 AB) | REF:TPIT-MIDOR-T-01461
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-09-PA-CRS_0 | 30/04/16 | CLIENT COMMENTS TO DATA SHEET FOR CENTRIFUGAL PUMP DATA SHEET - SDA SOLVENT PUMPS 51-P-46 A/B | REF.: TPIT-MIDOR-T-01494
CRS | MIDOR | 11 | MACHINERY | 2544-11-SP-0910-09-PA-CRS_1 | 24/04/16 | CLIENT COMMENTS TO DATA SHEET FOR CENTRIFUGAL PUMP DATA SHEET - SDA SOLVENT PUMPS 51-P-46 A/B | REF.:01494\MIDOR-TPIT-E-2016-04-25_20-11
CRS | MIDOR | 11 | PROCESS | 2544-11-SP-1500-45-PA-CRS_0 | 23/06/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEET FOR PRESSURE SAFETY VALVES | REF:T-2012/MIDOR-TPIT-E-2016-06-27_08-31 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01891 / 2544-11-SP-1500-45-PA-CRS-REPLY_0 | 30/06/16
CRS | MIDOR | 11 | PROCESS | 2544-11-SP-1500-45-PA-CRS-REPLY_0 | 30/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEET FOR PRESSURE SAFETY VALVES | REF:E-1891/2544-11-SP-1500-45-PA-CRS_0
CRS | MIDOR | 12 | MACHINERY | 2544-12-0910-03-PA-CRS_0 | 08/09/16 | CLIENT COMMENTS TO CENTRIFUGAL PUMPS DATA SHEET (12-P-53) | REF.: MIDOR-TPIT-T-00022 | CLOSED |  | TPIT-MIDOR-MOM-00129 - APPROVED/CLOSED | 27/02/17
CRS | MIDOR | 12 | MACHINERY | 2544-12-SP-0910-02 PB-CRS_0 | 16/05/16 | CLIENT COMMENTS TO UNIT 12 CENTRIFUGAL PUMP DATA SHEET LEAN AMINE PUMP 12-P-58 A/B | REF:T-1605/MIDOR-TPIT-E-2016-05-18_11-39 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02051/2544-12-SP-0910-02 PB-CRS-REPLY_0 | 08/08/16
CRS | MIDOR | 12 | MACHINERY | 2544-12-SP-0910-02 PB-CRS-REPLY_0 | 08/08/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 12 CENTRIFUGAL PUMP DATA SHEET LEAN AMINE PUMP 12-P-58 A/B | REF:E-2051/2544-12-SP-0910-02 PB-CRS_0
CRS | MIDOR | 13 | PROCESS | 2544-13-PID-0021-001-01-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 13 - PID | REF.: T-0729 - MIDOR-E-2016-03-03_13-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02083 | 30/08/16
CRS | MIDOR | 14 | PIPING | 2544-14-DW-0051-01-01-B-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 14 - AMINE REGENERATION PLOT PLAN | REF:T-1007/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 14 | PIPING | 2544-14-DW-0051-01-01-B-CRS_1 | 26/09/16 | CLIENT COMMENTS TO UNIT 14 - AMINE REGENERATION PLOT PLAN | REF:T-1007/MIDOR-TPIT-T-00051
CRS | MIDOR | 14 | PROCESS | 2544-14-NM-2100-01-A-CRS_0 | 04/04/16 | CLIENT COMMENTS TO UNIT 14 - LABORATORY TEST SCHEDULE | REF:T-1255/MIDOR-TPIT-E-2016-04-05_14-16 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01381/2544-14-NM-2100-01-A-CRS-REPLY_0 | 14/04/16
CRS | MIDOR | 14 | PROCESS | 2544-14-NM-2100-01-A-CRS-REPLY_0 | 14/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 14 - LABORATORY TEST SCHEDULE | REF: E-01381/2544-14-NM-2100-01-A-CRS_0
CRS | MIDOR | 14 | PROCESS | 2544-14-PID-0021-B-CRS_0 | 24/06/16 | CLIENT COMMENTS TO UNIT 14 PIPING AND INSTRUMENT DIAGRAM - UNIT 14 - AMINE REGENERATION UNIT | REF:TPIT-MIDOR-T-01341/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01941/2544-14-PID-0021-B-CRS-REPLY_0 | 13/07/16
CRS | MIDOR | 14 | PROCESS | 2544-14-PID-0021-B-CRS-REPLY_0 | 13/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 14 PIPING AND INSTRUMENT DIAGRAM - UNIT 14 - AMINE REGENERATION UNIT | REF:E-1941/2544-14-PID-0021-B-CRS_0
CRS | MIDOR | 14 | PROCESS | 2544-14-PID-0031-003-A-CRS_0 | 24/06/16 | CLIENT COMMENTS TO UNIT 14 PIPING AND INSTRUMENT DIAGRAM - UNIT 14 - AMINE REGENERATION UNIT | REF:TPIT-MIDOR-T-01341
CRS | MIDOR | 14 | PROCESS | 2544-14-PID-0031-B-CRS_0 | 24/06/16 | CLIENT COMMENTS TO UNIT 14 PIPING AND INSTRUMENT DIAGRAM - UNIT 14 - AMINE REGENERATION UNIT | REF:TPIT-MIDOR-T-01341/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01941/2544-14-PID-0031-B-CRS-REPLY_0 | 13/07/16
CRS | MIDOR | 14 | PROCESS | 2544-14-PID-0031-B-CRS-REPLY_0 | 13/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 14 PIPING AND INSTRUMENT DIAGRAM - UNIT 14 - AMINE REGENERATION UNIT | REF:E-1941/2544-14-PID-0031-B-CRS_0
CRS | MIDOR | 15 | PIPING | 2544-15-DW-0051-01-01-B-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 15 - SOUR WATER STRIPPER PLOT PLAN | REF:T-1002/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 15 | PIPING | 2544-15-DW-0051-01-01-B-CRS_1 | 26/09/16 | CLIENT COMMENTS TO UNIT 15 - SOUR WATER STRIPPER PLOT PLAN | REF:T-1002/MIDOR-TPIT-T-00051
CRS | MIDOR | 15 | ELECTRICAL | 2544-15-DW-1622-01-01-A-CRS-0 | 19/03/16 | CLIENT COMMENT TO SOUR WATR STRIPPER MAIN CABLE ROUTING UNIT 15 | REF.T-01011/MIDOR-TPIT-E- 19/03/16 14:36
CRS | MIDOR | 15 | ELECTRICAL | 2544-15-DW-1622-01-01-A-CRS-REPLY-0 | 19/01/17 | TPIT REPLY TO CLIENT COMMENT TO SOUR WATR STRIPPER MAIN CABLE ROUTING UNIT 15 | REF.T-01011/TPIT-E-2594
CRS | MIDOR | 15 | PROCESS | 2544-15-MSD-0011-01-01-A-CRS_0 | 04/08/16 | CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM UNIT 15 - SOUR WATER STRIPPER UNIT | REF.T-2313\MIDOR-TPIT-E-2016-08-04_08-36
CRS | MIDOR | 15 | PROCESS | 2544-15-MSD-0011-01-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM UNIT 15 - SOUR WATER STRIPPER UNIT | REF.T-2313\MIDOR-TPIT-T-00016 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02110 / 2544-15-MSD-0011-01-01-B-CRS-REPLY_0 | 12/09/16
CRS | MIDOR | 15 | PROCESS | 2544-15-MSD-0011-01-01-B-CRS-REPLY_0 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM UNIT 15 - SOUR WATER STRIPPER UNIT | REF:E2110\2544-15-MSD-0011-01-01-B-CRS_0
CRS | MIDOR | 15 | PROCESS | 2544-15-NM-2100-01-A-CRS_0 | 04/04/16 | CLIENT COMMENTS TO UNIT 15 - LABORATORY TEST SCHEDULE | REF:T-1256/MIDOR-TPIT-E-2016-04-05_14-16 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01381/2544-15-NM-2100-01-A-CRS-REPLY_0 | 14/04/16
CRS | MIDOR | 15 | PROCESS | 2544-15-NM-2100-01-A-CRS-REPLY_0 | 14/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 15 - LABORATORY TEST SCHEDULE | REF: E-01381/2544-15-NM-2100-01-A-CRS_0
CRS | MIDOR | 15 | PROCESS | 2544-15-PFD-0010-01-01-C-CRS_0 | 29/09/16 | CLIENT COMMENTS TO PROCESS FLOW DIAGRAM UNIT 15 | REF.T-2145\MIDOR-TPIT-T-00070
CRS | MIDOR | 15 | PROCESS | 2544-15-PFD-0010-01-01-C-CRS_1 | 20/10/16 | CLIENT COMMENTS FOR PROCESS FLOW DIAGRAM UNIT 15 | REF.MIDOR-TPIT-T-00110
CRS | MIDOR | 15 |  | 2544-15-PFD-0010-01-01-D-CRS_0 | 2018-01-31 | CLIENT COMMENTS FOR PFD UNIT 15 | REF.T-02849/MIDOR-TPIT-T-00434 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 15 |  | 2544-15-PFD-0010-01-01-D-CRS_1 | 2018-02-26 | CLIENT COMMENTS FOR PFD UNIT 15 | REF.T-02849/MIDOR-TPIT-T-00448 | CLOSED
CRS | MIDOR | 15 | PROCESS | 2544-15-PID-0021-A-CRS_0 | 20/06/16 | CLIENT COMMENTS TO UNIT 15 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-00609/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01942/2544-15-PID-0021-A-CRS-REPLY_0 | 13/07/16
CRS | MIDOR | 15 | PROCESS | 2544-15-PID-0021-A-CRS-REPLY_0 | 13/07/16 | TPIT-REPLY TO CLIENT COMMENTS TO UNIT 15 PIPING AND INSTRUMENT DIAGRAMS | REF:E-1942/2544-15-PID-0021-A-CRS_0
CRS | MIDOR | 15 | PROCESS | 2544-15-PID-0021-B-CRS_0 | 08/07/16 | CLIENT COMMENTS TO UNIT 15 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-02208/PMC-MIDOR-E-0065 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01963 / 2544-15-PID-0021-B-CRS-REPLY_0 | 14/07/16
CRS | MIDOR | 15 | PROCESS | 2544-15-PID-0021-B-CRS-REPLY_0 | 14/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 15 PIPING AND INSTRUMENT DIAGRAMS | REF:E-1963/2544-15-PID-0021-B-CRS_0
CRS | MIDOR | 15 | PROCESS | 2544-15-PID-0031-A-CRS_0 | 20/06/16 | CLIENT COMMENTS TO UNIT 15 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-00854/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01942/2544-15-PID-0031-A-CRS-REPLY_0 | 13/07/16
CRS | MIDOR | 15 | PROCESS | 2544-15-PID-0031-A-CRS-REPLY_0 | 13/07/16 | TPIT-REPLY TO CLIENT COMMENTS TO UNIT 15 PIPING AND INSTRUMENT DIAGRAMS | REF:E-1942/2544-15-PID-0021-A-CRS_0
CRS | MIDOR | 16 | PROCESS | 2544-16-NM-0020-01-B-CRS_0 | 23/06/16 | CLIENT COMMENTS TO UNIT 16 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF:TPIT-MIDOR-T-01515/PMC-MIDOR-E-0063
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0510-01-PA-CRS_0 | 04/05/16 | CLIENT COMMENTS TO UNIT 16 - PROCESS DATA SHEET FOR EXTRACTOR 16-T-01 | REF:T-1448/MIDOR-TPIT-E-2016-05-04_15-12
CRS | MIDOR | 16 | PVHE | 2544-16-SP-0570-01-PA-CRS_0 | 04/05/16 | CLIENT COMMENTS TO UNIT 16 - PROCESS DATA SHEET FOR EXTRACTOR - TRAYS AND INTERNALS MODIFICATIONS 16-IT-01 | REF:T-1448/MIDOR-TPIT-E-2016-05-04_15-12
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-02-PA-CRS_0 | 04/05/16 | CLIENT COMMENTS TO UNIT 16 - PROCESS DATA SHEET FOR CAUSTIC COALESCER 16-V-03 | REF:T-1448/MIDOR-TPIT-E-2016-05-04_15-12
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-03-PA-CRS_0 | 16/05/16 | CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR OXIDIZER - 16-V-04 | REF:T-1660/MIDOR-TPIT-E-2016-05-16_09-13
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-04-PA-CRS_0 | 16/05/16 | CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR DISULFIDE SEPARATOR - 16-V-05 | REF:T-1660/MIDOR-TPIT-E-2016-05-16_09-13 |  |  | 2544-16-SP-0810-04-PA-CRS-REPLY_0 - PIT-MIDOR-E-02555 | 04/01/17
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-04-PA-CRS_1 | 01/03/17 | CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR DISULFIDE SEPARATOR - 16-V-05 | REF:T-1660/TPIT-E-2555/MIDOR-TPIT-T-0197 | CLOSED |  | APPROVED
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-04-PA-CRS-REPLY_0 | 04/01/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR DISULFIDE SEPARATOR - 16-V-05 | REF:T-1660/TPIT-MIDOR-E-02555 |  |  | 2544-16-SP-0810-04-PA-CRS_1 - MIDOR-TPIT-T-00197 APPROVED/CLOSED | 01/03/17
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-06-PA-CRS_0 | 16/05/16 | CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR VENT TANK - 16-V-09 | REF:T-1660/MIDOR-TPIT-E-2016-05-16_09-13
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-07-PA-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FORWATER BREAK TANK 16-TK-01 | REF:T-1735/MIDOR-TPIT-E-2016-05-22_08-31 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01724/2544-16-SP-0810-07-PA-CRS-REPLY_0 | 01/06/16
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0810-07-PA-CRS-REPLY_0 | 01/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FORWATER BREAK TANK 16-TK-01 | REF:E-1724/2544-16-SP-0810-07-PA-CRS_0
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0940-01-PA-CRS_0 | 25/05/16 | CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR 16-P-04 A/B DISULFIDE OIL PUMPS | REF:T-1758/MIDOR-TPIT-E-2016-05-26_23-36 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0940-01-PA-CRS_1 | 30/05/16 | CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR 16-P-04 A/B DISULFIDE OIL PUMPS | REF:T-1758/MIDOR-TPIT-E-2016-05-30_21-20 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 16 | PROCESS | 2544-16-SP-0940-01-PA-CRS-REPLY_1 | 01/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 16 PROCESS DATA SHEET FOR 16-P-04 A/B DISULFIDE OIL PUMPS | REF:E-1726/2544-16-SP-0940-01-PA-CRS_1
CRS | MIDOR | 17 | HSE DESIGN | 2544-17-CN-1901-01-0-CRS_0 | 29/08/16 | CLIENT COMMENTS TO PRELIMINARY FIRE WATER DEMAND FOR UNIT-17, NEW CDU & VDU | REF: TPIT-MIDOR-T-2272/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 17 | PIPING | 2544-17-DW-0051-01-01-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO UNIT 17 NEW CDU & VDU UNIT PLOT PLAN | REF:T-1209/MIDOR-TPIT-E-2016-03-30_05-55 | TPIT RESPONSE REQUIRED |  | 2544-17-DW-0051-01-01-A-CRS-REPLY_0 | 04/04/16
CRS | MIDOR | 17 | PIPING | 2544-17-DW-0051-01-01-A-CRS_1 | 05/05/16 | CLIENT COMMENTS TO UNIT 17 NEW CDU & VDU UNIT PLOT PLAN | REF:T-1209/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-17-DW-0051-01-01-A-CRS-REPLY_1 TPIT-MIDOR-E-02088/MOM-0065 | 13/06/16
CRS | MIDOR | 17 | PIPING | 2544-17-DW-0051-01-01-A-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 PLOT PLAN | REF:2544-17-DW-0051-01-01-A-CRS_0/E-1292
CRS | MIDOR | 17 | PIPING | 2544-17-DW-0051-01-01-A-CRS-REPLY_1 | 13/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 PLOT PLAN | REF: TPIT-MIDOR-E-02088/MOM-0065
CRS | MIDOR | 17 | PIPING | 2544-17-DW-0051-01-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 - NEW CDU & VDU BLOCK P - ZONE P301 - DETAILED PLOT PLAN | REF.:T-1209/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 17 | HSE DESIGN | 2544-17-DW-1933-01-01-A-CRS_0 | 21/03/16 | CLIENT COMMENTS TO UNIT 17 SOLVENT DEASPHALTING UNIT FIRE FIGHTING LAYOUT | REF:T-0928/MIDOR-TPIT-E-2016-03-21_13-14
CRS | MIDOR | 17 | HSE DESIGN | 2544-17-DW-1933-01-01-B-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 17 SOLVENT DEASPHALTING UNIT FIRE FIGHTING LAYOUT | REF: TPIT-MIDOR-T-2273/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 17 | HSE DESIGN | 2544-17-DW-1950-01-01-A-CRS_0 | 22/05/16 | CLIENT COMMENTS TO UNIT 17 - NEW CDU & VDU FIRE AND GAS DETECTION LAYOUT | REF:T-1041/MIDOR-TPIT-E-2016-05-26_11-17
CRS | MIDOR | 17 | HSE DESIGN | 2544-17-DW-1950-01-01-B-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 17 - NEW CDU & VDU FIRE AND GAS DETECTION LAYOUT | REF: TPIT-MIDOR-T-2273/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 17 | PROCESS | 2544-17-NM-0020-01-A-CRS_0 | 30/05/16 | CLIENT COMMENTS TO UNIT 17 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF: T-1623/PMC-MIDOR-E-0026 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02097 / 2544-17-NM-0020-01-A-CRS-REPLY_0 | 06/09/16
CRS | MIDOR | 17 | PROCESS | 2544-17-NM-0020-01-A-CRS_1 | 09/09/16 | CLIENT COMMENTS TO UNIT 17 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF: MIDOR-TPIT-E-0017/CRS-REPLY_0 | TPIT RESPONSE REQUIRED |  | 2544-17-NM-0020-01-A-CRS-REPLY_1 | 14/09/16
CRS | MIDOR | 17 | PROCESS | 2544-17-NM-0020-01-A-CRS-REPLY_0 | 06/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF: 2544-17-NM-0020-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-0017 / 2544-17-NM-0020-01-A-CRS_1 | 09/09/16
CRS | MIDOR | 17 | PROCESS | 2544-17-NM-0020-01-A-CRS-REPLY_1 | 14/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF: 2544-17-NM-0020-01-A-CRS_1
CRS | MIDOR | 17 | HSE DESIGN | 2544-17-NM-1901-01-A-CRS_0 | 22/05/16 | CLIENT COMMENTS TO FIRE AND GAS IN-OUT LIST UNIT 17 NEW CDU AND VDU UNIT | REF:T-1620/MIDOR-TPIT-E-2016-05-26_11-03
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0510-05-PA-CRS_0 | 11/09/17 | CLIENT COMMENTS TO COLUMN DATA SHEET FOR DEBUTANIZER COLUMN 17-T-05 | REF:T-2045/MIDOR-TPIT-T-00392 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0510-06-PA-CRS_0 | 11/09/17 | CLIENT COMMENTS TO COLUMN DATA SHEET FOR AMINE GAS SCRUBBER COLUMN 17-T-04 | REF:T-2045/MIDOR-TPIT-T-00392 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 17 | PVHE | 2544-17-SP-0610-21-PA-CRS_0 | 13/04/16 | CLIENT COMMENTS TO UNIT 17 DATA SHEET FOR 17-E-22 A/B | REF:T-1390/MIDOR-TPIT-E-2016-04-13_08-53
CRS | MIDOR | 17 | PVHE | 2544-17-SP-0610-27-PA-CRS_0 | 13/04/16 | CLIENT COMMENTS TO UNIT 17 DATA SHEET FOR 17-E-55 | REF:T-1390/MIDOR-TPIT-E-2016-04-13_08-53
CRS | MIDOR | 17 | PVHE | 2544-17-SP-0610-28-PA-CRS_0 | 13/04/16 | CLIENT COMMENTS TO UNIT 17 DATA SHEET FOR 17-E-56 A/B | REF:T-1390/MIDOR-TPIT-E-2016-04-13_08-53
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-02-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-03 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-03-PB-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-04 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-06-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-07 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-07-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-08 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-08-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-09 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-09-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET FOR 17-V-10 | REF: TPIT-MIDOR-T-01346
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-11-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-12 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-12-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-51 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-13-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-52 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-14-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET UNIT 17 - 17-V-53 | REF:T-1337/MIDOR-TPIT-E-2016-04-12_08-10
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-0810-15-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET FOR 17-V-54 | REF: TPIT-MIDOR-T-01346
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-01-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET FOR 17-FL-51 A/B | REF: TPIT-MIDOR-T-01343
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-01-PA-CRS_1 | 01/03/17 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET FOR 17-FL-51 A/B | REF: T-01343/MIDOR-TPIT-T-00197 | CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-01-PA-CRS-REPLY_0 | 08/02/17 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET FOR 17-FL-51 A/B | REF: T-01343/TPIT-MIDOR-E-02644 |  |  | 2544-17-SP-0841-01-PA-CRS_1 - MIDOR-TPIT-T-00197 | 01/03/17
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-02-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET FOR 17-FL-52 A/B | REF: TPIT-MIDOR-T-01343
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-02-PA-CRS_1 | 01/03/17 | CLIENT COMMENTS TO DATA SHEET FOR 17-FL-52 A/B | REF: T-01343/MIDOR-TPIT-T-00197 | CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-02-PA-CRS-REPLY_0 | 08/02/17 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET FOR 17-FL-52 A/B | REF: T-01343/MIDOR-TPIT-T-02644 |  |  | 2544-17-SP-0841-03-PA-CRS_1 - MIDOR-TPIT-T-00197 | 01/03/17
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-03-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO DATA SHEET FOR 17-FL-53 A/B | REF: TPIT-MIDOR-T-01343
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-03-PA-CRS_1 | 01/03/17 | CLIENT COMMENTS TO DATA SHEET FOR 17-FL-53 A/B | REF: T-01343/MIDOR-TPIT-T-00197 | CLOSED |  | APPROVED | 01/03/17
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-0841-03-PA-CRS-REPLY_0 | 08/02/17 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET FOR 17-FL-53 A/B | REF: T-01343/TPIT-MIDOR-E-02644 |  |  | 2544-17-SP-0841-03-PA-CRS_1 - MIDOR-TPIT-T-00197 | 01/03/17
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-04-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-04 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-04-A-CRS_1 | 27/07/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-04 A/B | REF: T-00553/MDR-TPIT-T-00373 | CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-04-A-CRS_2 | 18/08/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-04 A/B | REF: T-00553/MDR-TPIT-T-00378 | CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-04-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-04 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-10-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-10 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-10-A-CRS_1 | 27/07/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-10 A/B | REF: T-00553/MDR-TPIT-T-00373 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-10-A-CRS_2 | 18/08/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-10 A/B | REF: T-00553/MDR-TPIT-T-00378 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-10-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-10 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-14-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-14 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-14-A-CRS_1 | 27/07/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-14 A/B | REF: T-00553/MDR-TPIT-T-00373 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-14-A-CRS_2 | 18/08/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-14 A/B | REF: T-00553/MDR-TPIT-T-00378 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-14-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-14 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-15-A-CRS_0 | 20/03/16 | CLIENT COMMENTS TO DATA SHEET FOR BFW PUMP 17-P-15 A/B | REF:T-1116/MIDOR-TPIT-E-2016-03-21_21-52
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-15-A-CRS_1 | 27/07/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-15 A/B&17-P-56 A/B&17-P-58 | REF:T1116/MDR-T-E-2016-03-21_21-52/T-373 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-15-A-CRS_2 | 18/08/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-15 A/B&17-P-56 A/B&17-P-58 | REF:T1116/MDR-TPIT-T-00378 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-16-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-16 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553 |  |  | 2544-17-SP-0910-16-A-CRS-REPLY_0 TPIT-MIDOR-E-02547 | 23/12/16
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-16-A-CRS_1 | 20/04/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-16 A/B WITH MACHINERY COMMENTS | REF: T-00553/TPIT-E-02547/MIDOR-T-00281 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-16-A-CRS_2 | 27/07/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-17 A/B | REF:T-553/TPIT-E-02547/MDR-T-00281/T-373 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-16-A-CRS_3 | 18/08/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-17 A/B | REF:T-553/MDR-TPIT-T-00378 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-16-A-CRS-REPLY_0 | 23/12/16 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-16 A/B WITH MACHINERY COMMENTS | REF: T-00553/TPIT-E-02547 |  |  | 2544-17-SP-0910-16-A-CRS_1 MIDOR-TPIT-T-00281 REVIEWED WITH COMMENTS | 20/04/17
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-16-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-16 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-17-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-17 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-17-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-17 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-18-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-52 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-18-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-52 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-19-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-53 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-19-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-53 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-21-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-55 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-21-A-CRS_1 | 27/07/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-55 A/B | REF: T-00553/MDR-TPIT-T-00373 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-21-A-CRS_2 | 18/08/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-55 A/B | REF: T-00553/MDR-TPIT-T-00378 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-21-PA-CRS_0 | 28/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17-P-55 A/B | REF: TPIT-MIDOR-T-00533
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-22-A-CRS_0 | 20/03/16 | CLIENT COMMENTS TO DATA SHEET FOR VACUUM RESIDUE PUMP 17-P-56 A/B | REF:T-1116/MIDOR-TPIT-E-2016-03-21_21-52
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-23-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 17 P 57 A/B WITH MACHINERY COMMENTS | REF: TPIT-MIDOR-T-00553
CRS | MIDOR | 17 | MACHINERY | 2544-17-SP-0910-24-A-CRS_0 | 20/03/16 | CLIENT COMMENTS TO DATA SHEET FOR CLOSED DRAIN PUMP 17-P-58 | REF:T-1116/MIDOR-TPIT-E-2016-03-21_21-52
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-03-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-10B | REF: TPIT-MIDOR-T-00553 | CLOSED |  | 2544-17-SP-1111-03-A-CRS-REPLY_0 TPIT-MIDOR-T-02556 | 05/01/17
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-03-A-CRS-1 | 20/04/17 | CLIENT APPROVED COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-10B | REF: T-553/TPIT-E-2556/MIDOR-T-00274 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-03-A-CRS-REPLY _0 | 05/01/17 | TPIT REPLY CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-10B | REF: T-553/TPIT-E-2556 | CLOSED |  | 2544-17-SP-1111-04-A-CRS_1 MIDOR-TPIT-T-00274 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-04-A-CRS_0 | 22/03/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-15B | REF:T-1166/MIDOR-TPIT-E-2016-03-22_22-35 | CLOSED |  | 2544-17-SP-1111-03-A-CRS-REPLY_0 TPIT-MIDOR-T-02556 | 05/01/17
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-04-A-CRS_2 | 10/07/17 | CLIENT APPROVED COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-15B | REF: T-1166/TPIT-E-2556/MDR-T-274/359 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-04-A-CRS-1 | 20/04/17 | CLIENT APPROVED COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-15B | REF: T-553/TPIT-E-2556/MIDOR-T-00274 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-04-A-CRS-REPLY _0 | 05/01/17 | TPIT REPLY CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-15B | REF: T-553/TPIT-E-2556 | CLOSED |  | 2544-17-SP-1111-04-A-CRS_1 MIDOR-TPIT-T-00274 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-06-A-CRS_0 | 22/03/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-16B | REF:T-1166/MIDOR-TPIT-E-2016-03-22_22-35 | CLOSED |  | 2544-17-SP-1111-06-A-CRS_1 MIDOR-TPIT-T-00280 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-06-A-CRS_1 | 20/04/17 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-16B | REF:T-1166/MIDOR-TPIT-T00280 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 17 | PROCESS | 2544-17-SP-1111-06-A-CRS_2 | 10/07/17 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBIN 17-STP-16B | REF:T-1166/MDR-TPIT-00280/359 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-4046-01-PA-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR CORROSION INHIBITOR INJECTION SYSTEM - 17-PK-02 | REF:T-2023/MDR-TPIT-00386 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-4046-02-PA-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR NEUTRALIZING AMINE INJECTION SYSTEM - 17-PK-03 | REF:T-2023/MDR-TPIT-00386 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-4046-03-PA-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR FILMING AMINES INJECTION SYSTEM - 17-PK-04 | REF:T-2023/MDR-TPIT-00386 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-4046-04-PA-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR DEMULSIFIER INJECTION SYSTEM - 17-PK-05 | REF:T-2023/MDR-TPIT-00386 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-4046-05-PA-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR PHOSPHATE INJECTION SYSTEM - 17-PK-06 | REF:T-2023/MDR-TPIT-00386 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 17 | PACKAGES | 2544-17-SP-4046-06-PA-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR CAUSTIC INJECTION SYSTEM - 17-PK-07 | REF:T-2023/MDR-TPIT-00386 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 18 | PIPING | 2544-18-DW-0051-01-01-D-CRS_0 | 05/05/16 | CLIENT COMMENTS TO UNIT 18 BLOCK P - ZONE P-202 UNIT 18 - DIESEL DISTILLATE UNIONFINING UNIT DETAILED PLOT PLAN | REF:T-1583/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 18 | PIPING | 2544-18-DW-0051-01-01-D-CRS_1 | 17/05/16 | CLIENT COMMENTS TO UNIT 18 BLOCK P - ZONE P-202 UNIT 18 - DIESEL DISTILLATE UNIONFINING UNIT DETAILED PLOT PLAN | REF: TPIT-MIDOR-T-01583 | TPIT RESPONSE REQUIRED |  | 2544-18-DW-0051-01-01-D-CRS-REPLY_1 TPIT-MIDOR-E-02088/MOM-0065 | 08/07/16
CRS | MIDOR | 18 | PIPING | 2544-18-DW-0051-01-01-D-CRS_2 | 18/07/16 | CLIENT COMMENTS TO UNIT 18 BLOCK P - ZONE P-202 UNIT 18 - DIESEL DISTILLATE UNIONFINING UNIT DETAILED PLOT PLAN | REF: MIDOR-TPIT-T-00054
CRS | MIDOR | 18 | PIPING | 2544-18-DW-0051-01-01-D-CRS-REPLY_1 | 08/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - NEW FLARE BLOCK C - ZONE C301 DETAILED PLOT PLAN | REF.:TPIT-MIDOR-E-02088/MOM-0065
CRS | MIDOR | 18 | PIPING | 2544-18-DW-0051-01-D-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO BLOCK P - ZONE P-202 UNIT 18 - DIESEL DISTILLATE UNIONFINING UNIT DETAILED PLOT PLAN | REF.:T-1583/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 18 | CIVIL | 2544-18-DW-1442-01-01-C-CRS_0 | 22/05/16 | CLIENT COMMENTS TO MAJOR UNDERGROUND LAYOUT NEW PROCESS AREA UNIT 18 | REF:T-1680/MIDOR-TPIT-E-2016-05-22_12-35 | TPIT RESPONSE REQUIRED |  | 2544-18-DW-1442-01-01-C-CRS-REPLY_0/TPIT-MIDOR-E-02202 | 30/09/16
CRS | MIDOR | 18 | CIVIL | 2544-18-DW-1442-01-01-C-CRS_1 | 11/10/16 | CLIENT COMMENTS TO MAJOR UNDERGROUND LAYOUT NEW PROCESS AREA UNIT 18 | REF:T-1680/E-2016-05-22_12-35/T-00079 |  |  | CLOSED | 11/10/16
CRS | MIDOR | 18 | CIVIL | 2544-18-DW-1442-01-01-C-CRS-REPLY_0 | 30/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MAJOR UNDERGROUND LAYOUT NEW PROCESS AREA UNIT 18 | REF:T-1680/MIDOR-TPIT-E-2016-05-22_12-35
CRS | MIDOR | 18 | HSE DESIGN | 2544-18-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 18 - DHT FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-0164/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 18 | HSE DESIGN | 2544-18-DW-1950-01-01-A-CRS_0 | 09/03/16 | CLIENT COMMENTS TO UNIT 18 - FIRE AND GAS DETECTION LAYOUT | REF:T-0403/MIDOR-TPIT-E-2016-03-09_08-05 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01399/2544-18-DW-1950-01-01-A-CRS-REPLY_0 | 15/04/16
CRS | MIDOR | 18 | HSE DESIGN | 2544-18-DW-1950-01-01-A-CRS_1 | 18/04/16 | CLIENT COMMENTS TO UNIT 18 - FIRE AND GAS DETECTION LAYOUT | REF:T-0403/MIDOR-TPIT-E-2016-04-19_21-44
CRS | MIDOR | 18 | HSE DESIGN | 2544-18-DW-1950-01-01-A-CRS-REPLY_0 | 14/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 18 - FIRE AND GAS DETECTION LAYOUT | REF:E-1399/2544-18-DW-1950-01-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-19_21-44/2544-18-DW-1950-01-01-A-CRS_1 | 19/04/16
CRS | MIDOR | 18 | PROCESS | 2544-18-NM-0020-01-B-CRS_0 | 23/05/16 | CLIENT COMMENTS TO UNIT 18 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF:TPIT-MIDOR-T-01529/PMC-MIDOR-E-0024 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01974 / 2544-18-NM-0020-01-B-CRS-REPLY_0 | 19/07/16
CRS | MIDOR | 18 | PROCESS | 2544-18-NM-0020-01-B-CRS-REPLY_0 | 19/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 18 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF:E-1974/2544-18-NM-0020-01-B-CRS_0
CRS | MIDOR | 18 | PROCESS | 2544-18-NM-2100-01-A-CRS_0 | 03/06/16 | CLIENT COMMENTS TO DHT U-18 TEST METHODS AND SAMPLING SCHEDULE | REF:T-1749/MIDOR-TPIT-E-2016-06-03_13-33 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01818/2544-18-NM-2100-01-A-CRS-REPLY_0 | 15/06/16
CRS | MIDOR | 18 | PROCESS | 2544-18-NM-2100-01-A-CRS-REPLY_0 | 15/06/16 | TPIT REPLY TO CLIENT COMMENTS TO DHT U-18 TEST METHODS AND SAMPLING SCHEDULE | REF:E-1818/2544-18-NM-2100-01-A-CRS_0
CRS | MIDOR | 18 | HSE DESIGN | 2544-18-PID-1931-001-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - UNIT 18 - DIESEL DISTILLATE UNIONFINING UNIT FIREFIGHTING SYSTEM | REF: TPIT-MIDOR-T-0635/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 18 | PVHE | 2544-18-SP-0710-02-PB-CRS_0 | 21/05/16 | CLIENT COMMENTS TO UNIT 18 - PROCESS DATA SHEET | REF.:T-565-MIDOR-TPIT-E-2016-21-08_01-10 |  |  | 2544-18-SP-0710-02-PB-CRS-REPLY_0 -TPIT-MIDOR-E-02555 | 04/01/17
CRS | MIDOR | 18 | PVHE | 2544-18-SP-0710-02-PB-CRS_1 | 07/03/17 | CLIENT COMMENTS TO UNIT 18 - PROCESS DATA SHEET | REF.:T-565/MIDOR-TPIT-00206
CRS | MIDOR | 18 | PVHE | 2544-18-SP-0710-02-PB-CRS_2 | 30/05/17 | CLIENT COMMENTS TO DATA SHEET FOR 18-E-05 | REF.:T-1637/MIDOR-TPIT-00336 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 18 | PVHE | 2544-18-SP-0710-02-PB-CRS-REPLY_0 | 04/01/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 18 - PROCESS DATA SHEET | REF.:T-565/TPIT-MIDOR-E-02555 |  |  | 2544-18-SP-0710-02-PB-CRS_1 - MIDOR-TPIT-T-00206 | 07/03/17
CRS | MIDOR | 18 | PVHE | 2544-18-SP-0710-02-PB-CRS-REPLY_1 | 08/03/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 18 - PROCESS DATA SHEET | REF.:T-565/MIDOR-T-206/TPIT-MIDOR-E-2744
CRS | MIDOR | 18 | MACHINERY | 2544-18-SP-0910-01-PB-CRS_0 | 08/08/16 | CLIENT COMMENTS TO UNIT 18 - FOR CHARGE PUMPS 18-P-01 A/B | REF:T-2404/MIDOR-TPIT-E-2016-09-08_11-35
CRS | MIDOR | 18 | MACHINERY | 2544-18-SP-0910-07-A-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR 18-P- 08-A/B EJECTOR RECEIVER | REF:T-1176/MDR-TPIT-00386 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 19 | PIPING | 2544-19-DW-0051-01-01-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO UNIT 19 SDA PLOT PLAN | REF:T-1210/MIDOR-TPIT-E-2016-03-30_05-55 | TPIT RESPONSE REQUIRED |  | 2544-19-DW-0051-01-01-A-CRS-REPLY_0 | 04/04/16
CRS | MIDOR | 19 | PIPING | 2544-19-DW-0051-01-01-A-CRS_1 | 13/05/16 | CLIENT COMMENTS TO UNIT 19 - SDA BLOCK P - ZONE P302 DETAILED PLOT PLAN | REF:T-1210/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-19-DW-0051-01-01-A-CRS-REPLY_1 TPIT-MIDOR-E-02088/MOM-0065 | 13/06/16
CRS | MIDOR | 19 | PIPING | 2544-19-DW-0051-01-01-A-CRS_2 | 26/09/16 | CLIENT COMMENTS TO UNIT 19 - SDA BLOCK P - ZONE P302 DETAILED PLOT PLAN | REF:T-1210/MIDOR-TPIT-T-00051 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 19 | PIPING | 2544-19-DW-0051-01-01-A-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 PLOT PLAN | 19-DW-0051-01-01-A-CRS_0/E-1292/MOM-65
CRS | MIDOR | 19 | PIPING | 2544-19-DW-0051-01-01-A-CRS-REPLY_1 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 PLOT PLAN | REF.:TPIT-MIDOR-E-02088/MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-19-DW-0051-01-01-A-CRS_2 TPIT-MIDOR-T-00051 | 26/09/16
CRS | MIDOR | 19 | PIPING | 2544-19-DW-0051-01-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 - SDA BLOCK P - ZONE P302 DETAILED PLOT PLAN | REF.:T-1210/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 19 | HSE DESIGN | 2544-19-DW-1933-01-01-A-CRS_0 | 14/03/16 | CLIENT COMMENTS TO UNIT 19 SOLVENT DEASPHALTING UNIT FIRE FIGHTING LAYOUT | REF:T-0930/MIDOR-TPIT-E-2016-03-20_17-12
CRS | MIDOR | 19 | HSE DESIGN | 2544-19-DW-1933-01-01-A-CRS_1 | 29/08/16 | CLIENT COMMENTS TO UNIT 19 SOLVENT DEASPHALTING UNIT FIRE FIGHTING LAYOUT | REF: TPIT-MIDOR-T-2227/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 19 | PROCESS | 2544-19-NM-0003-01-A-CRS_0 | 27/06/16 | CLIENT COMMENTS TO UNIT 19 - UTILITY CONSUMPTION SUMMARY | REF:T-2060/MIDOR-TPIT-E-2016-06-28_09-06
CRS | MIDOR | 19 | PROCESS | 2544-19-NM-0003-02-A-CRS_0 | 27/06/16 | CLIENT COMMENTS TO UNIT 19 - UTILITY CONSUMPTION SUMMARY | REF:T-2060/MIDOR-TPIT-E-2016-06-28_09-06
CRS | MIDOR | 19 | PROCESS | 2544-19-NM-0020-01-B-CRS_0 | 31/05/16 | CLIENT COMMENTS TO UNIT 19 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REFT-01623/MIDOR-TPIT-E-2016-06-07-21-24 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02096 / 2544-19-NM-0020-01-B-CRS-REPLY_0 | 07/09/16
CRS | MIDOR | 19 | PROCESS | 2544-19-NM-0020-01-B-CRS_1 | 09/09/16 | CLIENT COMMENTS TO UNIT 19 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF: MIDOR-TPIT-E-0017
CRS | MIDOR | 19 | PROCESS | 2544-19-NM-0020-01-B-CRS-REPLY_0 | 07/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE | REF: 2544-19-NM-0020-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-0017 / 2544-19-NM-0020-01-B-CRS_1 | 09/09/16
CRS | MIDOR | 19 | HEATERS AND BOILERS | 2544-19-SP-0110-01-B-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 19 - MECHANICAL DATA SHEET | REF.: T-0919 - MIDOR-E-2016-03-05_08-18 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01238/2544-19-SP-0110-01-B-CRS-REPLY_0 | 29/03/16
CRS | MIDOR | 19 | HEATERS AND BOILERS | 2544-19-SP-0110-01-B-CRS-REPLY_0 | 29/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 - MECHANICAL DATA SHEET | REF.: 2544-19-SP-0110-01-B-CRS_0/E-01238
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-0510-0X-PA-CRS_0 | 28/06/16 | CLIENT COMMENTS TO DATA SHEET UNIT 19 FOR HOT OIL PUMPOUT COOLER 19-E-08 | REF:T-2059/MIDOR-TPIT-E-2016-06-29_08-18
CRS | MIDOR | 19 | PVHE | 2544-19-SP-0570-0X-PA-CRS_0 | 28/06/16 | CLIENT COMMENTS TO DATA SHEET UNIT 19 FOR HOT OIL PUMPOUT COOLER 19-E-08 | REF:T-2059/MIDOR-TPIT-E-2016-06-29_08-18
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-0630-01-PB-CRS_0 | 17/04/16 | CLIENT COMMENTS TO DATA UNIT 19 FOR HOT OIL PUMPOUT COOLER 19-E-08 | RE T-1447/MIDOR-TPIT-E-2016-04-17_21-00
CRS | MIDOR | 19 | PVHE | 2544-19-SP-0710-01-B-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 19 - MECHANICAL DATA SHEET | REF.: T-0565 -MIDOR-TPIT-E-2016-03-08_18
CRS | MIDOR | 19 | PVHE | 2544-19-SP-0710-02-B-CRS_0 | 04/03/16 | CLIENT COMMENTS TO UNIT 19 - MECHANICAL DATA SHEET | REF.: T-0565 -MIDOR-TPIT-E-2016-03-08_18
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-0810-01-PA-CRS_0 | 23/06/16 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEETS (19-V-01/02/03) | REF:T-1205/MIDOR-TPIT-E-2016-06-27_08-31
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-0810-02-PA-CRS_0 | 23/06/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR LOW PRESSURE SOLVENT DRUM 19 V 02 | REF:T-2058/MIDOR-TPIT-E-2016-06-23_13-47
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-0810-02-PA-CRS_1 | 01/03/17 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEETS (19-V-01/02/03) | REF:T-1205/MIDOR-TPIT-T-00197 | CLOSED |  | APPROVED
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-0810-02-PA-CRS-REPLY_0 | 17/10/16 | TPIT REPLY TO CLIENT COMMENTS TO PROCESS DATA SHEET FOR LOW PRESSURE SOLVENT DRUM 19 V 02 | REF:T-2058/TPIT-MIDOR-E-02298 |  |  | 2544-19-SP-0810-02-PA-CRS_1 - IDOR-TPIT-T-00197 APPROVED/CLOSED | 01/03/17
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-0810-03-PA-CRS_0 | 23/06/16 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEETS (19-V-01/02/03) | REF:T-1205/MIDOR-TPIT-E-2016-06-27_08-31
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-03-A-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEET FOR HOT OIL CIRCULATION PUMPS 19-P-09 A/B | REF:T-1119/MIDOR-TPIT-E-2016-05-09_13-20
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-03-A-CRS_1 | 26/07/17 | CLIENT COMMENTS TO DATA SHEETS FOR HOT OIL CIRCULATION PUMPS 19-P-09 A/B | REF:T-1119/MDR-T-E-2016-05-09_13-20/T371 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-04-A-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEET FOR PITCH STRIPPER WASH OIL PUMPS - 19-P-05 A/B | REF:T-1119/MIDOR-TPIT-E-2016-05-09_13-20
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-05-A-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEET FOR DAO PRODUCT PUMPS 19-P-04 A/B | REF:T-1119/MIDOR-TPIT-E-2016-05-09_13-20
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-05-A-CRS_1 | 26/07/17 | CLIENT COMMENTS TO CENTRIFUGAL PUMP DATA SHEET 19P04A/B&19P05A/B&19P09A/B&19P13&19P14 | REF:T-1119/MDR-T-E-2016-05-09_13-20/T371 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-05-A-CRS_2 | 28/07/17 | CLIENT COMMENTS TO CENTRIFUGAL PUMP DATA SHEET 19P04A/B&19P05A/B&19P09A/B&19P13&19P14 | REF:T-1119/MDR-TPIT-T-00375 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-06-A-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEET FOR HOT OIL TRANSFER PUMP - 19-P-14 | REF:T-1119/MIDOR-TPIT-E-2016-05-09_13-20
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-06-B-CRS_0 | 26/07/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEET FOR HOT OIL TRANSFER PUMP - 19-P-14 | REF:T-2102/MIDOR-TPIT-E-2016-07-27_07-10
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-06-PA-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEET | REF:T-0926/MIDOR-TPIT-E-2016-03-12_09-02
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-07-A-CRS_0 | 09/05/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEET FOR HOT OIL PUMP OUT PUMP - 19-P-13 | REF:T-1119/MIDOR-TPIT-E-2016-05-09_13-20
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-07-B-CRS_0 | 26/07/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEET FOR HOT OIL PUMP OUT PUMP - 19-P-13 | REF:T-2102/MIDOR-TPIT-E-2016-07-27_07-10
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-08-PB-CRS_0 | 08/03/16 | CLIENT COMMENTS TO DATA SHEET FOR UNIT RELIEF KNOCKOUT DRUM PUMPS - 19-P-10 A/B | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-08-PB-CRS_1 | 26/04/16 | CLIENT COMMENTS TO DATA SHEET FOR UNIT RELIEF KNOCKOUT DRUM PUMPS - 19-P-10 A/B | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-08-PB-CRS_2 | 04/05/16 | CLIENT COMMENTS TO DATA SHEET FOR UNIT RELIEF KNOCKOUT DRUM PUMPS - 19-P-10 A/B | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-08-PB-CRS_3 | 24/04/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR UNIT RELIEF KNOCKOUT DRUM PUMPS 19-P-10 A/B | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0910-10-A-CRS_0 | 26/07/16 | CLIENT COMMENTS TO DATA SHEET FOR H.C SLOP DRUM PUMP - 19-P-15 | REF:T-2102/MIDOR-TPIT-E-2016-07-27_07-10
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0920-01-PA-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEET | REF:T-0926/MIDOR-TPIT-E-2016-03-12_09-02
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0931-02-PB-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEET | REF:T-1051/MIDOR-TPIT-E-2016-03-15_11-39
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0931-02-PC-CRS_0 | 08/03/16 | CLIENT COMMENTS TO DATA SHEET FOR ROTARY PUMP (19-P-06 A/B) PITCH PRODUCT PUMPS | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0931-02-PC-CRS_1 | 24/04/16 | CLIENT COMMENTS TO DATA SHEET FOR ROTARY PUMP (19-P-06 A/B) PITCH PRODUCT PUMPS | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0931-02-PC-CRS_2 | 04/05/16 | CLIENT COMMENTS TO DATA SHEET FOR ROTARY PUMP (19-P-06 A/B) PITCH PRODUCT PUMPS | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | MACHINERY | 2544-19-SP-0931-02-PC-CRS_3 | 26/04/16 | CLIENT COMMENTS TO DATA SHEET FOR ROTARY PUMP (19-P-06 A/B) PITCH PRODUCT PUMPS | REF.: T-01527/MIDOR-TPIT-T-00064
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-01-PB-CRS_0 | 08/03/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-06 A/B PITCH PRODUCT PUMPS DRIVER | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-01-PB-CRS_1 | 26/04/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-06 A/B PITCH PRODUCT PUMPS DRIVER | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-01-PB-CRS_2 | 04/05/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-06 A/B PITCH PRODUCT PUMPS DRIVER | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-01-PB-CRS_3 | 25/05/17 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-06 A/B PITCH PRODUCT PUMPS DRIVER | REF.: T-01527/MIDOR-T-00290 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-02-A-CRS_0 | 26/07/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-10 B UNIT RELIEF KOD PUMP DRIVER | REF:T-2102/MIDOR-TPIT-E-2016-07-27_07-10
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-02-PA-CRS_0 | 08/03/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-10 B UNIT RELIEF KOD PUMP DRIVER | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-02-PA-CRS_1 | 26/04/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-10 B UNIT RELIEF KOD PUMP DRIVER | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 19 | PROCESS | 2544-19-SP-1111-02-PA-CRS_2 | 04/05/16 | CLIENT COMMENTS TO DATA SHEET FOR STEAM TURBINE 19-STP-10 B UNIT RELIEF KOD PUMP DRIVER | REF.: TPIT-MIDOR-T-01527
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-01-C-CRS_0 | 13/05/16 | CLIENT COMMENTS TO UNIT 20 BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF:T-1679/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-20-DW-0051-01-01-C-CRS-REPLY_0 TPIT-MIDOR-E-02088/MOM-0065 | 08/06/16
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-01-C-CRS_1 | 05/05/16 | CLIENT COMMENTS TO UNIT 20 BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF. TPIT-MIDOR-T-01679 | TPIT RESPONSE REQUIRED |  | 2544-20-DW-0051-01-01-C-CRS-REPLY_1 TPIT-MIDOR-E-02088/MOM-0065 | 08/07/16
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-01-C-CRS_2 | 26/09/16 | CLIENT COMMENTS TO UNIT 20 BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF.:T-1679/MIDOR-TPIT-T-00051 | TPIT RESPONSE REQUIRED |  | 2544-20-DW-0051-01-01-C-CRS_1 TPIT-MIDOR-T-00051 (CLOSED) | 26/09/16
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-01-C-CRS-REPLY | 13/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF: MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-20-DW-0051-01-01-C-CRS_1 TPIT-MIDOR-MOM-00065 | 08/09/16
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-01-C-CRS-REPLY_0 | 08/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF: T-1679/TPIT-MIDOR-E-02088/MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-20-DW-0051-01-01-C-CRS_1 MIDOR-TPIT-T-00051 | 26/09/16
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-01-C-CRS-REPLY_1 | 08/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF.:TPIT-MIDOR-E-02088/
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-01-C-CRS-REPLY_2 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF.:TPIT-MIDOR-E-02088/ |  |  | 2544-20-DW-0051-01-01-C-CRS_2 TPIT-MIDOR-MOM-00065
CRS | MIDOR | 20 | PIPING | 2544-20-DW-0051-01-C-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO BLOCK P - ZONE P201 UNIT 20 - HCK DETAILED PLOT PLAN | REF.:T-1679/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 20 | HSE DESIGN | 2544-20-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 20 - HCK FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-0108/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 20 | PROCESS | 2544-20-NM-0020-01-B-CRS_0 | 19/05/16 | CLIENT COMMENTS TO MEMORANDUM - P&IDS PROCESS MARK-UP FINAL ISSUE FOR EARLY WORKS AND OBE | REF.:TPIT-MIDOR-T-01539/PMC-MIDOR-E-0020
CRS | MIDOR | 20 | PROCESS | 2544-20-NM-0020-01-B-CRS-REPLY_0 | 01/06/16 | TPIT REPLY TO CLIENT COMMENTS TO MEMORANDUM - P&IDS PROCESS MARK-UP FINAL ISSUE FOR EARLY WORKS AND OBE | REF.:E-01717/2544-20-NM-0020-01-B-CRS_0
CRS | MIDOR | 20 | HSE DESIGN | 2544-20-PID-1931-01-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO PIPING &INSTRUMENT DIAGRAM UNIT 20, FIRE FIGHTING SYSTEM | REF:T-0636 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01141/2544-20-PID-1931-01-01-A-CRS-REPLY_0 | 17/03/16
CRS | MIDOR | 20 | HSE DESIGN | 2544-20-PID-1931-01-01-A-CRS_1 | 29/08/16 | CLIENT COMMENTS TO PIPING &INSTRUMENT DIAGRAM UNIT 20, FIRE FIGHTING SYSTEM | REF: TPIT-MIDOR-T-0636/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 20 | HSE DESIGN | 2544-20-PID-1931-01-01-A-CRS-REPLY_0 | 17/03/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING &INSTRUMENT DIAGRAM UNIT 20, FIRE FIGHTING SYSTEM | RE 2544-20-PID-1931-01-01-A-CRS_0/E-1141 | OWNER RESPONSE REQUIRED |  | 2544-20-PID-1931-01-01-A-CRS_1 | 01/09/16
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0570-05-PA-CRS_0 | 13/03/17 | CLIENT COMMENTS TO UNIT 20 PROCESS DATA SHEET FOR DIESEL STRIPPER TRAYS & INTERNALS 20-IT-54 | REF:T-1496/MIDOR-TPIT-T-2016-04-13_12-28 | CLOSED |  | APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-07-PB-CRS_0 | 21/05/16 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR PRODUCT FRACTIONATOR CONDENSER | REF.T-1638/MIDOR-TPIT-E-2016-05-21_01-12 |  |  | 2544-20-SP-0710-07-PB-CRS-REPLY_0 - TPIT-MIDOR-E-02555 | 04/01/17
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-07-PB-CRS_1 | 07/03/17 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR PRODUCT FRACTIONATOR CONDENSER | REF.:T-1638/MIDOR-TPIT-T-00206 |  |  | 2544-20-SP-0710-07-PB-CRS-REPLY_1 - MIDOR-TPIT-E-02744 | 08/03/17
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-07-PB-CRS_2 | 30/05/17 | CLIENT COMMENTS TO DATA SHEET FOR 20-E-64 | REF.:T-1638/MIDOR-TPIT-00336 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-07-PB-CRS-REPLY_0 | 04/01/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR PRODUCT FRACTIONATOR CONDENSER | REF.:T-1638/TPIT-MIDOR-E-02555 |  |  | 2544-20-SP-0710-07-PB-CRS_1 -TPIT-MIDOR-T-00206 | 07/03/17
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-07-PB-CRS-REPLY_1 | 08/03/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR PRODUCT FRACTIONATOR CONDENSER | REF.:T-1638/TPIT-MIDOR-E-02744 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-11-PB-CRS_0 | 21/05/16 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR FIRST STAGE DISCHARGE COOLERS | REF.T-1638/MIDOR-TPIT-E-2016-05-21_01-12 |  |  | 2544-20-SP-0710-11-PB-CRS-REPLY_0 - TPIT-MIDOR-E-02555 | 04/01/17
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-11-PB-CRS_1 | 07/03/17 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR FIRST STAGE DISCHARGE COOLERS | REF.:T-1638/MIDOR-TPIT-T-00206 |  |  | 2544-20-SP-0710-11-PB-CRS-REPLY_1 - MIDOR-TPIT-E-02744 | 08/03/17
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-11-PB-CRS_2 | 30/05/17 | CLIENT COMMENTS TO DATA SHEET FOR 20-E-11 A/B | REF.:T-1638/MIDOR-TPIT-00336 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-11-PB-CRS-REPLY_0 | 04/01/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR FIRST STAGE DISCHARGE COOLERS | REF.:T-1638/TPIT-MIDOR-E-02555 |  |  | 2544-20-SP-0710-11-PB-CRS_1 -TPIT-MIDOR-T-00206 | 07/03/17
CRS | MIDOR | 20 | PVHE | 2544-20-SP-0710-11-PB-CRS-REPLY_1 | 08/03/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET FOR FIRST STAGE DISCHARGE COOLERS | REF.:T-1638/TPIT-MIDOR-E-02744 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 20 | MACHINERY | 2544-20-SP-0910-07-PB-CRS_0 | 06/06/16 | CLIENT COMMENTS TO 20P80A/B DATA SHEET | REF:T-1642/MIDOR-TPIT-E-2016-06-06_10-48 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01846/2544-20-SP-0910-07-PB-CRS-REPLY_0 | 22/06/16
CRS | MIDOR | 20 | MACHINERY | 2544-20-SP-0910-07-PB-CRS-REPLY_0 | 22/06/16 | TPIT REPLY TO CLIENT COMMENTS TO 20P80A/B DATA SHEET | REF:E-1846/2544-20-SP-0910-07-PB-CRS_0
CRS | MIDOR | 20 | PROCESS | 2544-20-SP-0940-01-PA-CRS_0 | 19/05/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR LEAN GAS KNOCKOUT LIQUID PUMPS 20-P-83A/B (UOP BASIC DESIGN N. 9000571-503_0) | REF.:TPIT MIDOR-T-01577/PMC-MIDOR-E-0020 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01717/2544-20-SP-0940-01-PA-CRS-REPLY_0 | 01/07/16
CRS | MIDOR | 20 | PROCESS | 2544-20-SP-0940-01-PA-CRS-REPLY_0 | 01/06/16 | TPIT REPLY TO CLIENT COMMENTS PROCESS D/S FOR LEAN GAS KNOCKOUT LIQUID PUMPS 20-P-83A/B | REF.:E-01717/2544-20-SP-0940-01-PA-CRS_0
CRS | MIDOR | 20 | MACHINERY | 2544-20-SP-1011-01-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO RECYCLE GAS COMPRESSORS - ITEM 20-K-01 | REF.T-0173/MIDOR-TPIT-E-2016-03-07_08-16
CRS | MIDOR | 20 | PROCESS | 2544-20-SP-1111-02-PB-CRS_0 | 01/09/17 | CLIENT COMMENTS TO PROCESS FRACTIONATOR BOTTOMS PUMP STEAM TURBINE(20-STP-54B) | REF.T-01484/MIDOR-TPIT-T-00383 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 20 | MACHINERY | 2544-20-SP-1112-01-A-CRS_0 | 04/03/16 | CLIENT COMMENTS TO RECYCLE GAS COMPRESSORS STEAM TURBINE - ITEM 20-STK-01 | REF.T-0173/MIDOR-TPIT-E-2016-03-07_08-16
CRS | MIDOR | 20 | PACKAGES | 2544-20-SP-4046-01-PB-CRS_0 | 11/05/17 | CLIENT COMMENTS TO DATASHEET FOR CHEMICAL DOSING SYSTEM-PHOSPHATE DOSING PACK ITEM 20-PK-01 | REF.T-2537/MIDOR-T-00311 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 21 | PIPING | 2544-21-DW-0051-01-01-1-CRS_0 | 01/05/16 | CLIENT COMMENTS TO UNIT 21 PLOT PLAN | REF:TPIT-MIDOR-T-01538 | TPIT RESPONSE REQUIRED |  | 2544-21-DW-0051-01-01-1-CRS_0 TPIT-MIDOR-E-02088/MOM-0065 | 14/07/16
CRS | MIDOR | 21 | PIPING | 2544-21-DW-0051-01-01-1-CRS-REPLY_0 | 14/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 PLOT PLAN | REF.:TPIT-MIDOR-E-02088/MOM-0065
CRS | MIDOR | 21 | PIPING | 2544-21-DW-0051-01-01-2-CRS_0 | 15/05/16 | CLIENT COMMENTS TO UNIT 21 PLOT PLAN | REF:TPIT-MIDOR-T-1606 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-L-00037 | 10/06/16
CRS | MIDOR | 21 | PIPING | 2544-21-DW-0051-01-01-A-CRS_0 | 20/03/16 | CLIENT COMMENTS TO UNIT 21 PLOT PLAN | REF:T-0520/MIDOR-TPIT-E-2016-03-21_22-24 | TPIT RESPONSE REQUIRED |  | 2544-21-DW-0051-01-01-A-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 21 | PIPING | 2544-21-DW-0051-01-01-A-CRS_1 | 28/10/16 | CLIENT COMMENTS TO UNIT 21 PLOT PLAN
CRS | MIDOR | 21 | PIPING | 2544-21-DW-0051-01-01-A-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 PLOT PLAN | 21-DW-0051-01-01-A-CRS/E-01356/MOM65
CRS | MIDOR | 21 | CIVIL | 2544-21-DW-1442-01-01-A-CRS_0 | 23/02/17 | CLIENT COMMENTS TO CONCEPT DESIGN UNDERGROUND PIPING AND CABLE TRENCHES | REF:T-694/MIDOR-T-00188
CRS | MIDOR | 21 | CIVIL | 2544-21-DW-1442-01-01-A-CRS_1 | 13/03/17 | CLIENT COMMENTS TO CONCEPT DESIGN UNDERGROUND PIPING AND CABLE TRENCHES | REF:T-694/MIDOR-T-00188/MIDOR-T-2015 | CLOSED |  | APPROVEDO/CLOSED
CRS | MIDOR | 21 | CIVIL | 2544-21-DW-1442-01-01-A-CRS-REPLY_0 | 23/02/17 | TPIT REPLY TO CLIENT COMMENTS TO CONCEPT DESIGN UNDERGROUND PIPING AND CABLE TRENCHES | REF:T-0694/2544-21-DW-1442-01-01-A-CRS_0 | CLOSED |  | 2544-21-DW-1442-01-01-A-CRS_1 - TPIT-MIDOR-T-00215 APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 21 | CIVIL | 2544-21-DW-1442-01-01-E-CRS_0 | 01/06/16 | CLIENT COMMENTS TO CONCEPT DESIGN UNDERGROUND PIPING AND CABLE TRENCHES | REF:T-1882/MIDOR-TPIT-E-2016-06-01_10-59 | TPIT RESPONSE REQUIRED |  | 2544-21-DW-1442-01-01-E-CRS-REPLY_0 TPIT-MIDOR-E-01807 | 14/06/16
CRS | MIDOR | 21 |  | 2544-21-DW-1442-01-01-E-CRS_1 | 2018-02-21 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 CONCEPT DESIGN UNDERGROUND PIPING AND CABLE TRENCHES | REF:E-1807/MIDOR-TPIT-T-00445 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 21 | CIVIL | 2544-21-DW-1442-01-01-E-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 CONCEPT DESIGN UNDERGROUND PIPING AND CABLE TRENCHES | REF:2544-21-DW-1442-01-01-E-CRS_0/E-1807
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1612-01-01-C-CRS_0 | 02/05/16 | CLIENT COMMENTS TO GROUNDING AND LIGHTING SYSTEM LAYOUT | REF:T-1545/MIDOR-TPIT-E-2016-05-03_07-54
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-B-CRS_0 | 07/04/16 | CLIENT COMMENTS TO UNIT 21 ELECTRICAL MAIN CABLE ROUTING AND TRENCHES LAYOUT | REF:T-1370/MIDOR-TPIT-E-2016-04-07_08-39
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-B-CRS_1 | 23/02/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 ELECTRICAL MAIN CABLE ROUTING AND TRENCHES LAYOUT | REF:E-1431/MIDOR-TPIT-T-00188
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-B-CRS_2 | 13/03/01 | CLIENT COMMENTS TO UNIT 21 ELECTRICAL MAIN CABLE ROUTING AND TRENCHES LAYOUT | REF:E-1431/MIDOR-TPIT-T-00215 | CLOSED |  | APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-B-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 ELECTRICAL MAIN CABLE ROUTING AND TRENCHES LAYOUT | REF:E-1431/2544-21-DW-1620-01-01-B-CRS_0 |  |  | 2544-21-DW-1620-01-01-B-CRS_1 - MIDOR-TPIT-T-00188 | 23/02/17
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-C-CRS_0 | 21/05/16 | CLIENT COMMENTS TO UNIT 21 HYDROGEN PRODUCTION UNIT ELECTRICAL MAIN CABLE ROUTING AND TRENCH LAYOUT | REF:T-1653/MIDOR-TPIT-E-2016-05-22_07-23 | TPIT RESPONSE REQUIRED |  | 2544-21-DW-1620-01-01-C-CRS-REPLY_0 TPIT-MIDOR-E-01642 | 23/05/16
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-C-CRS_1 | 23/02/17 | CLIENT COMMENTS TO UNIT 21 ELECTRICAL MAIN CABLE ROUTING AND TRENCHES LAYOUT | REF:E-1620/MIDOR-TPIT-T-00188
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-C-CRS_2 | 13/03/17 | CLIENT COMMENTS TO UNIT 21 ELECTRICAL MAIN CABLE ROUTING AND TRENCHES LAYOUT | REF:T-1653/MIDOR-TPIT-T-00214 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1620-01-01-C-CRS-REPLY_0 | 23/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 ELECTRICAL MAIN CABLE ROUTING AND TRENCHES LAYOUT | REF:E-1620/2544-21-DW-1620-01-01-C-CRS_0
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1622-01-01-0-CRS_0 | 02/05/16 | CLIENT COMMENTS TO ELECTRICAL CABLE TRENCH LAYOUT | REF:T-1546/MIDOR-TPIT-E-2016-05-03_07-54
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1622-01-01-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 21 ELECTRICAL CABLE TRENCH LAYOUT | REF:T-0766/MIDOR-TPIT-E-2016-03-03_12-38 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01453/2544-21-DW-1622-01-01-A-CRS-REPLY_0 | 21/04/16
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1622-01-01-A-CRS-REPLY_0 | 21/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 ELECTRICAL CABLE TRENCH LAYOUT | REF:T-0766/MIDOR-TPIT-E-2016-03-03_12-38
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1632-01-01-B-CRS_0 | 02/05/16 | CLIENT COMMENTS TO HYDROGEN PRODUCTION UNIT LIGHTING SYSTEM LAYOUT | REF:T-1547/MIDOR-TPIT-E-2016-05-03_07-54
CRS | MIDOR | 21 | CIVIL | 2544-21-DW-1721-01-01-C-CRS_0 | 01/06/16 | CLIENT COMMENTS TO CONCEPT DESIGN FOUNDATION LOCATION PLAN UNIT 21 | REF:T-1883/MIDOR-TPIT-E-2016-06-01_10-58 | TPIT RESPONSE REQUIRED |  | 2544-21-DW-1721-01-01-C-CRS-REPLY_0 TPIT-MIDOR-E-01806 | 14/06/16
CRS | MIDOR | 21 | CIVIL | 2544-21-DW-1721-01-01-C-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 CONCEPT DESIGN FOUNDATION LOCATION PLAN | REF:2544-21-DW-1721-01-01-C-CRS_0/E-1806
CRS | MIDOR | 21 | HSE DESIGN | 2544-21-DW-1900-01-01-B-CRS_0 | 08/03/16 | CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:T-696/MIDOR-TPIT-E-2016-04-11_02-21 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01497 2544-21-DW-1900-01-01-B-CRS_0 | 29/04/16
CRS | MIDOR | 21 | HSE DESIGN | 2544-21-DW-1900-01-01-B-CRS-REPLY_0 | 29/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 FIRE PROTECTION AND GAS DETECTION PLOT PLAN | REF:T-0696/MIDOR-TPIT-E-2016-04-11_02-21
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1920-01-01-C-CRS_0 | 02/05/16 | CLIENT COMMENTS TO AREA CLASSIFICATION LAYOUT | REF:T-1548/MIDOR-TPIT-E-2016-05-03_07-54
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1920-01-01-C-CRS_1 | 19/12/16 | CLIENT COMMENTS TO AREA CLASSIFICATION LAYOUT | REF:T-1548/TPIT-E-2510/MIDOR-T-0150 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-DW-1920-01-01-C-CRS-REPLY_0 | 16/12/16 | TPIT REPLY TO CLIENT COMMENTS TO AREA CLASSIFICATION LAYOUT | REF:T-1548/TPIT-MIDOR-T-2510 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 21 |  | 2544-21-DW-1920-01-01-D-CRS_0 | 2018-02-21 | CLIENT COMMENTS TO AREA CLASSIFICATION LAYOUT | REF:T-2387/MIDOR-TPIT-T-00446 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 21 |  | 2544-21-DW-1920-01-01-D-CRS_1 | 2018-03-05 | CLIENT COMMENTS TO AREA CLASSIFICATION LAYOUT | REF:T-2387/MIDOR-TPIT-T-00450 | CLOSED |  | APPROVED
CRS | MIDOR | 21 | HSE DESIGN | 2544-21-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 21 FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-2162/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 21 | HSE DESIGN | 2544-21-DW-1950-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 21 FIRE AND GAS DETECTION LAYOUT | REF: TPIT-MIDOR-T-2162/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 21 | PROJECT MANAGEMENT | 2544-21-EL-101-B-CRS_0 | 08/07/16 | CLIENT COMMENTS TO UNIT 21 - EQUIPMENT LIST | REF: TPIT-MIDOR-T-0519/MIDOR-TPIT-T-0008 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02094 / 2544-21-EL-101-B-CRS-REPLY_0 | 31/08/16
CRS | MIDOR | 21 | PROJECT MANAGEMENT | 2544-21-EL-101-B-CRS_1 | 14/09/16 | CLIENT COMMENTS TO UNIT 21 - EQUIPMENT LIST | REF:TPIT-MIDOR-T-0519/MIDOR-TPIT-T-00059
CRS | MIDOR | 21 | PROJECT MANAGEMENT | 2544-21-EL-101-B-CRS-REPLY_0 | 31/08/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 - EQUIPMENT LIST | REF: 2544-21-EL-101-B-CRS_0/T-00008 | OWNER RESPONSE REQUIRED |  | 2544-21-EL-101-B-CRS_1 MIDOR-TPIT-T-00059 (CLOSED) | 14/09/16
CRS | MIDOR | 21 | HEATERS AND BOILERS | 2544-21-JSD-0113-01-0-CRS_0 | 03/05/16 | CLIENT COMMENTS TO MECHANICAL BASIS OF DESIGN FOR A REFORMER FURNACE | REF.: TPIT-MIDOR-T-01551 |  |  | 2544-21-JSD-0113-01-0-CRS-REPLY_0 TPIT-MIDOR-E-01534 | 06/05/16
CRS | MIDOR | 21 | HEATERS AND BOILERS | 2544-21-JSD-0113-01-0-CRS-REPLY_0 | 06/05/16 | TPTI REPLY TO CLIENT COMMENTS TO MECHANICAL BASIS OF DESIGN FOR A REFORMER FURNACE | REF.: TPIT-MIDOR-E-01534
CRS | MIDOR | 21 | HSE DESIGN | 2544-21-JSD-1900-02-1-CRS_0 | 18/05/16 | CLIENT COMMENTS TO MECHANICAL BASIS OF DESIGN FOR A REFORMER FURNACE | REF.: TPIT-MIDOR-T-01563
CRS | MIDOR | 21 | PROCESS | 2544-21-MSD-0011-01-01-B-CRS_0 | 06/04/16 | CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM HYDROGEN GENERATION UNIT | REF:T-1363/MIDOR-TPIT-E-2016-04-17_12-30 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01442/2544-21-MSD-0011-01-01-B-CRS-REPLY_0 | 21/04/16
CRS | MIDOR | 21 | PROCESS | 2544-21-MSD-0011-01-01-B-CRS-REPLY_0 | 21/04/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM HYDROGEN GENERATION UNIT | REF T-1363/2544-21-MSD-0011-01-01-B-CRS
CRS | MIDOR | 21 | PROCESS | 2544-21-MSD-0011-02-01-B-CRS_0 | 06/04/16 | CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM HYDROGEN GENERATION UNIT | REF:T-1363/MIDOR-TPIT-E-2016-04-17_12-30 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01442/2544-21-MSD-0011-02-01-B-CRS-REPLY_0 | 21/04/16
CRS | MIDOR | 21 | PROCESS | 2544-21-MSD-0011-02-01-B-CRS-REPLY_0 | 21/04/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM HYDROGEN GENERATION UNIT | REF T-1363/2544-21-MSD-0011-01-01-B-CRS
CRS | MIDOR | 21 | PROCESS | 2544-21-MSD-0011-03-01-B-CRS_0 | 06/04/16 | CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM HYDROGEN GENERATION UNIT | REF:T-1363/MIDOR-TPIT-E-2016-04-17_12-30 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01442/2544-21-MSD-0011-03-01-B-CRS-REPLY_0 | 21/04/16
CRS | MIDOR | 21 | PROCESS | 2544-21-MSD-0011-03-01-B-CRS-REPLY_0 | 21/04/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAM HYDROGEN GENERATION UNIT | REF T-1363/2544-21-MSD-0011-01-01-B-CRS
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-NM-1601-01-4-CRS_0 | 01/05/16 | CLIENT COMMENTS TO UNIT 21 - ELECTRICAL CONSUMER LIST | REF:T-1534/MIDOR-TPIT-E-2016-05-01_20-47
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-NM-1601-01-5-CRS_0 | 02/05/16 | CLIENT COMMENTS TO ELECTRICAL CONSUMER LIST | REF:T-1552/MIDOR-TPIT-E-2016-05-03_07-54
CRS | MIDOR | 21 | ELECTRICAL | 2544-21-NM-1623-01-3-CRS_0 | 02/05/16 | CLIENT COMMENTS TO ELECTRICAL CABLE SCHEDULE | REF:T-1553/MIDOR-TPIT-E-2016-05-03_07-54
CRS | MIDOR | 21 | PROCESS | 2544-21-PID-0021-2-CRS_0 | 10/06/16 | CLIENT COMMENTS TO UNIT 21 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-1581/PMC-MIDOR-E-0044 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01823/2544-21-PID-0021-2-CRS-REPLY_0 | 17/06/16
CRS | MIDOR | 21 | PROCESS | 2544-21-PID-0021-2-CRS-REPLY_0 | 17/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 - PIPING AND INSTRUMENT DIAGRAMS | REF:E-1823/2544-21-PID-0021-2-CRS_0
CRS | MIDOR | 21 | PROCESS | 2544-21-PID-0031-2-CRS_0 | 10/06/16 | CLIENT COMMENTS TO UNIT 21 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-1581/PMC-MIDOR-E-0044
CRS | MIDOR | 21 | PVHE | 2544-21-SP-0610-03-PC-CRS_0 | 13/04/16 | CLIENT COMMENTS TO UNIT 21 PROCESS DATA SHEET BFW PREHEATER (21-E-04) | REF:T-1366/MIDOR-TPIT-E-2016-04-13_10-21 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01436/2544-21-SP-0610-03-PC-CRS-REPLY_0 | 13/04/16
CRS | MIDOR | 21 | PVHE | 2544-21-SP-0610-03-PC-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 PROCESS DATA SHEET BFW PREHEATER (21-E-04) | REF:E-1436/2544-21-SP-0610-03-PC-CRS_0
CRS | MIDOR | 21 | PVHE | 2544-21-SP-0610-04-PD-CRS_0 | 13/04/16 | CLIENT COMMENTS TO UNIT 21 PROCESS DATASHEET BFW PREHEATER (CLEAN STEAM) (21-E-05) | REF:T-1366/MIDOR-TPIT-E-2016-04-13_10-21 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01436/2544-21-SP-0610-04-PD-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 21 | PVHE | 2544-21-SP-0610-04-PD-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 PROCESS DATASHEET BFW PREHEATER (CLEAN STEAM) (21-E-05) | REF::E-1436/2544-21-SP-0610-04-PD-CRS_0
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-01-02-CRS_0 | 15/06/16 | CLIENT COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-01 A/B) | REF.: TPIT-MIDOR-T-01986 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01812/2544-21-SP-0910-01-02-CRS-REPLY_0 | 15/06/16
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-01-02-CRS_1 | 03/07/16 | CLIENT COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-01 A/B) | REF.T-1986/MIDOR-TPIT-E-2016-07-03_13-35 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01899/2544-21-SP-0910-01-02-CRS-REPLY_1 | 04/07/16
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-01-02-CRS_2 | 20/04/17 | CLIENT APPROVED COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-01 A/B) | REF.E-1899/MIDOR-TPIT-T-00274 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-01-02-CRS-REPLY_0 | 15/06/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-01 A/B) | REF.:E-1812/2544-21-SP-0910-01-02-CRS_0
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-01-02-CRS-REPLY_1 | 04/07/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-01 A/B) | REF.E-1899/2544-21-SP-0910-01-02-CRS_1 |  |  | 2544-21-SP-0910-01-02-CRS_2 MIDOR-TPIT-T-00274 APPROVED/CLOSED | 20/04/17
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-01-PC-CRS_0 | 17/04/16 | CLIENT COMMENTS TO UNIT 21 - D/S FOR PUMPS | REF:T-1368/MIDOR-TPIT-E-2016-04-17_22-09 | TPIT RESPONSE REQUIRED |  | 2544-21-SP-0910-01-PC-CRS-REPLY_0 TPIT-MIDOR-E-01537 | 06/05/16
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-01-PC-CRS-REPLY_0 | 06/05/16 | TPIT REPLY TO CLIENT COMMENTS TO PROCESS DATA SHEET BFW BOOSTER PUMP (21-P-01 A/B) | REF.:2544-21-SP-0910-01-PC-CRS_0/E-01537 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-05-29_12-09 | 29/05/16
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-02-02-CRS_0 | 16/05/16 | CLIENT COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-02 A/B) | REF.T-1569/MIDOR-E-2016-05-16_19-10 |  |  | 2544-21-SP-0910-02-02-CRS-REPLY_0 TPIT-MIDOR-E-02764 | 14/03/13
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-02-02-CRS_1 | 07/04/17 | CLIENT COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-02 A/B) | REF.T-1569/MIDOR-T-00259 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-0910-02-02-CRS-REPLY_0 | 14/03/17 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL DATA SHEET BFW BOOSTER PUMP (21-P-02 A/B) | REF.T-1569/TPIT-MIDOR-E-02764 |  |  | 2544-21-SP-0910-02-02-CRS_1 MIDOR-TPIT-T-00259 REVIEWED WITH COMMENTS | 07/04/17
CRS | MIDOR | 21 | MACHINERY | 2544-21-SP-1020-01-1-CRS_0 | 10/05/16 | CLIENT COMMENTS TO MECHANICAL DATA SHEET RECIPROCATING COMPRESSOR (21-K-01) | REF.: TPIT-MIDOR-T-01599
CRS | MIDOR | 22 | PIPING | 2544-22-DW-0051-01-01-B-CRS_0 | 13/05/16 | CLIENT COMMENTS TO UNIT 22 - SULPHUR RECOVERY AND TGT (3RD TRAIN ) PLOT PLAN | REF:T-1069/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-22-DW-0051-01-01-B-CRS-REPLY_0 TPIT-MIDOR-E-02088/MOM-0065 | 17/06/16
CRS | MIDOR | 22 | PIPING | 2544-22-DW-0051-01-01-B-CRS_1 | 27/09/16 | CLIENT COMMENTS TO UNIT 22 - SULPHUR RECOVERY AND TGT (3RD TRAIN ) PLOT PLAN | REF:T-1069/MIDOR-TPIT-T-00054 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 22 | PIPING | 2544-22-DW-0051-01-01-B-CRS-REPLY_0 | 17/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 22 - SULPHUR RECOVERY AND TGT (3RD TRAIN ) PLOT PLAN | REF: T-1069/TPIT-MIDOR-E-02088/MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-22-DW-0051-01-01-B-CRS_1 MIDOR-TPIT-T-000054 (CLOSED) | 27/09/16
CRS | MIDOR | 22 | ELECTRICAL | 2544-22-DW-1622-01-01-A-CRS_0 | 23/02/17 | CLIENT COMMENTS TO SULPHUR RECOVERY & TGT 3RD TRAIN CABLE ROUTING | REF:T-0680/MIDOR-TPIT-T-00188 |  |  | 2544-22-DW-1622-01-01-A-CRS-REPLY_0 - TPIT-MIDOR-E-02755 | 10/03/17
CRS | MIDOR | 22 | ELECTRICAL | 2544-22-DW-1622-01-01-A-CRS_1 | 13/03/17 | CLIENT COMMENTS TO SULPHUR RECOVERY & TGT 3RD TRAIN CABLE ROUTING | REF:T-0680/MIDOR-TPIT-T-001215 | CLOSED |  | APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 22 | ELECTRICAL | 2544-22-DW-1622-01-01-A-CRS-REPLY_0 | 10/03/17 | CLIENT COMMENTS TO SULPHUR RECOVERY & TGT 3RD TRAIN CABLE ROUTING | REF:T-0680/MIDOR-T-00188/TPIT-E 2755 | CLOSED |  | 2544-22-DW-1622-01-01-A-CRS_1-MIDOR-TPIT-T-00215 | 13/03/17
CRS | MIDOR | 22 | CIVIL | 2544-22-DW-1822-03-B-CRS-REPLY_0 | 07/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 22 - ONE LINE DIAGRAM FOR STEEL ROAD | REF: T-01263/TPIT-MIDOR-E-02235 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 22 | PROJECT MANAGEMENT | 2544-22-EL-101-B-CRS_0 | 11/07/16 | CLIENT COMMENTS TO UNIT 22 - EQUIPMENT LIST | REF: TPIT-MIDOR-T-1289/MIDOR-TPIT-T-0008 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02094 / 2544-22-EL-101-B-CRS-REPLY_0 | 31/08/16
CRS | MIDOR | 22 | PROJECT MANAGEMENT | 2544-22-EL-101-B-CRS_1 | 26/09/16 | CLIENT COMMENTS TO UNIT 22 - EQUIPMENT LIST | REF:TPIT-MIDOR-T-1289/MIDOR-TPIT-T-00059 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 22 | PROJECT MANAGEMENT | 2544-22-EL-101-B-CRS-REPLY_0 | 31/08/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 22 - EQUIPMENT LIST | REF: 2544-22-EL-101-B-CRS_0/T-00008 | OWNER RESPONSE REQUIRED |  | 2544-22-EL-101-B-CRS_1 MIDOR-TPIT-T-00059 (CLOSED) | 26/09/16
CRS | MIDOR | 22 | PROCESS | 2544-22-PID-0021-041-01-B-CRS_0 | 29/09/16 | CLIENT COMMENTS TO UNIT 22 - PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-01353/MIDOR-TPIT-T-0070 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 22 | PROCESS | 2544-22-PID-0021-B-CRS_0 | 14/04/16 | CLIENT COMMENTS TO UNIT 22 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-1353/MIDOR-TPIT-E-2016-04-14_13-15 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01429/2544-22-PID-0021-B-CRS-REPLY_0 | 20/04/16
CRS | MIDOR | 22 | PROCESS | 2544-22-PID-0021-B-CRS_1 | 15/06/16 | CLIENT COMMENTS TO UNIT 22 - PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-01353/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01944/2544-22-PID-0021-B-CRS-REPLY_1 | 13/07/16
CRS | MIDOR | 22 | PROCESS | 2544-22-PID-0021-B-CRS-REPLY_0 | 20/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 22 - PIPING AND INSTRUMENT DIAGRAMS | REF:E-1429/2544-22-PID-0021-B-CRS_0
CRS | MIDOR | 22 | PROCESS | 2544-22-PID-0021-B-CRS-REPLY_1 | 13/07/16 | TPIT-REPLY TO CLIENT COMMENTS TO UNIT 22 - PIPING AND INSTRUMENT DIAGRAMS | REF:E-01944/2544-22-PID-0021-B-CRS_1
CRS | MIDOR | 22 | PROCESS | 2544-22-PID-0031-B-CRS_0 | 15/06/16 | CLIENT COMMENTS TO UNIT 22 - PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-01364/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01944/2544-22-PID-0031-B-CRS-REPLY_0 | 13/07/16
CRS | MIDOR | 22 | PROCESS | 2544-22-PID-0031-B-CRS-REPLY_0 | 13/07/16 | TPIT-REPLY TO CLIENT COMMENTS TO UNIT 22 - PIPING AND INSTRUMENT DIAGRAMS | REF:E-01944/2544-22-PID-0031-B-CRS_0
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-0660-01-B-CRS_0 | 11/04/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR HEAT EXCHANGERS/WATER COOLERS | REF:T-0828/MIDOR-TPIT-E-2016-04-12_07-29
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-0660-03-B-CRS_0 | 11/04/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR HEAT EXCHANGERS/WATER COOLERS | REF:T-0828/MIDOR-TPIT-E-2016-04-12_07-29
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-02-A-22P02-CRS-REPLY_1 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET UNDEGASSED SULPHUR PUMPS 22 P 02 A/B | REF.: T-00203/TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-02-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-03-A-22P03-CRS-REPLY_0 | 29/05/17 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET DEGASSED SULPHUR PUMPS 22 P 03 A/B | REF.: T-00203/TPIT-MIDOR-MOM-00123 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-03-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-05-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-06-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-07-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-08-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-09-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | MACHINERY | 2544-22-SP-0910-10-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF:T-0730/MIDOR-TPIT-E-2016-04-19_21-41
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-1040-01-PA-CRS_0 | 18/07/17 | CLIENT COMMENTS TO DATA SHEET FOR AIR BLOWER 22-K-01 | REF:T-0193/MDR-TPIT-T-00366 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-1040-01-PB-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR AIR BLOWER | REF:T-0932/MIDOR-TPIT-E-2016-03-11_11-16
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-1040-01-PB-CRS_1 | 01/09/17 | CLIENT COMMENTS TO DATA SHEET FOR AIR BLOWER 22-K-01 | REF:T-932/MDR-T-E-2016-03-11_11-16/T-384 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-1040-02-PC-CRS_0 | 06/04/16 | CLIENT COMMENTS TO DATA SHEET FOR INCINERATOR AIR FANS 22 F 01 A/B | RE T-1292/MIDOR-TPIT-E-2016-04-06_13-23 | TPIT RESPONSE REQUIRED |  | 2544-22-SP-1040-02-PC-CRS-REPLY_0 | 11/04/16
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-1040-02-PC-CRS_1 | 17/04/16 | CLIENT COMMENTS TO DATA SHEET FOR INCINERATOR AIR FANS 22 F 01 A/B | RE T-1292/MIDOR-TPIT-E-2016-04-18_06-15
CRS | MIDOR | 22 | PROCESS | 2544-22-SP-1040-02-PC-CRS-REPLY_0 | 11/04/16 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET FOR INCINERATOR AIR FANS 22 F 01 A/B | REF: E-1350/2544-22-SP-1040-02-PC-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-22-SP-1040-02-PC-CRS_1 | 17/04/16
CRS | MIDOR | 23 | PIPING | 2544-23-DW-0051-01-01-C-CRS_0 | 21/03/16 | CLIENT COMMENTS TO UNIT 23 - AMINE REGENERATOR UNIT PLOT PLAN | REF:T-1086/MIDOR-TPIT-E-2016-03-21_22-09 | TPIT RESPONSE REQUIRED |  | 2544-23-DW-0051-01-01-C-CRS-REPLY_0 | 31/03/16
CRS | MIDOR | 23 | PIPING | 2544-23-DW-0051-01-01-C-CRS_1 | 13/05/16 | CLIENT COMMENTS TO UNIT 23 - AMINE REGENERATOR UNIT PLOT PLAN | REF:T-1086/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-23-DW-0051-01-01-C-CRS-REPLY_1 | 04/10/16
CRS | MIDOR | 23 | PIPING | 2544-23-DW-0051-01-01-C-CRS_2 | 04/10/16 | CLIENT COMMENTS TO UNIT 23 - AMINE REGENERATOR UNIT PLOT PLAN | REF:T-1086
CRS | MIDOR | 23 | PIPING | 2544-23-DW-0051-01-01-C-CRS-REPLY_0 | 31/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 - AMINE REGENERATOR UNIT PLOT PLAN | REF: 2544-23-DW-0051-01-01-C-CRS/E-1248
CRS | MIDOR | 23 | PIPING | 2544-23-DW-0051-01-01-C-CRS-REPLY_1 | 04/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 - AMINE REGENERATOR UNIT PLOT PLAN | REF: TPIT-MIDORT-01086 | OWNER RESPONSE REQUIRED |  | 2544-23-DW-0051-01-01-C-CRS_2 MIDOR-TPIT-T-00067 (CLOSED) | 04/10/16
CRS | MIDOR | 23 | ELECTRICAL | 2544-23-DW-1622-01-01-A-CRS_0 | 23/02/17 | CLIENT COMMENTS TO AMINE REGENERATOR UNIT MAIN CABLE ROUTING | REF:T-0681/MIDOR-TPIT-T-00188 |  |  | 2544-23-DW-1622-01-01-A-CRS-REPLY_0 - TPIT-MIDOR-E-02755 | 10/03/17
CRS | MIDOR | 23 | ELECTRICAL | 2544-23-DW-1622-01-01-A-CRS_1 | 13/03/17 | CLIENT COMMENTS TO AMINE REGENERATOR UNIT MAIN CABLE ROUTING | REF:T-0680/MIDOR-TPIT-T-001215 | CLOSED |  | APPROVED/CLOSED | 13/03/17
CRS | MIDOR | 23 | ELECTRICAL | 2544-23-DW-1622-01-01-A-CRS-REPLY_0 | 10/03/17 | CLIENT COMMENTS TO AMINE REGENERATOR UNIT MAIN CABLE ROUTING | REF:T-0680/MIDOR-T-00188/TPIT-E 2755 | CLOSED |  | 2544-23-DW-1622-01-01-A-CRS_1-MIDOR-TPIT-T-00215 | 13/03/17
CRS | MIDOR | 23 | ELECTRICAL | 2544-23-NM-1601-01-B-CRS_0 | 23/02/17 | CLIENT COMMENTS TO UNIT 23 - ELECTRICAL CONSUMER LIST | REF:T-1601/TPIT-MIDOR-T-00188 |  |  | 2544-23-NM-1601-01-B-CRS-REPLY_0 - TPIT-MIDPR-E-02755 | 10/03/17
CRS | MIDOR | 23 | ELECTRICAL | 2544-23-NM-1601-01-B-CRS_1 | 13/03/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 - ELECTRICAL CONSUMER LIST | REF:T-1601/TPIT-E-02755/MIDOR-T-00215 | CLOSED |  | APPROVED CLOSED | 13/03/17
CRS | MIDOR | 23 | ELECTRICAL | 2544-23-NM-1601-01-B-CRS-REPLY_0 | 10/03/17 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 - ELECTRICAL CONSUMER LIST | REF:T-1601/MIDOR-T-00188/TPIT-E-02755 | CLOSED |  | 2544-23-NM-1601-01-B-CRS_1 - MIDOR-TPIT-T-00215 APPROVED CLOSED | 13/03/17
CRS | MIDOR | 23 | PROCESS | 2544-23-NM-2100-01-A-CRS_0 | 04/04/16 | CLIENT COMMENTS TO UNIT 23 - LABORATORY TEST SCHEDULE | REF:T-1257/MIDOR-TPIT-E-2016-04-05_14-16 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01381/2544-23-NM-2100-01-A-CRS-REPLY_0 | 14/04/16
CRS | MIDOR | 23 | PROCESS | 2544-23-NM-2100-01-A-CRS-REPLY_0 | 14/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 - LABORATORY TEST SCHEDULE | REF: E-01381/2544-23-NM-2100-01-A-CRS_0
CRS | MIDOR | 23 | PROCESS | 2544-23-PID-0021-B-CRS_0 | 13/06/16 | CLIENT COMMENTS TO UNIT 23 PIPING AND INSTRUMENT DIAGRAM - UNIT 23 - AMINE REGENERATION UNIT | REF:TPIT-MIDOR-T-01342/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01945 /2544-23-PID-0021-B-CRS-REPLY_0 | 13/07/16
CRS | MIDOR | 23 | PROCESS | 2544-23-PID-0021-B-CRS-REPLY_0 | 13/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 PIPING AND INSTRUMENT DIAGRAM - UNIT 23 - AMINE REGENERATION UNIT | REF: E-1945/2544-23-PID-0021-B-CRS_0
CRS | MIDOR | 23 | PROCESS | 2544-23-PID-0031-B-CRS_0 | 13/06/16 | CLIENT COMMENTS TO UNIT 23 PIPING AND INSTRUMENT DIAGRAM - SULPHUR RECOVERY UNIT AND TAIL GAS TREATMENT UNIT UTILITIES | REF:TPIT-MIDOR-T-01365/PMC-MIDOR-E-0063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01945 / 2544-23-PID-0031-B-CRS-REPLY_0 | 13/07/16
CRS | MIDOR | 23 | PROCESS | 2544-23-PID-0031-B-CRS-REPLY_0 | 13/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 PIPING AND INSTRUMENT DIAGRAM - UNIT 23 - AMINE REGENERATION UNIT | REF: E-1945/2544-23-PID-0031-B-CRS_0
CRS | MIDOR | 24 | PIPING | 2544-24-DW-0051-01-01-A-CRS_0 | 24/07/16 | CLIENT COMMENTS TO UNIT 24 SOUR WATER STRIPPER (3RD TRAIN) PLOT PLAN | REF:T-2191/MIDOR-TPIT-E-2016-07-31_16-38 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02054 / 2544-24-DW-0051-01-01-A-CRS-REPLY_0 | 08/08/16
CRS | MIDOR | 24 | PIPING | 2544-24-DW-0051-01-01-A-CRS_1 | 08/07/16 | CLIENT COMMENTS TO UNIT 24 SOUR WATER STRIPPER (3RD TRAIN) PLOT PLAN | REF:T-2191 | TPIT RESPONSE REQUIRED |  | 2544-24-DW-0051-01-01-A-CRS-REPLY_1 - TPIT-MIDOR-E-02088/MOM-0065 | 15/07/16
CRS | MIDOR | 24 | PIPING | 2544-24-DW-0051-01-01-A-CRS_2 | 30/09/16 | CLIENT COMMENTS TO UNIT 24 SOUR WATER STRIPPER (3RD TRAIN) PLOT PLAN | REF: MIDOR-TPIT-T-00063
CRS | MIDOR | 24 | PIPING | 2544-24-DW-0051-01-01-A-CRS-REPLY_0 | 08/08/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 24 SOUR WATER STRIPPER (3RD TRAIN) PLOT PLAN | REF:E-2054/2544-24-DW-0051-01-01-A-CRS_0
CRS | MIDOR | 24 | PIPING | 2544-24-DW-0051-01-01-A-CRS-REPLY_1 | 15/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 24 PLOT PLAN | REF.:TPIT-MIDOR-E-02088/MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-24-DW-0051-01-01-A-CRS_2 MIDOR-TPIT-T-00063 (CLOSED) | 30/09/16
CRS | MIDOR | 24 | CIVIL | 2544-24-DW-1442-01-01-A-CRS_0 | 28/07/16 | CLIENT COMMENTS TO UNIT 24 - SOUR WATER STRIPPER UG LAYOUT SEWER AND DRAINAGE SYSTEMS AND CONCRETE TRENCH | REF:T-2332/MIDOR-TPIT-E-2016-07-31_15-38 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02017/2544-24-DW-1442-01-01-A-CRS-REPLY_0 | 01/08/16
CRS | MIDOR | 24 | CIVIL | 2544-24-DW-1442-01-01-A-CRS-REPLY_0 | 01/08/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 24 - SOUR WATER STRIPPER UG LAYOUT SEWER AND DRAINAGE SYSTEMS AND CONCRETE TRENCH | REF:E-2017/2544-24-DW-1442-01-01-A-CRS_0
CRS | MIDOR | 24 | HSE DESIGN | 2544-24-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 24 - SOUR WATER STRIPPER (3RD TRAIN) - FIRE-FIGHTING & FIRE PROTECTION DRAWING - LAYOUT | REF: TPIT-MIDOR-T-2258/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 24 | HSE DESIGN | 2544-24-DW-1950-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 24 - SOUR WATER STRIPPER (3RD TRAIN) LOCATION OF FIRE & GAS DETECTION | REF: TPIT-MIDOR-T-2258/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 24 | PROCESS | 2544-24-PID-0021-A-CRS_0 | 07/07/16 | CLIENT COMMENTS TO UNIT 24 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-02209/PMC-MIDOR-E-0066 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01963 / 2544-24-PID-0021-A-CRS-REPLY_0 | 14/07/16
CRS | MIDOR | 24 | PROCESS | 2544-24-PID-0021-A-CRS-REPLY_0 | 14/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 24 PIPING AND INSTRUMENT DIAGRAMS | REF:E-01963 / 2544-24-PID-0021-A-CRS_0
CRS | MIDOR | 25 | PACKAGES | 2544-25-SP-4110-101-A-CRS_0 | 06/10/17 | CLIENT COMMENTS TO PARTICULAR TECHNICAL SPECIFICATION FOR MODULAR LPG TREATMENT UNIT (UNIT 25) | REF:T-02710/MIDOR-TPIT-T-00406
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-B-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF:T-1179/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-31-DW-0051-01-01-B-CRS-REPLY_0 TPIT-MIDOR-E-02089 | 02/09/16
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-B-CRS_1 | 30/09/16 | CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF:T-1179/MIDOR-TPIT-T-00063 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF:E-2088/2544-31-DW-0051-01-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-31-DW-0051-01-01-B-CRS_1 MIDOR-TPIT-T-00063 (CLOSED) | 30/09/16
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-C-CRS_0 | 25/05/16 | CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF.:1779/MIDOR-TPIT-E-2016-05-26_11-12 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02115 / 2544-31-DW-0051-01-01-C-CRS-REPLY_0 | 12/09/16
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-C-CRS_1 | 25/05/16 | CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF:T-1779/MIDOR-TPIT-E-2016-05-26_23-54 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02115 / 2544-31-DW-0051-01-01-C-CRS-REPLY_2 | 12/09/16
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-C-CRS_2 | 27/05/16 | CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF.: TPIT-MIDOR-T-01779 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02115 / 2544-31-DW-0051-01-01-C-CRS-REPLY_1 | 12/09/16
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-C-CRS-REPLY_0 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF:E-2115/2544-31-DW-0051-01-01-C-CRS_0
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-C-CRS-REPLY_1 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF:E-2115/2544-31-DW-0051-01-01-C-CRS_2
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-01-C-CRS-REPLY_2 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF:E-2115/2544-31-DW-0051-01-01-C-CRS_1
CRS | MIDOR | 31 | PIPING | 2544-31-DW-0051-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B DETAILED PLOT PLAN | REF.:T-1179/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 31 | INSTRUMENTATION | 2544-31-DW-1572-01-01-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 31 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1992/MIDOR-TPIT-E-2016-06-15_02-36
CRS | MIDOR | 31 | ELECTRICAL | 2544-31-DW-1622-01-01-A-CRS_0 | 18/03/16 | CLIENT COMMENTS TO UNIT 31 ZONE U2B ELECTRICAL MAIN CABLE ROUTINGS | REF:T-0989/MIDOR-TPIT-E-2016-03-19_07-01 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01213 2544-31-DW-1622-01-01-A-CRS-REPLY_0 | 22/03/16
CRS | MIDOR | 31 | ELECTRICAL | 2544-31-DW-1622-01-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 31 ZONE U2B ELECTRICAL MAIN CABLE ROUTINGS | REF:T-00989/E-1213/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 31 | ELECTRICAL | 2544-31-DW-1622-01-01-A-CRS-REPLY_0 | 22/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 ZONE U2B ELECTRICAL MAIN CABLE ROUTINGS | REF:E-1213/2544-31-DW-1622-01-01-A-CRS_0
CRS | MIDOR | 31 | ELECTRICAL | 2544-31-DW-1622-01-01-B-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 31 - RAW WATER BLOCK U - ZONE U2B ELECTRICAL MAIN CABLE ROUTING | REF:T-1436/MIDOR-TPIT-E-2016-04-17_05-51 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01993/2544-31-DW-1622-01-01-B-CRS-REPLY_0 | 20/07/16
CRS | MIDOR | 31 | ELECTRICAL | 2544-31-DW-1622-01-01-B-CRS-REPLY_0 | 20/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 ZONE U2B ELECTRICAL MAIN CABLE ROUTINGS | REF:E-1993/2544-31-DW-1622-01-01-B-CRS_0
CRS | MIDOR | 31 | PROCESS | 2544-31-JSD-0001-01-A-CRS_0 | 28/07/16 | CLIENT COMMENTS TO POTABLE WATER DESIGN BASIS | REF:T-2334/MIDOR-TPIT-E-2016-07-31_10-46
CRS | MIDOR | 31 | PROCESS | 2544-31-JSD-0001-01-A-CRS_1 | 07/11/16 | CLIENT COMMENTS TO POTABLE WATER DESIGN BASIS | REF:T-2334/MIDOR-TPIT-T-00122 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 31 | PROCESS | 2544-31-JSD-0001-01-A-CRS_2 | 22/11/16 | CLIENT COMMENTS TO POTABLE WATER DESIGN BASIS | REF:T-2334/M-T-00122/T-E-2416-M-T-131 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 31 | PROCESS | 2544-31-JSD-0001-01-A-CRS-REPLY_0 | 24/10/16 | TPIT REPLY TO CLIENT COMMENTS TO POTABLE WATER DESIGN BASIS | REF:T-2334/TPIT-E-02331 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 31 | PROCESS | 2544-31-JSD-0001-01-A-CRS-REPLY_1 | 15/11/16 | TPIT REPLY TO CLIENT COMMENTS TO POTABLE WATER DESIGN BASIS | REF:T-2334/MIDOR-T-00122/TPIT-E-2416 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 31 | PROCESS | 2544-31-JSD-0001-01-A-CRS-REPLY_2 | 25/11/16 | TPIT REPLY TO CLIENT COMMENTS TO POTABLE WATER DESIGN BASIS | REF:T-2334/MIDOR-T-00122/TPIT-E-2453 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 31 | PROCESS | 2544-31-PID-0021-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 31 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-0862/MIDOR-TPIT-E-2016-03-08_10-08
CRS | MIDOR | 31 | PROCESS | 2544-31-PID-0021-B-CRS_0 | 01/06/16 | CLIENT COMMENTS TO U 31 PID | REF:T-1853/MIDOR-TPIT-E-2016-06-02_08-30
CRS | MIDOR | 31 | MACHINERY | 2544-31-SP-0910-02-PB-CRS_0 | 15/06/16 | CLIENT COMMENTS UF FEED PUMPS FOR 31-P-03 A/B-N | REF:T-1953/MIDOR-TPIT-E-2016-06-15_12-55
CRS | MIDOR | 31 | MACHINERY | 2544-31-SP-0910-04-PA-CRS_0 | 15/06/16 | CLIENT COMMENTS TO FILTERED EFFLUENT PUMPS 31-P-05 A/B-N | REF:T-2024/MIDOR-TPIT-E-2016-06-15_13-00
CRS | MIDOR | 34 | PROCESS | 2544-34-PID-0021-001-01-B-CRS_0 | 08/06/16 | CLIENT COMMENTS TO UNIT 34 PIPING AND INSTRUMENT DIAGRAM - NITROGEN PRODUCTION UNIT 42-PK-02-N | REF:T-1854/MIDOR-TPIT-E-2016-06-10_16-46
CRS | MIDOR | 36 | INSTRUMENTATION | 2544-36-DW-1572-01-01-A-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 36 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1993/MIDOR-TPIT-E-2016-06-15_02-36
CRS | MIDOR | 36 | INSTRUMENTATION | 2544-36-DW-1572-01-01-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 36 - INSTRUMENT MAIN CABLE ROUTING | REF:T-1993/MIDOR-TPIT-E-2016-06-15_02-36
CRS | MIDOR | 36 | MACHINERY | 2544-36-SP-0910-01-PB-CRS_0 | 08/06/16 | CLIENT COMMENTS TO DATA SHEET FOR DEMI PACKAGE FEED PUMP 36-P-02 A/B-N | REF:T-1903/MIDOR-TPIT-E-2016-06-08_13-27
CRS | MIDOR | 36 | MACHINERY | 2544-36-SP-0910-03-PA-CRS_0 | 08/06/16 | CLIENT COMMENTS TO DATA SHEET FOR UF EFFLUENT PUMPS 36-P-04 A/N | REF:T-1903/MIDOR-TPIT-E-2016-06-08_13-27
CRS | MIDOR | 37 | PIPING | 2544-37-DW-0051-01-01-B-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 36TO38-41TO44-B.F.W.STEAM GENERAT.-CONDENSATE TREAT.P.AIR/I.AIR NITROGEN CAUSTIC-UNCONVERT | REF:T-1198/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-37-DW-0051-01-01-B-CRS-REPLY_0 TPIT-MIDOR-E-02088/MOM-0065 | 13/06/16
CRS | MIDOR | 37 | PIPING | 2544-37-DW-0051-01-01-B-CRS_1 | 30/09/16 | CLIENT COMMENTS TO UNIT 36TO38-41TO44-B.F.W.STEAM GENERAT.-CONDENSATE TREAT.P.AIR/I.AIR NITROGEN CAUSTIC-UNCONVERT | REF:T-1198/MIDOR-TPIT-T-00063
CRS | MIDOR | 37 | PIPING | 2544-37-DW-0051-01-01-B-CRS-REPLY_0 | 13/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 36TO38-41TO44-B.F.W.STEAM GENERAT.-CONDENSATE TREAT.P.AIR/I.AIR NITROGEN CAUSTIC- | REF.:TPIT-MIDOR-E-02088/MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-37-DW-0051-01-01-B-CRS_1 MIDOR-TPIT-T-00063 (CLOSED) | 30/09/16
CRS | MIDOR | 37 | PIPING | 2544-37-DW-0051-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 36 TO 38 - 41 TO 44 - DETAILED PLOT PLAN | REF.:T-1198/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 37 | HSE DESIGN | 2544-37-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 37TO38 - 41TO44 BLOCK U - ZONE U1ZA - FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-1959/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-001-03-B-CRS_0 | 25/05/16 | CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - STEAM GENERATION DEAERATOR 37-V-05-N | RE T-1760 -MIDOR-TPIT-E-2016-05-26_11-03 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01684/2544-37-PID-0021-001-03-B-CRS-REPLY_0 | 27/05/16
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-001-03-B-CRS_1 | 30/05/16 | CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - STEAM GENERATION DEAERATOR 37-V-05-N | RE 2544-37-PID-0021-001-03-B-CRS-REPLY_0
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-001-03-B-CRS-REPLY_0 | 27/05/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - STEAM GENERATION DEAERATOR 37-V-05-N | RE E-1684/2544-37-PID-0021-001-03-B-CRS | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-05-30_08-32/2544-37-PID-0021-001-03-B-CRS_1 | 30/05/16
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-A-CRS_0 | 24/03/16 | CLIENT COMMENTS TO UNIT 37 PIPING AND INSTRUMENT DIAGRAMS | REF. TPIT-MIDOR-T-01186 | TPIT RESPONSE REQUIRED |  | 2544-37-PID-0021-A-CRS-REPLY_0 TPIT-MIDOR-E-01685 | 01/04/16
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-A-CRS_1 | 09/04/16 | CLIENT COMMENTS TO UNIT 37 PIPING AND INSTRUMENT DIAGRAMS
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-A-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 37 - PIPING AND INSTRUMENT DIAGRAMS | REF:E-01685 /2544-37-PID-0021-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-37-PID-0021-A-CRS_1 | 09/04/16
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-B-CRS_0 | 10/06/16 | CLIENT COMMENTS TO UNIT 37 PIPING AND INSTRUMENT DIAGRAMS | REF.T-1760/PMC-MIDOR-E-0039
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0021-B-CRS-REPLY_0 | 01/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 37 PIPING AND INSTRUMENT DIAGRAMS | REF:E-1892/2544-37-PID-0021-B-CRS_0
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0031-A-CRS_0 | 24/03/16 | CLIENT COMMENTS TO UNIT 37 PIPING AND INSTRUMENT DIAGRAMS | REF. TPIT-MIDOR-T-01186 | TPIT RESPONSE REQUIRED |  | 2544-37-PID-0031-A-CRS-REPLY_0 TPIT-MIDOR-E-01685 | 01/04/16
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0031-A-CRS_1 | 09/04/16 | CLIENT COMMENTS TO UNIT 37 PIPING AND INSTRUMENT DIAGRAMS
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0031-A-CRS-REPLY_0 | 01/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 37 - PIPING AND INSTRUMENT DIAGRAMS | REF:E-01685 /2544-37-PID-0031-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-37-PID-0031-A-CRS_1 | 09/04/16
CRS | MIDOR | 37 | PROCESS | 2544-37-PID-0031-B-CRS_0 | 10/06/16 | CLIENT COMMENTS TO UNIT 37 PIPING AND INSTRUMENT DIAGRAMS | REF.T-1760/MIDOR-TPIT-E-2016-06-10_16-45
CRS | MIDOR | 37 | PACKAGES | 2544-37-SP-0845-01-PC-CRS_0 | 05/05/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR DEAERATORS AND DEGASSIFIERS - DEAERATOR - 37-V-05-N | REF:T-1604/MIDOR-TPIT-E-2016-05-05_14-35 | TPIT RESPONSE REQUIRED |  | 2544-37-SP-0845-01-PC-CRS-REPLY_0 TPIT-MIDOR-E-01687 | 27/05/16
CRS | MIDOR | 37 | PACKAGES | 2544-37-SP-0845-01-PC-CRS-REPLY_0 | 27/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 37 PROCESS DATA SHEET FOR DEAERATORS AND DEGASSIFIERS - DEAERATOR - 37-V-05-N | REF.E-01687/2544-05-SP-0845-01-PC-CRS_0
CRS | MIDOR | 38 | PROCESS | 2544-38-JSD-0001-01-A-CRS_0 | 28/07/16 | CLIENT COMMENTS TO UNIT 38 CONDENSATE COLLECTION AND TREATMENT DESIGN BASIS | REF:T-2338/MIDOR-TPIT-E-2016-07-31_09-18 | TPIT RESPONSE REQUIRED |  | 2544-38-JSD-0001-01-A-CRS-REPLY_0 TPIT-MIDOR-E-02065 | 10/08/16
CRS | MIDOR | 38 | PROCESS | 2544-38-JSD-0001-01-A-CRS-REPLY_0 | 10/08/16 | TPTI REPLY TO CLIENT COMMENTS TO UNIT 38 CONDENSATE COLLECTION AND TREATMENT DESIGN BASIS | REF.: E-02065/2544-38-JSD-0001-01-A-CRS
CRS | MIDOR | 38 | INSTRUMENTATION | 2544-38-NM-1511-01-B-CRS_0 | 27/03/16 | CLIENT COMMENTS TO IN/OUT LIST UNIT 38 | REF:T-1160/MIDOR-TPIT-E-2016-04-03_14-06
CRS | MIDOR | 38 | INSTRUMENTATION | 2544-38-NM-1511-01-B-CRS_1 | 06/02/17 | CLIENT COMMENTS TO IN/OUT LIST UNIT 38 | REF:T-1160/MIDOR-TPIT-T-00171 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 38 | INSTRUMENTATION | 2544-38-NM-1511-01-B-CRS-_2 | 16/02/17 | CLIENT COMMENTS TO IN/OUT LIST UNIT 38 | REF:T-1160/T-E-2650/MIDOR-TPIT-T-178
CRS | MIDOR | 38 | INSTRUMENTATION | 2544-38-NM-1511-01-B-CRS-REPLY_1 | 10/02/17 | TPIT REPL Y TO CLIENT COMMENTS TO IN/OUT LIST UNIT 38 | REF:T-1160/MIDOR-T-00171/T-E-02650
CRS | MIDOR | 38 | PROCESS | 2544-38-PID-0021-A-CRS_0 | 30/05/16 | CLIENT COMMENTS TO U-38 P&IDS | REF:T-00968/PMC-MIDOR-E-0029 | TPIT RESPONSE REQUIRED |  | 2544-38-PID-0021-A-CRS-REPLY_0 TPIT-MIDOR-E-01746 | 07/06/16
CRS | MIDOR | 38 | PROCESS | 2544-38-PID-0021-A-CRS_1 | 09/06/16 | CLIENT COMMENTS TO U-38 P&IDS | REF:T-00968/ PMC-MIDOR-E-0040
CRS | MIDOR | 38 | PROCESS | 2544-38-PID-0021-A-CRS-REPLY_0 | 07/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 38 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-00968 /2544-38-PID-0021-A-CRS_0
CRS | MIDOR | 38 | PROCESS | 2544-38-PID-0021-B-CRS_0 | 26/05/16 | CLIENT COMMENTS TO UNIT 38 - PIPING AND INSTRUMENT DIAGRAM | REF:T-1741/MIDOR-TPIT-E-2016-05-27_00-03
CRS | MIDOR | 39 | PROCESS | 2544-39-PID-0021-B-CRS_0 | 17/06/16 | CLIENT COMMENTS TO UNIT 39 PIPING AND INSTRUMENT DIAGRAM - FUEL GAS SYSTEM | REF:TPIT-MIDOR-T-01668/PMC-MIDOR-E-0063
CRS | MIDOR | 40 | PROCESS | 2544-40-PID-0021-B-CRS_0 | 17/06/16 | CLIENT COMMENTS TO UNIT 40 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-01669/PMC-MIDOR-E-0063
CRS | MIDOR | 40 | PROCESS | 2544-40-PID-0021-B-CRS_1 | 11/01/17 | CLIENT COMMENTS TO UNIT 40 PIPING AND INSTRUMENT DIAGRAMS | REF:T-01669/TPIT-E-2520/MIDOR-T-00156 | CLOSED |  | APPROVED | 11/01/17
CRS | MIDOR | 40 | PROCESS | 2544-40-PID-0021-B-CRS-REPLY_0 | 22/12/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 40 PIPING AND INSTRUMENT DIAGRAMS | REF:T-01669/PMC-E-0063/TPIT-E-02520 |  |  | 2544-40-PID-0021-B-CRS_1 - MIDOR-TPIT-T-00156 APPROVED/CLOSED | 11/01/17
CRS | MIDOR | 41 | PROCESS | 2544-41-MSD-0011-01-01-A-CRS_0 | 14/03/16 | CLIENT COMMENTS TO UNIT 41 - MATERIAL SELECTION DIAGRAMS | REF:T-1026/MIDOR-TPIT-E-2016-03-15_07-17
CRS | MIDOR | 41 | PROCESS | 2544-41-MSD-0011-01-02-A-CRS_0 | 14/03/16 | CLIENT COMMENTS TO UNIT 41 - MATERIAL SELECTION DIAGRAMS | REF:T-1026/MIDOR-TPIT-E-2016-03-15_07-17
CRS | MIDOR | 41 | PROCESS | 2544-41-MSD-0011-01-03-A-CRS_0 | 14/03/16 | CLIENT COMMENTS TO UNIT 41 - MATERIAL SELECTION DIAGRAMS | REF:T-1026/MIDOR-TPIT-E-2016-03-15_07-17
CRS | MIDOR | 41 | PROCESS | 2544-41-PID-0021-A-CRS-REPLY_0 | 05/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 41 - PID | REF: MIDOR-TPIT-E-2016-04-03_02-36
CRS | MIDOR | 41 | PROCESS | 2544-41-PID-0021-B-CRS_0 | 08/06/16 | CLIENT COMMENTS TO REVAMPED U-41 PIDS | REF:T-1418/MIDOR-TPIT-E-2016-06-10_16-45 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01909 2544-41-PID-0021-B-CRS-REPLY_0 | 07/07/16
CRS | MIDOR | 41 | PROCESS | 2544-41-PID-0021-B-CRS-REPLY_0 | 07/07/16 | TPIT REPLY TO CLIENT COMMENTS TO REVAMPED U-41 PIDS | REF:E-1909/2544-41-PID-0021-B-CRS_0
CRS | MIDOR | 42 | PROCESS | 2544-42-PFD-0010-02-01-A-CRS_0 | 04/08/16 | CLIENT COMMENTS TO PROCESS FLOW DIAGRAM UNIT 42 - NITROGEN SYSTEM | REF.T-2366\MIDOR-TPIT-E-2016-08-04_14-52
CRS | MIDOR | 42 | PROCESS | 2544-42-PID-0021-004-02-C-CRS_0 | 25/05/16 | CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - NITROGEN PRODUCTION UNIT 42-PK-02-N | REF.: TPIT-MIDOR-T-01782
CRS | MIDOR | 42 | PROCESS | 2544-42-PID-0021-B_CRS_0 | 15/05/16 | CLIENT COMMENTS TO UNIT 42 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-01670 | TPIT RESPONSE REQUIRED |  | 2544-42-PID-0021-B-CRS-REPLY_0 | 18/05/16
CRS | MIDOR | 42 | PROCESS | 2544-42-PID-0021-B_CRS_1 | 19/05/16 | CLIENT COMMENTS TO UNIT 42 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-01670
CRS | MIDOR | 42 | PROCESS | 2544-42-PID-0021-B-CRS-REPLY_0 | 18/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 42- PID |  | OWNER RESPONSE REQUIRED |  | 2544-42-PID-0021-B-CRS_1 | 19/05/16
CRS | MIDOR | 44 | PROCESS | 2544-44-PID-0021-A-CRS-REPLY_0 | 05/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 44 - PID | REF: MIDOR-TPIT-E-2016-04-03_02-36
CRS | MIDOR | 45 | PROCESS | 2544-45-MSD-0011-01-01-A-CRS_0 | 11/03/16 | CLIENT COMMENTS TO UNIT 45 - MATERIAL SELECTION DIAGRAMS | REF:T-1031/MIDOR-TPIT-E-2016-03-12_18-45
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-01-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I101 DETAILED PLOT PLAN | REF:T-1249/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-46-DW-0051-01-01-A-CRS-REPLY_0 TPIT-MIDOR-E-02089 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-01-01-A-CRS_1 | 30/09/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I101 DETAILED PLOT PLAN | REF:T-1249/MIDOR-TPIT-T-0063
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-01-01-A-CRS-REPLY_0 | 14/06/16 | TPIT CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I101 DETAILED PLOT PLAN | REF:T-1249/TPIT-MIDOR-E-02089/MOM-65 | OWNER RESPONSE REQUIRED |  | 2544-46-DW-0051-01-01-A-CRS_1 MIDOR-TPIT-T-00063 (CLOSED) | 30/09/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-01-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I101 DETAILED PLOT PLAN | REF.:T-1249/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-02-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I102 DETAILED PLOT PLAN | REF:T-1249/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-46-DW-0051-02-01-A-CRS-REPLY_0/TPIT-MIDOR-T-2089 | 13/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-02-01-A-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I102 DETAILED PLOT PLAN | REF:T-1249/MIDOR-TPIT-T-00047
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-02-01-A-CRS-REPLY_0 | 13/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I102 DETAILED PLOT PLAN | E-2089/MIDOR-TPIT-E-16-05-30_22-38/MOM65 |  |  | 2544-46-DW-0051-02-01-A-CRS_1/MIDOR-TPIT-T-00047 | 23/09/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-02-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I102 DETAILED PLOT PLAN | REF.:T-1249/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-03-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I102 DETAILED PLOT PLAN | REF:T-1181/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-46-DW-0051-03-01-A-CRS-REPLY_0/TPIT-MIDOR-E-2089 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-03-01-A-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I102 DETAILED PLOT PLAN | REF:T-1181/MIDOR-TPIT-T-00047
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-03-01-A-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I102 DETAILED PLOT PLAN | E-2089/MIDOR-TPIT-E-16-05-30_22-38/MOM65 |  |  | 2544-46-DW-0051-03-01-A-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-03-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I103 DETAILED PLOT PLAN | REF.:T-1181/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-01-A-CRS_0 | 08/03/16 | CLIENT COMMENTS TO UNIT 46 - DETAILED PLOT PLAN | REF:T-0858/MIDOR-TPIT-E-2016-03-08_22-00 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02115 / 2544-46-DW-0051-04-01-A-CRS-REPLY_0 | 12/09/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-01-A-CRS-REPLY_0 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - DETAILED PLOT PLAN | E-2115/46-DW-0051-04-01-A-CRS_0/MOM65
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-01-B-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS /UTILITIES INTERCONNECTING BLOCK I - ZONE I104 DETAILED PLOT PLAN | REF:T-1195/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-46-DW-0051-04-01-B-CRS-REPLY_0/TPIT-MIDOR-T-2089 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-01-B-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS /UTILITIES INTERCONNECTING BLOCK I - ZONE I104 DETAILED PLOT PLAN | REF:T-1195/MIDOR-TPIT-T-00047
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-01-B-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - PROCESS /UTILITIES INTERCONNECTING BLOCK I - ZONE I104 DETAILED PLOT PLAN | REF:E-2089/MIDOR-TPIT-E-2016-05-30_22-38 |  |  | 2544-46-DW-0051-04-01-B-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-01-C-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS /UTILITIES INTERCONNECTING BLOCK I - ZONE I104 DETAILED PLOT PLAN | REF.: TPIT-MIDOR-T-01781 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02115 / 2544-46-DW-0051-04-01-C-CRS-REPLY_0 | 12/09/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-01-C-CRS-REPLY_0 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - PROCESS /UTILITIES INTERCONNECTING BLOCK I - ZONE I104 DETAILED PLOT PLAN | REF:E-2115/2544-46-DW-0051-04-01-C-CRS_0
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-04-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I104 DETAILED PLOT PLAN | REF.:T-1195/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-05-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I105 DETAILED PLOT PLAN | REF:T-1181/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-46-DW-0051-05-01-A-CRS-REPLY_0/TPIT-MIDOR-T-2089 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-05-01-A-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I105 DETAILED PLOT PLAN | REF:T-1181/MIDOR-TPIT-T-00047
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-05-01-A-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I105 DETAILED PLOT PLAN | E-2089/MIDOR-TPIT-E-16-05-30_22-38/MOM65 |  |  | 2544-46-DW-0051-05-01-A-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-05-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I105 DETAILED PLOT PLAN | REF.:T-1181/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-06-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I106 DETAILED PLOT PLAN | REF:T-1181/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-46-DW-0051-06-01-A-CRS-REPLY_0/TPIT-MIDOR-T-2089 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-06-01-A-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I106 DETAILED PLOT PLAN | REF:T-1181/MIDOR-TPIT-T-00047
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-06-01-A-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I106 DETAILED PLOT PLAN | REF:E-2089/MIDOR-TPIT-E-2016-05-30_22-38 |  |  | 2544-46-DW-0051-06-01-A-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 46 | PIPING | 2544-46-DW-0051-06-A-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT46 - PROCESS-UTILITIES INTERCONNECTING BLOCK I - ZONE I106 DETAILED PLOT PLAN | REF.:T-1181/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 46 | INSTRUMENTATION | 2544-46-DW-1572-01-A-CRS_0 | 14/06/16 | CLIENT COMMENTS TO UNIT 46 - INSTRUMENT MAIN CABLE ROUTING | REF:T-2013/MIDOR-TPIT-E-2016-06-15_02-36
CRS | MIDOR | 46 | PROCESS | 2544-46-NM-0020-01-B-CRS_0 | 30/01/17 | CLIENT COMMENTS TO PROCESS INTERCONNECTING PIDS | REF.: MIDOR-TPIT-T-00168
CRS | MIDOR | 46 | PROCESS | 2544-46-NM-0020-01-B-CRS-REPLY_0 | 24/02/17 | TPIT REPLY TO CLIENT COMMENTS TO PROCESS INTERCONNECTING PIDS | REF.: T-2528/MIDOR-T-00168/TPIT-E-02700
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-001-02-B-CRS_0 | 30/05/16 | CLIENT COMMENTS TO UNIT 46 PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING (EPC CONTRACT) PROCESS INTERCONNECTING | REF:TPIT-MIDOR-T-1876/MIDOR-TPIT-T-00043 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-001-02-B-CRS_1 | 07/09/16 | CLIENT COMMENTS TO UNIT 46 PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING (EPC CONTRACT) PROCESS INTERCONNECTING | REF:TPIT-MIDOR-T-1876/MIDOR-TPIT-T-00062 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02155 / 2544-46-PID-0021-001-02-B-CRS-REPLY_0 | 22/09/16
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-001-02-B-CRS_2 | 13/10/16 | CLIENT COMMENTS TO UNIT 46 PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING (EPC CONTRACT) PROCESS INTERCONNECTING | REF:TPIT-MIDOR-T-1876/MIDOR-TPIT-T-00088 | TPIT RESPONSE REQUIRED |  | 2544-46-PID-0021-001-02-B-CRS-REPLY_1 TPIT-MIDOR-E-02237 | 07/10/16
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-001-02-B-CRS-REPLY_0 | 22/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 PID - INTERCONNECTING (EPC CONTRACT) PROCESS INTERCONNECTING | REF:2544-46-PID-0021-001-02-B-CRS_1 | OWNER RESPONSE REQUIRED |  | 2544-46-PID-0021-001-02-B-CRS_2 MIDOR-TPIT-T-00062 | 27/09/16
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-001-02-B-CRS-REPLY_1 | 07/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 PID - INTERCONNECTING (EPC CONTRACT) PROCESS INTERCONNECTING | REF:2544-46-PID-0021-001-02-B-CRS_1 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-001-02-B-CRS-REPLY_2 | 21/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 PID - INTERCONNECTING (EPC CONTRACT) PROCESS INTERCONNECTING | REF:2544-46-PID-0021-001-02-B-CRS_2 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-A-CRS_0 | 30/05/16 | CLIENT COMMENTS TO UNIT 46 PIPING AND INSTRUMENT DIAGRAMS | REF:TPIT-MIDOR-T-01813
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0021-A-CRS-REPLY_0 | 05/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46 - PID | REF: MIDOR-TPIT-E-2016-04-03_02-36
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-057-02-A-CRS_1 | 16/09/16 | CLIENT COMMENTS TO P&ID 057-02 UNIT 46 | REF:T-1742/MIDOR-TPIT-T-00049
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-059-01-A-CRS_1 | 16/09/16 | CLIENT COMMENTS TO P&ID 057-02 UNIT 46 | REF:T-1742/MIDOR-TPIT-T-00049
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-061-01-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO U 46 PIDS | REF:T-1028/PMC-MIDOR-E-0025
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-061-01-B-CRS_1 | 16/09/16 | CLIENT COMMENTS TO P&ID 061-01 UNIT 46 | REF:T-1742/MIDOR-TPIT-T-00050
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-068-01-A-CRS_0 | 27/05/16 | CLIENT COMMENTS TO U 46 PIDS | REF:T-1028/PMC-MIDOR-E-0025
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-06X-01-CRS_0 | 03/04/16 | CLIENT COMMENTS TO PIPING &INSTRUMENT DIAGRAM UNIT 46 | REF:T-01028
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-A-CRS_0 | 30/05/16 | CLIENT COMMENTS TO UNIT 46 PIPING AND INSTRUMENT DIAGRAMS UTILITIES INTERCONNECTING | REF:TPIT-MIDOR-T-01742
CRS | MIDOR | 46 | PROCESS | 2544-46-PID-0031-B-CRS_0 | 30/05/16 | CLIENT COMMENTS TO UNIT 46 PIPING AND INSTRUMENT DIAGRAMS UTILITIES INTERCONNECTING | REF:TPIT-MIDOR-T-01742
CRS | MIDOR | 46 | MACHINERY | 2544-46-SP-0910-01-PB-CRS_0 | 26/05/16 | CLIENT COMMENTS TO UNIT 46 | REF:T-1776/MIDOR-TPIT-E-2016-05-26_23-35
CRS | MIDOR | 47 | PIPING | 2544-47-DW-0051-01-01-B-CRS_0 | 13/05/16 | CLIENT COMMENTS TO UNIT 47 - NEW COOLING WATER - BLOCK U - ZONE U301 DETAILED PLOT PLAN | REF:T-1211/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-47-DW-0051-01-01-B-CRS-REPLY_0 TPIT-MIDOR-E-02088/MOM-0065 | 13/06/16
CRS | MIDOR | 47 | PIPING | 2544-47-DW-0051-01-01-B-CRS_1 | 27/09/16 | CLIENT COMMENTS TO UNIT 47 - NEW COOLING WATER - BLOCK U - ZONE U301 DETAILED PLOT PLAN | REF:T-1211/MIDOR-TPIT-T-00054
CRS | MIDOR | 47 | PIPING | 2544-47-DW-0051-01-01-B-CRS-REPLY_0 | 13/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47 - NEW COOLING WATER - BLOCK U - ZONE U301 DETAILED PLOT PLAN | REF.:TPIT-MIDOR-E-02088/MOM-0065 | OWNER RESPONSE REQUIRED |  | 2544-47-DW-0051-01-01-B-CRS_1 MIDOR-TPIT-T-00054 (CLOSED) | 27/09/16
CRS | MIDOR | 47 | PIPING | 2544-47-DW-0051-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT47 - NEW COOLING WATER - BLOCK U - ZONE U301 DETAILED PLOT PLAN | REF.:T-1211/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 47 | PROCESS | 2544-47-JSD-0001-01-A-CRS_0 | 19/07/16 | CLIENT COMMENTS TO UNIT 47 NEW COOLING WATER DESIGN BASIS | REF.T-2131\MIDOR-TPIT-E-2016-07-19_12-48
CRS | MIDOR | 47 | PROCESS | 2544-47-NM-0003-01-A-CRS_0 | 19/07/16 | CLIENT COMMENTS TO UNIT 47 UTILITIES CONSUMPTION SUMMARY NEW COOLING WATER SYSTEM | REF.T-2062\MIDOR-TPIT-E-2016-07-19_12-47
CRS | MIDOR | 47 | PROCESS | 2544-47-NM-0013-01-A-CRS_0 | 29/06/16 | CLIENT COMMENTS TO UNIT 47 - CAUSE AND EFFECT DIAGRAM | REF:T-2078/MIDOR-TPIT-E-2016-06-30_21-48
CRS | MIDOR | 47 | PROCESS | 2544-47-PFD-0010-01-01-A-CRS_0 | 19/07/16 | CLIENT COMMENTS TO UNIT47 - PROCESS FLOW DIAGRAMS | REF.T-2116\MIDOR-TPIT-E-2016-07-19_12-47
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-01-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 47- PID | REF: TPIT-MIDOR-T-00860 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01342/2544-47-PID-0021-002-01-A-CRS-REPLY_0 | 08/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-01-A-CRS_1 | 09/04/16 | CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-006-01-A-CRS-REPLY_0 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01342/2544-47-PID-0021-002-01-A-CRS-REPLY_1 | 19/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-01-A-CRS_2 | 26/04/16 | CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-002-01-A-CRS-REPLY_1
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-01-A-CRS-REPLY_0 | 08/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-002-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-11_06-27/2544-47-PID-0021-002-01-A-CRS_1 | 09/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-01-A-CRS-REPLY_1 | 19/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-002-01-A-CRS_1 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-27_06-07/2544-47-PID-0021-002-01-A-CRS_2 | 26/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-02-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 47- PID | REF: TPIT-MIDOR-T-00860 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01342/2544-47-PID-0021-002-02-A-CRS-REPLY_0 | 08/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-02-A-CRS_1 | 09/04/16 | CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-006-01-A-CRS-REPLY_0 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01342/2544-47-PID-0021-002-01-A-CRS-REPLY_1 | 19/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-02-A-CRS_2 | 26/04/16 | CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-002-02-A-CRS-REPLY_1
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-02-A-CRS-REPLY_0 | 08/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-002-02-A-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-11_06-27/2544-47-PID-0021-002-02-A-CRS_1 | 09/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-02-A-CRS-REPLY_1 | 19/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-002-02-A-CRS_1 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-27_06-07/2544-47-PID-0021-002-02-A-CRS_2 | 26/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-002-02-A-CRS-REPLY_2 | 30/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-002-02-A-CRS_1 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-006-01-A-CRS_0 | 03/03/16 | CLIENT COMMENTS TO UNIT 47- PID | REF: TPIT-MIDOR-T-00860 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01342/2544-47-PID-0021-006-01-A-CRS-REPLY_0 | 08/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-006-01-A-CRS_1 | 09/04/16 | CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-006-01-A-CRS-REPLY_0 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01342/2544-47-PID-0021-002-01-A-CRS-REPLY_1 | 19/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-006-01-A-CRS_2 | 26/04/16 | CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-006-01-A-CRS-REPLY_1
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-006-01-A-CRS-REPLY_0 | 08/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-006-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-11_06-27/2544-47-PID-0021-006-01-A-CRS_1 | 09/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-006-01-A-CRS-REPLY_1 | 19/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47- PID | RE 2544-47-PID-0021-006-01-A-CRS_1 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-27_06-07/2544-47-PID-0021-006-01-A-CRS_2 | 26/04/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO NEW COOLING WATER U-47 P&IDS | REF:T-1828/PMC-MIDOR-E-0041 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02194/2544-47-PID-0021-B-CRS-REPLY_0 | 30/09/16
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0021-B-CRS-REPLY_0 | 30/06/16 | TPIT REPLY TO CLIENT COMMENTS TO NEW COOLING WATER U-47 P&IDS | REF: E-2194/2544-47-PID-0021-B-CRS_0
CRS | MIDOR | 47 | PROCESS | 2544-47-PID-0031-B-CRS_0 | 09/06/16 | CLIENT COMMENTS TO NEW COOLING WATER U-47 P&IDS | REF:T-1828/PMC-MIDOR-E-0041
CRS | MIDOR | 47 | HSE DESIGN | 2544-47-PID-1931-001-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - UNIT 47 - NEW WATER COOLING FIRE WATER NETWORK | REF:T-1715/MIDOR-TPIT-E-2016-05-26_10-59
CRS | MIDOR | 47 | PACKAGES | 2544-47-SP-0310-01-B-CRS_0 | 13/06/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0310-201 | REF:T-1888/MIDOR-TPIT-E-2016-06-13_13-06
CRS | MIDOR | 47 | PACKAGES | 2544-47-SP-0310-01-PB-CRS_0 | 01/06/16 | CLIENT COMMENTS TO UNIT 47 - 47PK01 PROCESS DATA SHEET | REF:T-1709/MIDOR-TPIT-E-2016-06-02_08-37
CRS | MIDOR | 47 | MACHINERY | 2544-47-SP-0910-01-PB-CRS_0 | 19/05/16 | CLIENT COMMENTS TO UNIT 47 DATA SHEET FOR CW CIRCULATION PUMPS - 47-P-01 A/B/C/D | REF:TPIT-MIDOR-T-01711
CRS | MIDOR | 47 | MACHINERY | 2544-47-SP-0910-01-PB-CRS_1 | 30/05/16 | CLIENT COMMENTS TO UNIT 47 DATA SHEET FOR CW CIRCULATION PUMPS - 47-P-01 A/B/C/D | REF:T-1711/MIDOR-TPIT-E-2016-05-30_21-31
CRS | MIDOR | 47 | MACHINERY | 2544-47-SP-0910-02-A-CRS_0 | 30/05/16 | CLIENT COMMENTS TO UNIT 47P02 DATA SHEET | REF:T-1120/MIDOR-TPIT-E-2016-05-31_13-03
CRS | MIDOR | 47 | MACHINERY | 2544-47-SP-0910-02-A-CRS_1 | 27/07/17 | CLIENT COMMENTS TO DATA SHEET FOR CENTRIFUGAL PUMP 47-P-02 | REF: T-01120/MDR-TPIT-T-00373 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 47 | MACHINERY | 2544-47-SP-0910-02-A-CRS_2 | 18/08/17 | CLIENT COMMENTS TO DATA SHEET FOR CENTRIFUGAL PUMP 47-P-02 | REF: T-01120/MDR-TPIT-T-00378 | CLOSED |  | DATA SHEET APPROVED/CLOSED
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-01-01-A-CRS_0 | 02/03/16 | CLIENT COMMENTS TO UNIT 48 - CONTROL BUILDING LAYOUT | REF:T-0792/MIDOR-TPIT-E-2016-03-14_19-10
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-01-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-1 | REF:T-02142/ MIDOR-TPIT-T-00011 | TPIT RESPONSE REQUIRED |  | 2544-48-DW-1523-01-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02159 | 13/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-01-01-B-CRS-REPLY_0 | 13/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-1 | REF E-2159/2544-48-DW-1523-01-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-48-DW-1523-B-CRS_1 MIDOR-TPIT-T-00071 | 30/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-02-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SATELLITE INSTRUMENT BUILDING LAYOUT CR02 | REF:T-0723/MIDOR-TPIT-E-2016-04-02_11-01
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-02-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-2 | REF:T-02142/ MIDOR-TPIT-T-00011 | TPIT RESPONSE REQUIRED |  | 2544-48-DW-1523-02-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02159 | 13/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-02-01-B-CRS-REPLY_0 | 13/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-2 | REF:E-2159/2544-48-DW-1523-02-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-48-DW-1523-B-CRS_1 MIDOR-TPIT-T-00071 | 30/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-04-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SATELLITE INSTRUMENT BUILDING LAYOUT CR04 | REF:T-0587/MIDOR-TPIT-E-2016-04-02_10-39
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-05-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SATELLITE INSTRUMENT BUILDING LAYOUT CR05 | REF:T-0587/MIDOR-TPIT-E-2016-04-02_10-39
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-05-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-5 | REF:T-02142/ MIDOR-TPIT-T-00011 | TPIT RESPONSE REQUIRED |  | 2544-48-DW-1523-05-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02159 | 13/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-05-01-B-CRS-REPLY_0 | 13/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-5 | REF:E-2159/2544-48-DW-1523-05-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-48-DW-1523-B-CRS_1 MIDOR-TPIT-T-00071 | 30/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-06-01-A-CRS_0 | 01/04/16 | CLIENT COMMENTS TO UNIT48 SATELLITE INSTRUMENT BUILDING LAYOUT CR06 | REF:T-0647/MIDOR-TPIT-E-2016-04-11_06-27
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-06-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-6 | REF:T-02142/ MIDOR-TPIT-T-00011 | TPIT RESPONSE REQUIRED |  | 2544-48-DW-1523-06-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02159 | 13/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-06-01-B-CRS-REPLY_0 | 13/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-6 | REF:E-2159/2544-48-DW-1523-06-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-48-DW-1523-B-CRS_1 MIDOR-TPIT-T-00071 | 30/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-07-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SATELLITE INSTRUMENT BUILDING LAYOUT CR07 | REF:T-0741/MIDOR-TPIT-E-2016-04-02_11-01
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-07-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-7 | REF:T-02142/ MIDOR-TPIT-T-00011 | TPIT RESPONSE REQUIRED |  | 2544-48-DW-1523-07-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02159 | 13/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-07-01-B-CRS-REPLY_0 | 13/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-7 | REF:E-2159/2544-48-DW-1523-07-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-48-DW-1523-B-CRS_1 MIDOR-TPIT-T-00071 | 30/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-09-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-9 | REF:T-02142/ MIDOR-TPIT-T-00011 | TPIT RESPONSE REQUIRED |  | 2544-48-DW-1523-09-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02159 | 13/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-09-01-B-CRS-REPLY_0 | 13/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-9 | REF E-2159/2544-48-DW-1523-09-01-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-48-DW-1523-B-CRS_1 MIDOR-TPIT-T-00071 | 30/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-10-01-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO SATELLITE INSTRUMENT BUILDING LAYOUT CR10 | REF:T-0426//MIDOR-TPIT-E-16-03-29_14-36
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-10-01-B-CRS_0 | 31/08/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-10 | REF:T-02142/ MIDOR-TPIT-T-00011 | TPIT RESPONSE REQUIRED |  | 2544-48-DW-1523-10-01-B-CRS-REPLY_0/TPIT-MIDOR-E-02159 | 13/09/16
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-10-01-B-CRS-REPLY_0 | 13/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-10 | REF:E-2159/2544-48-DW-1523-10-01-B-CRS_0
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-11-01-A-CRS_0 | 29/03/16 | CLIENT COMMENTS TO SATELLITE INSTRUMENT BUILDING LAYOUT - CR-11 | REF:T-1177/MIDOR-TPIT-E-2016-03-30_06-11
CRS | MIDOR | 48 | INSTRUMENTATION | 2544-48-DW-1523-B-CRS_1 | 30/09/16 | CLIENT COMMENTS TO UNIT 48 CENTRAL CONTROL BUILDING LAYOUT - CR-1 | REF:T-02142/ MIDOR-TPIT-T-00071 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-01-01-A-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNIT 49 - SUBSTATION LAYOUTS | REF:T-0937/MIDOR-TPIT-E-2016-03-10_08-13 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01148/2544-49-DW-1625-01-01-A-CRS-REPLY_0 | 18/03/16
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-01-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 49 - SUBSTATION LAYOUTS | REF:T-00937/TPIT-E-1148/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-01-01-A-CRS-REPLY_0 | 18/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 49 - SUBSTATION LAYOUTS | REF:2544-49-DW-1625-01-01-A-CRS_0/E-1148
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-02-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-2 | REF:T-0984/MIDOR-TPIT-E-2016-03-19_07-03 | TPIT RESPONSE REQUIRED |  | 2544-49-DW-1625-02-01-A-CRS-REPLY_0 TPIT-MIDOR-E-02200 | 03/10/16
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-02-01-A-CRS-REPLY_0 | 03/10/16 | TPIT REPLY TO CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-2 | REF:T-0984/TPIT-MIDOR-E-02200
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-03-01-A-CRS_0 | 10/03/16 | CLIENT COMMENTS TO UNIT 49 - SUBSTATION LAYOUTS | REF:T-0937/MIDOR-TPIT-E-2016-03-10_08-13 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01148/2544-49-DW-1625-03-01-A-CRS-REPLY_0 | 18/03/16
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-03-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-2 | REF:T-0984/TPIT-E-02200/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-03-01-A-CRS-REPLY_0 | 18/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 49 - SUBSTATION LAYOUTS | REF:2544-49-DW-1625-03-01-A-CRS_0/E-1148
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-04-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-4 | REF:T-0984/MIDOR-TPIT-E-2016-03-19_07-03
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-05-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-5 | REF:T-0984/MIDOR-TPIT-E-2016-03-19_07-03
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-06-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-6 | REF:T-0984/MIDOR-TPIT-E-2016-03-19_07-03
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-07-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-7 | REF:T-0984/MIDOR-TPIT-E-2016-03-19_07-03
CRS | MIDOR | 49 | ELECTRICAL | 2544-49-DW-1625-08-01-A-CRS_0 | 17/03/16 | CLIENT COMMENTS TO SUBSTATION EQUIPMENT LAYOUT SS-8 | REF:T-0984/MIDOR-TPIT-E-2016-03-19_07-03
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-04-01-A-CRS_0 | 21/04/16 | CLIENT COMMENTS TO UNIT 51 - KEROSENE STORAGE SYSTEM - BLOCK A - ZONE A102 - DETAILED PLOT PLAN | REF: TPIT-MIDOR-T-01375
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-06-01-A-CRS_0 | 21/04/16 | CLIENT COMMENTS TO UNIT 51 - KEROSENE STORAGE SYSTEM - BLOCK A - ZONE A106 - DETAILED PLOT PLAN | REF: TPIT-MIDOR-T-01375
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-08-01-A-CRS_0 | 21/04/16 | CLIENT COMMENTS TO UNIT 51 - KEROSENE STORAGE SYSTEM - BLOCK A - ZONE A108 - DETAILED PLOT PLAN | REF: TPIT-MIDOR-T-01375
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-28-01-A-CRS_0 | 15/04/16 | CLIENT COMMENTS TO UNIT UNIT 51- NEW INTERMEDIATE STORAGE TANKS PLOT PLAN | REF:T-1387/MIDOR-TPIT-E-2016-04-17_14-29 | TPIT RESPONSE REQUIRED |  | 2544-51-DW-0051-28-01-A-CRS-REPLY_0 | 18/04/16
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-28-01-A-CRS_1 | 13/05/16 | CLIENT COMMENTS TO UNIT 51 - NEW INTERMEDIATE STORAGE BLOCK A - ZONE A201 - DETAILED PLOT PLAN | REF:T-1387/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02091 / 2544-51-DW-0051-28-01-A-CRS-REPLY_0 | 09/09/16
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-28-01-A-CRS-REPLY_0 | 18/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 51 - NEW INTERMEDIATE STORAGE BLOCK A - ZONE A201 - DETAILED PLOT PLAN | REF:E-2091/2544-51-DW-0051-28-01-A-CRS_1
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-28-01-B-CRS_0 | 25/05/16 | CLIENT COMMENTS TO UNIT 51- NEW INTERMEDIATE STORAGE TANKS PLOT PLAN | REF:T-1720/MIDOR-TPIT-E-2016-05-26_11-06 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02091 / 2544-51-DW-0051-28-01-B-CRS-REPLY_0 | 29/05/16
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-28-01-B-CRS_2 | 26/09/16 | CLIENT COMMENTS TO UNIT 51 - NEW INTERMEDIATE STORAGE BLOCK A - ZONE A201 - DETAILED PLOT PLAN | REF:T-1387/MIDOR-TPIT-T-00051
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-28-01-B-CRS-REPLY_0 | 29/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 51- NEW INTERMEDIATE STORAGE TANKS PLOT PLAN | REF:E-2091/2544-51-DW-0051-28-01-B-CRS_0
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-28-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 51 - NEW INTERMEDIATE STORAGE BLOCK A - ZONE A201 - DETAILED PLOT PLAN | REF.:T-1720/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-A-CRS_0 | 13/05/16 | CLIENT COMMENTS TO UNIT 51 DETAILED PLOT PLAN | REF:T-857-1277/MIDOR-E-2016-05-30_22-38
CRS | MIDOR | 51 | PIPING | 2544-51-DW-0051-B-CRS_0 | 13/05/16 | CLIENT COMMENTS TO UNIT 51 DETAILED PLOT PLAN | REF:T-1277/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-01-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:T-0880/MIDOR-TPIT-E-2016-03-15_22-14 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01212 2544-51-DW-1622-01-01-A-CRS-REPLY_0 | 23/03/16
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:T-00880/E-1212/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-01-A-CRS-REPLY_0 | 23/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:E-1212/2544-51-DW-1622-01-01-A-CRS_0
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-02-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:T-0880/MIDOR-TPIT-E-2016-03-15_22-14 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01212 2544-51-DW-1622-01-02-A-CRS-REPLY_0 | 23/03/16
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-02-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:T-00880/E-1212/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-02-A-CRS-REPLY_0 | 23/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:E-1212/2544-51-DW-1622-01-02-A-CRS_0
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-03-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:T-0880/MIDOR-TPIT-E-2016-03-15_22-14 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01212 2544-51-DW-1622-01-03-A-CRS-REPLY_0 | 23/03/16
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-03-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:T-00880/E-1212/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 51 | ELECTRICAL | 2544-51-DW-1622-01-03-A-CRS-REPLY_0 | 23/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 51 - ELECTRICAL CABLE ROUTING | REF:E-1212/2544-51-DW-1622-01-03-A-CRS_0
CRS | MIDOR | 51 | HSE DESIGN | 2544-51-DW-1950-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 56 - SULPHUR SOLIDIFICATION LOCATION OF FIRE AND GAS DETECTION | REF: TPIT-MIDOR-T-2275/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 51 | PVHE | 2544-51-DW-2520-01-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL DATA SHEET FOR UF CRUDE TANKS - ITEM 51-TK-45/46 | REF: TPIT-MIDOR-00413/TPIT-MIDOR-E-01523
CRS | MIDOR | 51 | PVHE | 2544-51-DW-2520-02-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL DATA SHEET FOR KHT FEED TANKS - ITEM 51-TK-44 | REF: TPIT-MIDOR-00413/TPIT-MIDOR-E-01523
CRS | MIDOR | 51 | PVHE | 2544-51-DW-2520-03-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL DATA SHEET FOR 2ND STAGE HC FEED TANK - ITEM 51-TK-47 | REF: TPIT-MIDOR-00413/TPIT-MIDOR-E-01523
CRS | MIDOR | 51 | PVHE | 2544-51-DW-2520-04-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MECHANICAL DATA SHEET FOR LOW FLASH DRY SLOPS - ITEM 51-TK-48 | REF: TPIT-MIDOR-00413/TPIT-MIDOR-E-01523
CRS | MIDOR | 51 | PROCESS | 2544-51-PFD-0010-01-01-A-CRS_0 | 04/08/16 | CLIENT COMMENTS TO PROCESS FLOW DIAGRAM STORAGE SYSTEM CRUDE OIL & INTERMEDIATE STORAGE | REF.T-2368\MIDOR-TPIT-E-2016-08-04_14-52
CRS | MIDOR | 51 | PROCESS | 2544-51-PFD-0010-01-03-A-CRS_0 | 04/08/16 | CLIENT COMMENTS TO PROCESS FLOW DIAGRAM STORAGE SYSTEM INTERMEDIATE STORAGE | REF.T-2368\MIDOR-TPIT-E-2016-08-04_14-52
CRS | MIDOR | 51 | PROCESS | 2544-51-PFD-0010-06-01-A-CRS_0 | 04/08/16 | CLIENT COMMENTS TO PROCESS FLOW DIAGRAM STORAGE SYSTEM INTERMEDIATE STORAGE FUEL OIL BLENDING | REF.T-2368\MIDOR-TPIT-E-2016-08-04_14-52
CRS | MIDOR | 51 | PROCESS | 2544-51-PID-0021-A-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 51 - PIPING AND INSTRUMENT DIAGRAMS | REF:920/921/1100/TPIT-E-2016-05-26_23-49
CRS | MIDOR | 51 | PROCESS | 2544-51-PID-0021-B-CRS_0 | 15/06/16 | CLIENT COMMENTS TO UNIT 51 PIPING AND INSTRUMENT DIAGRAM - | REF:TPIT-MIDOR-T-01851/PMC-MIDOR-E-0063
CRS | MIDOR | 51 | PROCESS | 2544-51-PID-0031-A-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 51 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-0922/MIDOR-TPIT-E-2016-05-26_23-49
CRS | MIDOR | 51 | MACHINERY | 2544-51-SP-0910-01-PB-CRS_0 | 28/04/16 | CLIENT COMMENTS TO DATA SHEET FOR CENTRIFUGAL PUMP DATA SHEET - SDA SOLVENT PUMPS 51-P-46 A/B | REF.: TPIT-MIDOR-T-01500 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01515 2544-51-SP-0910-01-PB-CRS-REPLY_0 | 04/05/16
CRS | MIDOR | 51 | MACHINERY | 2544-51-SP-0910-01-PB-CRS_1 | 02/05/16 | CLIENT COMMENTS TO DATA SHEET FOR CENTRIFUGAL PUMP DATA SHEET - SDA SOLVENT PUMPS 51-P-46 A/B | REF.:T1500\MIDOR-TPIT-E-2016-05-04_06-20
CRS | MIDOR | 51 | MACHINERY | 2544-51-SP-0910-01-PB-CRS-REPLY_0 | 04/05/16 | TPIT REPLY TO CLIENT COMMENTS TO PROCESS CENTRIFUGAL PUMP DATA SHEET - SDA SOLVENT PUMPS 51-P-46 A/B | REF: T-01500/2544-51-SP-0910-01-PB-CRS_0
CRS | MIDOR | 51 | MACHINERY | 2544-51-SP-0910-05-PB-CRS_0 | 08/06/16 | CLIENT COMMENTS TO NHT FEED PUMPS FOR 51-P-17A/B-R | REF:T-1915/MIDOR-TPIT-E-2016-06-08_13-26
CRS | MIDOR | 51 | PROCESS | 2544-51-SP-1120-01-PA-CRS_0 | 07/04/16 | CLIENT COMMENTS TO UNIT 51 STEAM TURBINE STEAM TURBINE - | REF:T-1225/MIDOR-TPIT-E-2016-04-08_11-21
CRS | MIDOR | 51 | PACKAGES | 2544-51-SP-4261-02-PA-CRS_0 | 25/05/16 | CLIENT COMMENTS TO UNIT 51 DATA SHEET FOR AGITATORS - LOW FLASH DRY SLOPE TANK 51TK48-N - ITEM 51-MX-48 A/B-N | REF:T-1777/MIDOR-TPIT-E-2016-05-26_23-38
CRS | MIDOR | 51 | PACKAGES | 2544-51-SP-4261-03-PA-CRS_0 | 25/05/16 | CLIENT COMMENTS TO UNIT 51 DATA SHEET FOR AGITATORS - KEROSENE PRODUCT TANK - 51-MX-19 A/B | REF:T-1774/MIDOR-TPIT-E-2016-05-26_23-37
CRS | MIDOR | 52 | PIPING | 2544-52-DW-0051-03-01-B-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 52 - LOADING SYSTEM BLOCK D - ZONE D103 DETAILED PLOT PLAN | REF:T-1412/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-52-DW-0051-03-01-B-CRS-REPLY_0/TPIT-MIDOR-T-2089 | 14/06/16
CRS | MIDOR | 52 | PIPING | 2544-52-DW-0051-03-01-B-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 52 - LOADING SYSTEM BLOCK D - ZONE D103 DETAILED PLOT PLAN | REF:T-1412/MIDOR-TPIT-T-00047
CRS | MIDOR | 52 | PIPING | 2544-52-DW-0051-03-01-B-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 52 - LOADING SYSTEM BLOCK D - ZONE D103 DETAILED PLOT PLAN | REF:E-2089/MIDOR-TPIT-E-2016-05-30_22-38 |  |  | 2544-52-DW-0051-03-01-B-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 52 | PIPING | 2544-52-DW-0051-03-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 52 - LOADING SYSTEM BLOCK D - ZONE D103 DETAILED PLOT PLAN | REF.:T-1412/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 53 | PIPING | 2544-53-DW-0051-05-01-B-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 53 - NEW FLARE BLOCK C - ZONE C301 DETAILED PLOT PLAN | REF:T-1373/MIDOR-TPIT-E-2016-05-30_22-38 | TPIT RESPONSE REQUIRED |  | 2544-53-DW-0051-05-01-B-CRS-REPLY_0 TPIT-MIDOR-E-02088/MOM-0065 | 17/07/16
CRS | MIDOR | 53 | PIPING | 2544-53-DW-0051-05-01-B-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 53 - NEW FLARE BLOCK C - ZONE C301 DETAILED PLOT PLAN | REF:T-1373/MIDOR-TPIT-T-00047
CRS | MIDOR | 53 | PIPING | 2544-53-DW-0051-05-01-B-CRS-REPLY_0 | 17/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - NEW FLARE BLOCK C - ZONE C301 DETAILED PLOT PLAN | REF.:TPIT-MIDOR-E-02088/MOM-0065 |  |  | 2544-53-DW-0051-05-01-B-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 53 | HSE DESIGN | 2544-53-DW-1933-01-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 53 - NEW FLARE BLOCK C - ZONE C301 FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-2029/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | HSE DESIGN | 2544-53-DW-1933-02-01-A-CRS_0 | 29/08/16 | CLIENT COMMENTS TO UNIT 53 - NEW FLARE BLOCK C - ZONE C106 FIREFIGHTING LAYOUT | REF: TPIT-MIDOR-T-2040/MIDOR-TPIT-T-0010 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-01-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:TPIT-MIDOR-T-01033
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-02-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:TPIT-MIDOR-T-01033
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-03-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:TPIT-MIDOR-T-01033 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01522 2544-53-MSD-0011-01-03-A-CRS-REPLY_0 | 05/05/16
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-03-A-CRS_1 | 15/05/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:1033/MIDOR-TPIT-E-2016-05-16_18-39
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-03-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAMS UNIT 53 - FLARE SYSTEM | REF: T-01033/2544-53-MSD-0011-03-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-53-MSD-0011-01-03-A-CRS_1 MIDOR-TPIT-E-2016-05-16_18-39 | 15/05/16
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-04-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:TPIT-MIDOR-T-01033 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01522 2544-53-MSD-0011-01-04-A-CRS-REPLY_0 | 05/05/16
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-04-A-CRS_1 | 15/05/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:1033/MIDOR-TPIT-E-2016-05-16_18-39
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-04-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAMS UNIT 53 - FLARE SYSTEM | REF: T-01033/2544-53-MSD-0011-04-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-53-MSD-0011-01-04-A-CRS_1 MIDOR-TPIT-E-2016-05-16_18-39 | 15/05/16
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-05-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:TPIT-MIDOR-T-01033 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01522 2544-53-MSD-0011-01-05-A-CRS-REPLY_0 | 05/05/16
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-05-A-CRS_1 | 15/05/16 | CLIENT COMMENTS TO UNIT 53 - MATERIAL SELECTION DIAGRAMS | REF.:1033/MIDOR-TPIT-E-2016-05-16_18-39
CRS | MIDOR | 53 | PROCESS | 2544-53-MSD-0011-01-05-A-CRS-REPLY_0 | 05/05/16 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL SELECTION DIAGRAMS UNIT 53 - FLARE SYSTEM | REF: T-01033/2544-53-MSD-0011-05-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-53-MSD-0011-01-05-A-CRS_1 MIDOR-TPIT-E-2016-05-16_18-39 | 15/05/16
CRS | MIDOR | 53 | PIPING | 2544-53-NM-1350-01-A-CRS_0 | 30/08/16 | CLIENT COMMENTS TO UNIT 53 - MECHANICAL TIE-IN LIST | REF: TPIT-MIDOR-T-1146/MIDOR-TPIT-T-0008 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02112 / 2544-53-NM-1350-01-A-CRS-REPLY_0 | 12/09/16
CRS | MIDOR | 53 | PIPING | 2544-53-NM-1350-01-A-CRS_1 | 04/10/16 | CLIENT COMMENTS TO UNIT 53 - MECHANICAL TIE-IN LIST | REF: TPIT-MIDOR-T-1146/MIDOR-TPIT-T-0069
CRS | MIDOR | 53 | PIPING | 2544-53-NM-1350-01-A-CRS-REPLY_0 | 12/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - MECHANICAL TIE-IN LIST | REF:E-2112/2544-53-NM-1350-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-53-NM-1350-01-A-CRS_1 MIDOR-TPIT-T-00069 (CLOSED) | 04/10/16
CRS | MIDOR | 53 | INSTRUMENTATION | 2544-53-NM-1511-01-A-CRS_0 | 27/03/16 | CLIENT COMMENTS TO UNIT 53 IO LIST | REF.:01165/MIDOR-TPIT-E-2016-04-03_14-50
CRS | MIDOR | 53 | PROCESS | 2544-53-PFD-0010-01-02-A-CRS_0 | 02/06/16 | CLIENT COMMENTS TO U 53 - PROCESS FLOW DIAGRAMS | REF:T-1788/MIDOR-TPIT-E-2016-06-03_13-28 | TPIT RESPONSE REQUIRED |  | 2544-53-PFD-0010-01-02-A-CRS-REPLY_0 TPIT-MIDOR-E-01753 | 08/06/16
CRS | MIDOR | 53 | PROCESS | 2544-53-PFD-0010-01-02-A-CRS-REPLY_0 | 08/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - PROCESS FLOW DIAGRAMS | REF:T-01788/2544-53-PFD-0010-01-02-A-CR
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-001-01-A-CRS_1 | 25/10/16 | CLIENT COMMENTS TO UNIT 53 - PIPING AND INSTRUMENT DIAGRAM FLARE H2S FLARE HP FLARE MAIN HEADER AND KO DRUM (53-V-01) | REF:T-01845/MIDOR-TPIT-T-00110 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-001-01-A-CRS_2 | 22/11/16 | CLIENT COMMENTS TO UNIT 53 - PIPING AND INSTRUMENT DIAGRAM FLARE H2S FLARE HP FLARE MAIN HEADER AND KO DRUM (53-V-01) | REF:T-01845/MIDOR-TPIT-T-00131 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-001-01-A-CRS_3 | 12/12/16 | CLIENT COMMENTS TO UNIT 53 - PIPING AND INST DIAGRAM FLARE H2S / HP / MAIN HEADER AND KO DRUM (53-V-01) | REF:T-01845/E-2453/MIDOR-T-00147 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-001-01-A-CRS-REPLY_0 | 20/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - PIPING AND INSTRUMENT DIAGRAMS | REF: TPIT-MIDOR-T-01845
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-001-01-A-CRS-REPLY_1 | 18/11/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-01845/MIDOR-T-131/TPIT-E-2437
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-001-01-A-CRS-REPLY_2 | 25/11/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - PID FLARE H2S FLARE HP FLARE MAIN HEADER AND KO DRUM (53-V-01) | REF:T-01845/MIDOR-TPIT-T-00131/E-2453 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-005-01-A-CRS_1 | 30/05/16 | CLIENT COMMENTS TO UNIT 53 - PIPING AND INSTRUMENT DIAGRAM FLARE H2S FLARE HP FLARE MAIN HEADER AND KO DRUM (53-V-01) | REF:T-1155/PMC-MIDOR-E-0027/0031 | TPIT RESPONSE REQUIRED |  | 2544-53-PID-0021-05-01-A-CRS-REPLY-1 TPIT-MIDOR-E-01722 | 31/05/15
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-005-01-A-CRS-REPLY-1 | 31/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 53 - PIPING AND INSTRUMENT DIAGRAM FLARE H2S FLARE HP FLARE MAIN HEADER AND KO DRU | REF: T-01155/PMC-MIDOR-E-0027
CRS | MIDOR | 53 | PROCESS | 2544-53-PID-0021-A-CRS_0 | 19/03/16 | CLIENT COMMENTS TO UNIT 53 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-1845/MIDOR-TPIT-E-2016-11-18_09-29 |  |  |  | 20/10/16
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PA-CRS_1 | 11/08/16 | CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-00898/MIDOR-TPIT-00001 | TPIT RESPONSE REQUIRED |  | 2544-53-SP-0910-05-PA-CRS-REPLY_0 TPIT-MIDOR-E-02228 | 04/10/16
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PA-CRS_2 | 13/10/16 | CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-00898/E-02228/MIDOR-TPIT-00088 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PA-CRS_3 | 25/10/16 | CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-00898/E-2322/MIDOR-TPIT-00111 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PA-CRS_4 | 22/11/16 | CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-00898/E-2399/MIDOR-TPIT-00130 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PA-CRS-REPLY_1 | 04/10/16 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-00898/TPIT-MIDOR-E-02228
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PA-CRS-REPLY_2 | 13/10/16 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: MIDOR-TPIT-T088/TPIT-MIDOR-E-02322
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PA-CRS-REPLY_3 | 10/11/16 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-898/MIDOR-T-00111/TPIT-E-2399 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PB-CRS_0 | 16/11/16 | CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-2507/MIDOR-T-00128 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PB-CRS_1 | 21/12/16 | CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-2507/TPIT-E-2507/MIDOR-T-00151 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-05-PB-CRS-REPLY_0 | 16/12/16 | TPIT REPLY TO CLIENT COMMENTS TO DATA SHEET 53-P-05 A-B | REF: T-2507/TPIT-E-2507 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-06-PA-CRS_0 | 15/06/16 | CLIENT COMMENTS TO NEW HC KO DRUM PUMPS FOR 53-P-06 A/B | REF:T-2003/MIDOR-TPIT-E-2016-06-15_12-58
CRS | MIDOR | 53 | MACHINERY | 2544-53-SP-0910-07-PA-CRS_0 | 15/06/16 | CLIENT COMMENTS TO NEW HC KO DRUM PUMPS FOR 53-P-06 A/B | REF:T-2003/MIDOR-TPIT-E-2016-06-15_12-58
CRS | MIDOR | 54 | PIPING | 2544-54-DW-0051-01-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 54 - WASTE WATER TREATMENT BLOCK C - ZONES C107 - C201 DETAILED PLOT PLAN | REF:T-0847/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 54 | PIPING | 2544-54-DW-0051-02-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 54 - WASTE WATER TREATMENT BLOCK C - ZONE C108 DETAILED PLOT PLAN | REF:T-0847/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 54 | PIPING | 2544-54-DW-0051-03-01-A-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 54 - WASTE WATER TREATMENT BLOCK C - ZONE C109 DETAILED PLOT PLAN | REF:T-0847/MIDOR-TPIT-E-2016-05-30_22-38
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-01-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:T-0907/MIDOR-TPIT-E-2016-03-15_22-25 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01211 2544-54-DW-1622-01-01-A-CRS-REPLY_0 | 24/03/16
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-01-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:T-00907/E-1210/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-01-A-CRS-REPLY_0 | 24/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:E-1210/2544-54-DW-1622-01-01-A-CRS_0
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-02-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:T-0907/MIDOR-TPIT-E-2016-03-15_22-25 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01211 2544-54-DW-1622-01-01-A-CRS-REPLY_0 | 24/03/16
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-02-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:T-00907/E-1210/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-02-A-CRS-REPLY_0 | 24/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:E-1210/2544-54-DW-1622-01-02-A-CRS_0
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-03-A-CRS_0 | 15/03/16 | CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:T-0907/MIDOR-TPIT-E-2016-03-15_22-25 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01211 2544-54-DW-1622-01-01-A-CRS-REPLY_0 | 24/03/16
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-03-A-CRS_1 | 16/01/17 | CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:T-00907/E-1210/MIDOR-T-00162 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 54 | ELECTRICAL | 2544-54-DW-1622-01-03-A-CRS-REPLY_0 | 24/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54 - ELECTRICAL CABLE ROUTING | REF:E-1210/2544-54-DW-1622-01-03-A-CRS_0
CRS | MIDOR | 54 | PROCESS | 2544-54-JSD-0001-01-A-CRS_0 | 11/05/16 | CLIENT COMMENTS TO UNIT 54,55 EFFLUENT WASTE WATER TREATMENT SYSTEM DESIGN BASIS | REF.: TPIT-MIDOR-T-01666 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01567/2544-54-JSD-0001-01-A-CRS-REPLY_0 | 11/05/16
CRS | MIDOR | 54 | PROCESS | 2544-54-JSD-0001-01-A-CRS_1 | 31/05/16 | CLIENT COMMENTS TO UNIT 54,55 EFFLUENT WASTE WATER TREATMENT SYSTEM DESIGN BASIS | REF.: 2544-54-JSD-0001-01-A-CRS-REPLY_0
CRS | MIDOR | 54 | PROCESS | 2544-54-JSD-0001-01-A-CRS-REPLY_0 | 11/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54,55 EFFLUENT WASTE WATER TREATMENT SYSTEM DESIGN BASIS | REF.: E-1567/2544-54-JSD-0001-01-A-CRS_0 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-05-31_14-20/2544-54-JSD-0001-01-A-CRS_1 | 31/05/16
CRS | MIDOR | 54 |  | 2544-54-JSD-0001-01-B-CRS_0 | 2018-02-14 | CLIENT COMMENTS TO UNIT 54,55 EFFLUENT WASTE WATER TREATMENT SYSTEM DESIGN BASIS | REF.: MIDOR-TPIT-T-00440 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 54 |  | 2544-54-JSD-0001-01-B-CRS_1 | 2018-03-22 | CLIENT COMMENTS TO UNIT 54,55 EFFLUENT WASTE WATER TREATMENT SYSTEM DESIGN BASIS | REF.: MIDOR-TPIT-T-00460 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 54 |  | 2544-54-JSD-0001-01-B-CRS_2 | 2018-04-05 | CLIENT COMMENTS TO UNIT 54,55 EFFLUENT WASTE WATER TREATMENT SYSTEM DESIGN BASIS | REF.: MIDOR-TPIT-T-00465 | TPIT RESPONSE REQUIRED
CRS | MIDOR | 54 | PROCESS | 2544-54-NM-0003-01-A-CRS_0 | 05/09/16 | CLIENT COMMENTS TO UNIT 54 UTILITIES CONSUMPTION WASTE WATER TREATMENT | REF.MIDOR-TPIT-T-00025/TPIT-MIDOR-T-2192 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02161 / 2544-54-NM-0003-01-A-CRS-REPLY_0 | 23/09/16
CRS | MIDOR | 54 | PROCESS | 2544-54-NM-0003-01-A-CRS-REPLY_0 | 23/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54 UTILITIES CONSUMPTION WASTE WATER TREATMENT | REF.E-2162/2544-54-NM-0003-01-A-CRS_0
CRS | MIDOR | 54 | PROCESS | 2544-54-PID-0021-A-CRS_0 | 16/07/16 | CLIENT COMMENTS TO UNIT 54 PIPING AND INSTRUMENT DIAGRAM - SULPHUR RECOVERY UNIT AND TAIL GAS TREATMENT UNIT UTILITIES | REF:T-2089/MIDOR-TPIT-E-2016-07-17_13-18 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01966 / 2544-54-PID-0021-A-CRS-REPLY_0 | 19/07/16
CRS | MIDOR | 54 | PROCESS | 2544-54-PID-0021-A-CRS_1 | 22/07/16 | CLIENT COMMENTS TO UNIT 54 PIPING AND INSTRUMENT DIAGRAM - SULPHUR RECOVERY UNIT AND TAIL GAS TREATMENT UNIT UTILITIES | REF: 2544-54-PID-0021-A-CRS-REPLY_0
CRS | MIDOR | 54 | PROCESS | 2544-54-PID-0021-A-CRS-REPLY_0 | 19/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54 PIPING AND INSTRUMENT DIAGRAM - UNIT 23 - AMINE REGENERATION UNIT | REF: E-1966/2544-54-PID-0021-B-CRS_0 | OWNER RESPONSE REQUIRED |  | 2544-54-PID-0021-A-CRS_1/MIDOR-TPIT-E-2016-07-24_07-49 | 22/07/16
CRS | MIDOR | 54 | PROCESS | 2544-54-PID-0021-A-CRS-REPLY_1 | 26/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54 PIPING AND INSTRUMENT DIAGRAM - UNIT 23 - AMINE REGENERATION UNIT | REF: E-1990/2544-54-PID-0021-B-CRS_1 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01990/2544-54-PID-0021-A-CRS_1 | 26/07/16
CRS | MIDOR | 54 | MACHINERY | 2544-54-SP-0910-01-0-CRS_0 | 08/06/16 | CLIENT COMMENTS TO CENTRIFUGAL PUMP DATA SHEET FOR LIFT PUMP - 54-P-01 A/B-N | REF.:T-1840/MIDOR-TPIT-E-2016-06-08
CRS | MIDOR | 54 | MACHINERY | 2544-54-SP-0910-01-0-CRS_1 | 06/06/16 | CLIENT COMMENTS TO CENTRIFUGAL PUMP DATA SHEET FOR LIFT PUMP - 54-P-01 A/B-N | REF.T-1840/MIDOR-TPIT-E-2016-06-07_02-55 | TPIT RESPONSE REQUIRED |  | 2544-54-SP-0910-01-0-CRS-REPLY_1 TPIT-MIDOR-E-01810 | 15/06/16
CRS | MIDOR | 54 | MACHINERY | 2544-54-SP-0910-01-0-CRS-REPLY_1 | 15/06/16 | TPIT REPLY TO CLIENT COMMENTS TOCENTRIFUGAL PUMP DATA SHEET FOR LIFT PUMP - 54-P-01 A/B-N | REF: T-01840/2544-54-SP-0910-01-0-CRS_1
CRS | MIDOR | 54 | MACHINERY | 2544-54-SP-0910-04-PB-CRS_0 | 25/04/16 | CLIENT COMMENTS TO UNIT 54 DATA SHEET FOR CENTRIFUGAL PUMP DATA SHEET - SDA SOLVENT PUMPS 51-P-46 A/B | REF.:00708\MIDOR-TPIT-E-2016-04-26_09-03
CRS | MIDOR | 54 | MACHINERY | 2544-54-SP-0910-06-0-CRS_0 | 15/06/16 | CLIENT COMMENTS TO NON OILY WATER SUMP PUMPS FOR 54-P-45 A/B | REF:T-1994/MIDOR-TPIT-E-2016-06-15_12-57
CRS | MIDOR | 54 | MACHINERY | 2544-54-SP-0910-07-PB-CRS_0 | 25/04/16 | CLIENT COMMENTS TO UNIT 54 CENTRIFUGAL PUMP DATA SHEET FOR DAF RECYCLE PUMP - 54-P-07 D-N | REF.:00708\MIDOR-TPIT-E-2016-04-26_09-03
CRS | MIDOR | 54 | PROCESS | 2544-54-SP-0940-01-PA-CRS_0 | 05/06/16 | CLIENT COMMENTS TO RECIPROCATING PUMP DATASHEET 54P21A/B | REF:T-1858/MIDOR-TPIT-E-2016-06-05_14-41 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01869/2544-54-SP-0940-01-PA-CRS-REPLY_0 | 27/06/16
CRS | MIDOR | 54 | PROCESS | 2544-54-SP-0940-01-PA-CRS-REPLY_0 | 27/06/16 | TPIT REPLY TO CLIENT COMMENTS TO RECIPROCATING PUMP DATASHEET 54P21A/B | REF:E-1869/2544-54-SP-0940-01-PA-CRS_0
CRS | MIDOR | 54 | PROCESS | 2544-54-SP-1040-01-PA-CRS_0 | 31/05/16 | CLIENT COMMENTS TO 54K02C DATA SHEET | REF:T-1843/MIDOR-TPIT-E-2016-05-31_13-42
CRS | MIDOR | 54 | PROCESS | 2544-54-SP-1040-01-PB-CRS_0 | 11/09/17 | CLIENT COMMENTS TO 54K02C DATA SHEET | REF:T-2082/MIDOR-TPIT-T-00393 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 54 | PROCESS | 2544-54-SP-1040-01-PB-CRS_1 | 02/10/17 | CLIENT COMMENTS TO 54K02C DATA SHEET | REF:T-2082/MIDOR-TPIT-T-00403 | CLOSED |  | APPROVED/CLOSED
CRS | MIDOR | 55 | PROCESS | 2544-55-PID-0021-003-01-A-CRS_0 | 21/07/16 | CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - WASTE WATER TREATMENT SANITARY WATER LIFTING 55 BA 03 | REF:T-1670/MIDOR-TPIT-E-2016-07-21_13-27
CRS | MIDOR | 55 | PROCESS | 2544-55-PID-0021-003-01-A-CRS_1 | 03/11/16 | CLIENT COMMENTS TO PIPING AND INSTRUMENT DIAGRAM - WASTE WATER TREATMENT DIAGRAM UNIT 55
CRS | MIDOR | 55 | PROCESS | 2544-55-PID-0021-A-CRS_0 | 26/06/16 | CLIENT COMMENTS TO UNIT 55 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-2028/MIDOR-TPIT-E-2016-06-27_08-32 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01859 TPIT-MIDOR-E-01868/2544-55-PID-0021-A-CRS-REPLY_0 | 27/06/16
CRS | MIDOR | 55 | PROCESS | 2544-55-PID-0021-A-CRS_1 | 29/06/16 | CLIENT COMMENTS TO UNIT 55 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-2028/MIDOR-TPIT-E-2016-06-27_08-32 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02028 TPIT-MIDOR-E-01868/2544-55-PID-0021-A-CRS-REPLY_01 | 27/06/16
CRS | MIDOR | 55 | PROCESS | 2544-55-PID-0021-A-CRS-REPLY_0 | 27/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 55 - PIPING AND INSTRUMENT DIAGRAMS | REF:E-1868/2544-55-PID-0021-A-CRS_0
CRS | MIDOR | 55 | MACHINERY | 2544-55-SP-0910-03-PA-CRS_0 | 06/09/17 | CLIENT COMMENTS TO DATA SHEET FOR PUMP 55-P-03 | REF:T-2077/MIDOR-TPIT-T-00387 | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS
CRS | MIDOR | 56 | PIPING | 2544-56-DW-0051-01-01-C-CRS_0 | 20/05/16 | CLIENT COMMENTS TO UNIT 56 - SULPHUR SOLIDIFICATION UNIT PLOT PLAN | REF:T-1087/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-56-DW-0051-01-01-C-CRS-REPLY_0//TPIT-MIDOR-T-2089 | 14/06/16
CRS | MIDOR | 56 | PIPING | 2544-56-DW-0051-01-01-C-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 56 - SULPHUR SOLIDIFICATION UNIT PLOT PLAN | REF:T-1087/MIDOR-TPIT-T-00047
CRS | MIDOR | 56 | PIPING | 2544-56-DW-0051-01-01-C-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 56 - SULPHUR SOLIDIFICATION UNIT PLOT PLAN | REF:T-1087/MIDOR-TPIT-T-00047 |  |  | 2544-56-DW-0051-01-01-C-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 56 | CIVIL | 2544-56-DW-1745-01-B-CRS-REPLY_0 | 07/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 56 SULPHER SOLIDIFICATION FOUNDATION RETAINING WALL FOR SULPHER STACKIN | REF: T-0279/TPIT-MIDOR-E-02235 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 56 | CIVIL | 2544-56-DW-1823-01-01-A-CRS_0 | 11/10/16 | CLIENT COMMENTS TO UNIT 56 - STEEL STRUCTURE OF SULPHUR SOLIDIFICATION SHELTER UNIT 56 | REF:T-00754 |  |  | APPROVED/CLOSED | 11/10/16
CRS | MIDOR | 56 | CIVIL | 2544-56-DW-1823-01-A-CRS-REPLY_0 | 07/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 56 - STEEL STRUCTURE OF SULPHUR SOLIDIFICATION SHELTER UNIT 56 | REF: T-00754/TPIT-MIDOR-E-02235 | OWNER RESPONSE REQUIRED
CRS | MIDOR | 56 | MACHINERY | 2544-56-SP-0910-01-A-CRS_0 | 09/03/16 | CLIENT COMMENTS TO UNIT 56 - D/S FOR CENTRIFUGAL PUMP | REF:T-0945/MIDOR-TPIT-E-2016-03-11_11-07
CRS | MIDOR | 58 | PROCESS | 2544-58-PID-0031-056-A-CRS_0 | 26/05/16 | CLIENT COMMENTS TO UNIT 58 - PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING (BLT CONTRACT) UTILITIES | REF:T-1743/MIDOR-TPIT-E-2016-05-27_00-10
CRS | MIDOR | 58 | PROCESS | 2544-58-PID-0031-056-A-CRS_1 | 26/05/16 | CLIENT COMMENTS TO UNIT 58 - PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING (BLT CONTRACT) UTILITIES | REF:T-1743/PMC-MIDOR-E-0042
CRS | MIDOR | 59 | PROCESS | 2544-59-PID-0031-056-01-A-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 59 PIPING AND INSTRUMENT DIAGRAM - INTERCONNECTING (BLT CONTRACT) UTILITIES INTERCONNECTING | REF:T-1744/PMC-MIDOR-E-0043
CRS | MIDOR | 60 | PIPING | 2544-60-DW-0051-01-01-B-CRS_0 | 24/05/16 | CLIENT COMMENTS TO UNIT 60 - INTERCONNECTING PIPE WAY - BLOCK I - ZONE I201 - DETAILED PLOT PLAN | REF:T-1415/MIDOR-TPIT-E-2016-05-30_22-38 | OWNER RESPONSE REQUIRED |  | 2544-60-DW-0051-01-01-B-CRS-REPLY_0/TPIT-MIDOR-T-2089 | 14/06/16
CRS | MIDOR | 60 | PIPING | 2544-60-DW-0051-01-01-B-CRS_1 | 23/09/16 | CLIENT COMMENTS TO UNIT 60 - INTERCONNECTING PIPE WAY - BLOCK I - ZONE I201 - DETAILED PLOT PLAN | REF:T-1415/MIDOR-TPIT-T-00047
CRS | MIDOR | 60 | PIPING | 2544-60-DW-0051-01-01-B-CRS-REPLY_0 | 14/06/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 60 - INTERCONNECTING PIPE WAY - BLOCK I - ZONE I201 - DETAILED PLOT PLAN | REF:E-2089/MIDOR-TPIT-E-2016-05-30_22-38 |  |  | 2544-60-DW-0051-01-01-B-CRS_1/MIDOR-TPIT-T-00047 | 14/06/16
CRS | MIDOR | 60 | PIPING | 2544-60-DW-0051-01-B-CRS-REPLY_0 | 02/09/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 60 - INTERCONNECTING PIPE WAY - BLOCK I - ZONE I201 - DETAILED PLOT PLAN | REF.:T-1415/TPIT-MIDOR-MOM-00065 | CLOSED
CRS | MIDOR | 60 | CIVIL | 2544-60-DW-1701-01-01-A-CRS_0 | 18/07/16 | CLIENT COMMENTS TO UNIT 60 - CIVIL DRAWING | REF:T-2109/MIDOR-TPIT-E-2016-07-19_10-41 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01967/2544-60-DW-1701-01-01-A-CRS-REPLY_0 | 19/07/16
CRS | MIDOR | 60 | CIVIL | 2544-60-DW-1701-01-01-A-CRS-REPLY_0 | 19/07/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 60 - CIVIL DRAWING | REF:E-1967/2544-60-DW-1701-01-01-A-CRS_0
CRS | MIDOR | 60 | PROCESS | 2544-60-PID-0031-057-01-A-CRS_0 | 26/05/16 | CLIENT COMMENTS TO UNIT 60 - PIPING AND INSTRUMENT DIAGRAM - UNIT DESCRIPTION UTILITIES INTERCON. NEW COOLING WATER SYST | REF:T-1745/MIDOR-TPIT-E-2016-05-27_00-06 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01681/2544-60-PID-0031-057-01-A-CRS-REPLY_0 | 27/05/16
CRS | MIDOR | 60 | PROCESS | 2544-60-PID-0031-057-01-A-CRS_1 | 26/05/16 | CLIENT COMMENTS TO UNIT 60 - PIPING AND INSTRUMENT DIAGRAM - UNIT DESCRIPTION UTILITIES INTERCON. NEW COOLING WATER SYST | RE:2544-60-PID-0031-057-01-A-CRS-REPLY_0
CRS | MIDOR | 60 | PROCESS | 2544-60-PID-0031-057-01-A-CRS-REPLY_0 | 27/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 60 - PID - UNIT DESCRIPTION UTILITIES INTERCON. NEW COOLING WATER SYST | REF:E-1681/2544-60-PID-0031-057-01-A-CRS | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-05-31_14-20/2544-60-PID-0031-057-01-A-CRS_1 | 31/05/16
CRS | MIDOR | 60 | PROCESS | 2544-60-PID-0031-A-CRS_0 | 09/06/16 | CLIENT COMMENTS TO UNIT 60 - PIPING AND INSTRUMENT DIAGRAMS | REF:T-1745/PMC-MIDOR-E-0045
Email | MIDOR | 00 | MATERIAL TECHNOLOGY | MIDOR-TPIT-E-0026 | 29/09/16 | CLIENT COMMENTS TO PIPING MATERIAL CLASS SPECIFICATION | REF: TPIT-MIDOR-T-02121 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02189 | 30/09/16
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-0029 | 03/10/16 | CLIENT COMMENTS TO FIREFIGHTING SPECIFICATION | REF: T-0606/2544-00-JSD-1900-01-B-CRS_2 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | PROCUREMENT | MIDOR-TPIT-E-2015-10-21_10-15 | 21/10/15 | CLIENT COMMENTS TO UNIT 00 - PROCUREMENT PROCEDURE | REF.: TPIT-MIDOR-T-00013
Email | MIDOR | 00 | PROCUREMENT | MIDOR-TPIT-E-2015-10-23_10-31 | 23/10/15 | CLIENT COMMENTS TO UNIT 00 - PROCUREMENT PROCEDURE | REF.: TPIT-MIDOR-T-00013
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-15_08-31 | 15/11/15 | CLIENT COMMENTS TO ELECT GENERAL SPECIFICATION | REF.: TPIT-MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00217 | 16/11/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-15_14-08 | 15/11/15 | CLIENT COMMENTS TO SPECIFICATION | REF.: TPIT-MIDOR-T-00032 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00303 | 24/11/15
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-18_20-58 | 18/11/15 | CLIENT COMMENTS TO ELECT GENERAL SPECIFICATION | REF.:TPIT-MIDOR-E-00217/MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00386 | 01/12/15
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2015-11-18_21-15 | 18/11/15 | CLIENT COMMENTS TO AUXILIARY STEAM BOILERS DESIGN/GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.:TPIT-MIDOR-T-00022 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00768 | 29/01/16
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2015-11-18_21-17 | 18/11/15 | CLIENT COMMENTS TO MATERIAL REQUISTION 0411-101 | REF.:TPIT-MIDOR-T-00045/46 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00353 | 27/11/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-18_21-19 | 18/11/15 | CLIENT COMMENTS TO SPECIFICATIONS | REF.: TPIT-MIDOR-T-00032 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00352 | 27/11/15
Email | MIDOR | 17 | PROCESS | MIDOR-TPIT-E-2015-11-19_10-18 | 19/11/15 | CLIENT COMMENTS TO UNIT 17 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00063 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00259 | 19/11/15
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-21_08-30 | 21/11/15 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.:TPIT-MIDOR-T-00018 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00342 | 27/11/15
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2015-11-22_11-39 | 22/11/15 | CLIENT COMMENTS TO GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.: TPIT-MIDOR-T-00022/MIDOR-E-00259 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00445 | 10/12/15
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2015-11-23_12-29 | 23/11/15 | CLIENT COMMENTS TO GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.: TPIT-MIDOR-T-00022/MIDOR-E-00259 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00445 | 10/12/15
Email | MIDOR | 00 | MATERIAL TECHNOLOGY | MIDOR-TPIT-E-2015-11-26_06-46 | 26/11/15 | CLIENT COMMENTS TO UNIT 00 - TYPICAL INSTALLATION STANDARDS | REF.: TPIT-MIDOR-T-00059 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00346 | 27/11/15
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2015-11-26_12-50 | 26/11/15 | CLIENT COMMENTS TO PLOT PLANS | REF.: TPIT-MIDOR-T-00070/71/73/74/75 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00369 | 30/11/15
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-11-26_20-13 | 26/11/16 | CLIENT COMMENTS TO UNIT 18 - 18-K-01 | REF: TPIT-MIDOR-T-00078
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-26_20-32 | 26/11/15 | CLIENT COMMENTS TO PROJECT PROCEDURE | REF.: TPIT-MIDOR-T-00069
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2015-11-26_20-35 | 26/11/15 | CLIENT COMMENTS TO UNIT 20 - RECYCLE GAS COMPRESSORS | REF.: TPIT-MIDOR-T-00079
Email | MIDOR | 00 | PACKAGES | MIDOR-TPIT-E-2015-11-26_20-44 | 26/11/15 | CLIENT COMMENTS TO UNIT 00 - JSS FOR PACKAGE UNIT | REF.: TPIT-MIDOR-T-00086 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00357 | 27/11/15
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-28_07-31 | 28/11/15 | CLIENT COMMENTS TO ELECTRICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00072 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00406 | 03/12/15
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-28_07-32 | 28/11/15 | CLIENT COMMENTS TO ELECTRICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00072
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-28_07-41 | 02/12/15 | CLIENT COMMENTS
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-28_10-51 | 28/11/15 | CLIENT COMMENTS TO ELECTRICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00072 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00387 | 01/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-29_08-29 | 29/11/15 | CLIENT COMMENTS TO PROJECT SPECIFICATION | REF.: TPIT-MIDOR-T-00072 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00388 | 01/12/15
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-29_08-30 | 29/11/15 | CLIENT COMMENTS TO ELECTRICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00072 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00389 | 01/12/15
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2015-11-29_08-31 | 29/11/15 | CLIENT COMMENTS TO PLOT PLANS (MIDOR DOCUMENTS CODING & NUMBERING SISTEM) | REF.: TPIT-MIDOR-T-00070/71/73/74/75 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00365 | 30/11/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-29_08-39 | 02/12/15 | CLIENT COMMENTS
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-30_08-17 | 30/11/15 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.:TPIT-MIDOR-T-00018/72
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-11-30_08-26 | 30/11/15 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00072
Email | MIDOR | 00 | MATERIAL TECHNOLOGY | MIDOR-TPIT-E-2015-11-30_08-26BIS | 30/11/15 | CLIENT COMMENTS TO UNIT 00 - TYPICAL INSTALLATION STANDARDS | REF.: TPIT-MIDOR-T-00059/MIDOR-E-00346 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00413 | 03/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-30_09-53 | 02/12/15 | CLIENT COMMENTS
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-30_09-53BIS | 02/12/15 | CLIENT COMMENTS
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-11-30_21-34 | 30/11/15 | CLIENT COMMENTS TO REQUIREMENTS FOR VENDOR DOCUMENTATION | REF.: TPIT-MIDOR-T-00044
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-01_19-34 | 02/12/15 | CLIENT COMMENTS TO UNIT 20 - RECYCLE GAS | REF.: TPIT-MIDOR-T-00079
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-12-02_07-21 | 02/12/15 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00072
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-02_14-25 | 02/12/15 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.:TPIT-MIDOR-T-00056
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2015-12-03_06-39 | 03/12/15 | CLIENT COMMENTS TO GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.: TPIT-MIDOR-T-00022/MIDOR-E-00259 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00445 | 10/12/15
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-12-03_06-43 | 02/12/15 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.:TPIT-MIDOR-E-00388/TPIT-MIDOR-T-72
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-12-03_06-46 | 03/12/15 | CLIENT COMMENTS TO ELECT GENERAL SPECIFICATION | REF.:TPIT-MIDOR-E-00386/MIDOR-T-00019 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00508 | 16/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-06_09-37 | 06/12/15 | CLIENT COMMENTS TO UNIT 00 - DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00105 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00626 | 14/01/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-06_11-39 | 06/12/15 | CLIENT COMMENTS TO UNIT 00 - GENERAL DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00125
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2015-12-07_08-52 | 07/12/15 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.: TPIT-MIDOR-E-00406/T-00072 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00581 | 07/01/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-08_11-55 | 08/12/15 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00122
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-08_11-55BIS | 08/12/15 | CLIENT COMMENTS TO UNIT 08 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00118
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-08_11-56 | 08/12/15 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00121
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-08_12-01 | 08/12/15 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.: TPIT-MIDOR-T-00128 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00675 | 19/01/16
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2015-12-09_07-49 | 09/12/15 | CLIENT COMMENTS TO UNIT 20 - RECYCLE GAS COMPRESSORS | REF.: TPIT-MIDOR-T-00079
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-09_14-52 | 09/12/15 | CLIENT COMMENTS TO UNIT 00 - DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00119
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-09_14-54 | 09/12/15 | CLIENT COMMENTS TO UNIT 00 - GENERAL DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00109
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-11_22-05 | 11/12/15 | CLIENT COMMENTS TO SPECIFICATIONS | REF.: TPIT-MIDOR-T-00056
Email | MIDOR | 17 | PROCESS | MIDOR-TPIT-E-2015-12-14_07-24 | 14/12/15 | CLIENT COMMENTS TO UNIT 17 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00132 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00683 | 20/01/16
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2015-12-15_09-41 | 15/12/15 | CLIENT COMMENTS TO MATERIAL REQUISITION 2544-00-MR-0511-001 | REF.: TPIT-MIDOR-T-00155 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00533 | 18/12/15
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-15_10-37 | 15/12/15 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00142
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2015-12-16_13-09 | 16/12/15 | CLIENT COMMENTS TO JOB DESIGN SPECIFICATION FOR PIPING STRESS ANALYSIS | REF.: TPIT-MIDOR-T-00137
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-18_07-49 | 18/12/15 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.: TPIT-MIDOR-T-00188
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2015-12-18_08-51 | 18/12/15 | CLIENT COMMENTS TO UNIT 00 - CIVIL DRAWINGS | REF.: TPIT-MIDOR-T-00156
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-20_16-38 | 20/12/15 | CLIENT COMMENTS TO UNIT 00 - DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00187 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00798 | 03/02/16
Email | MIDOR | 47 | PIPING | MIDOR-TPIT-E-2015-12-21_07-13 | 21/12/15 | CLIENT COMMENTS TO UNIT 47 - DETAILED PLOT PLAN | REF.: TPIT-MIDOR-T-00198
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-21_09-40 | 21/12/15 | CLIENT COMMENTS TO UNIT 00 - DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00187
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2015-12-21_10-31 | 21/12/15 | CLIENT COMMENTS TO UNIT 00 - CIVIL DRAWINGS | REF.: TPIT-MIDOR-T-00156
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2015-12-22_08-48 | 22/12/15 | CLIENT COMMENTS TO UNIT 00 - CIVIL DRAWINGS | REF.: TPIT-MIDOR-T-00222
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-22_11-38 | 22/12/15 | CLIENT COMMENTS TO UNIT 41 - DATA SHEETS | REF.:TPIT-MIDOR-T-00178
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-24_13-55 | 24/12/15 | CLIENT COMMENTS TO UNIT 00 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00097
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-25_15-28 | 25/12/15 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00121
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-25_15-28BIS | 25/12/15 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00097 |  |  | TPIT-MIDOR-E-00936 | 23/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-25_15-41 | 25/12/15 | CLIENT COMMENTS TO UNIT 37 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00207 |  |  | TPIT-MIDOR-E-00699 | 21/01/16
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2015-12-25_15-45 | 25/12/15 | CLIENT COMMENTS TO UNIT 0A - CIVIL DRAWINGS | REF.: TPIT-MIDOR-T-00223
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-25_15-46 | 25/12/15 | CLIENT COMMENTS TO UNIT 37 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00206 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00697 | 21/01/16
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2015-12-25_15-49 | 25/12/15 | CLIENT COMMENTS TO UNIT 0A - CIVIL DRAWINGS | REF.: TPIT-MIDOR-T-00222
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2015-12-25_20-59 | 25/12/15 | CLIENT COMMENTS TO UNIT 0A - CIVIL DRAWINGS | REF.: TPIT-MIDOR-T-00223
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-25_20-59BIS | 25/12/15 | CLIENT COMMENTS TO UNIT 41 - DATA SHEET | REF.: TPIT-MIDOR-T-00177
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-26_19-47 | 26/12/15 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.: TPIT-MIDOR-T-00230 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00945 | 23/02/16
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2015-12-27_20-27 | 27/12/15 | CLIENT COMMENTS TO MACHINERY PROJECT SPECIFICATION | REF.: TPIT-MIDOR-T-00022/32/56/230 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00606 - TPIT-MIDOR-E-00945 DTD 23/02/2016 | 12/01/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-29_14-12 | 29/12/15 | CLIENT COMMENTS TO UNIT 22 - PROCESS DATA SHEET | REF: TPIT-MIDOR-T-00194/00193 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00922 | 22/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-29_14-13 | 29/12/15 | CLIENT COMMENTS TO UNIT 23 - PROCESS DATA SHEET | REF: TPIT-MIDOR-T-00197 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00921 | 22/02/16
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2015-12-30_06-31 | 30/12/15 | CLIENT COMMENTS TO MATERIAL REQUISTION 0411-101 | REF.:TPIT-MIDOR-T-00045
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-30_10-43 | 30/12/15 | CLIENT COMMENTS TO UNIT 42 - DUTY SPECIFICATION | REF.:TPIT-MIDOR-T-00243
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-30_10-43BIS | 30/12/15 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00235
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-30_10-44 | 30/12/15 | CLIENT COMMENTS TO UNIT 36 - DUTY SPECIFICATION | REF.:TPIT-MIDOR-T-00244
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-30_11-13 | 30/12/15 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.:TPIT-MIDOR-T-00261 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00945 | 23/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2015-12-30_13-09 | 30/12/15 | CLIENT COMMENTS TO UNIT 00 - JSS FOR GENERAL PURPOSE | REF.: TPIT-MIDOR-T-00090 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00945 | 23/02/16
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2015-12-30_13-09BIS | 30/12/15 | CLIENT COMMENTS TO UNIT 00 - JSS FOR STEAM TURBINE | REF.: TPIT-MIDOR-T-00091 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00945 | 23/02/16
Email | MIDOR | 17 | PVHE | MIDOR-TPIT-E-2015-12-30_14-02 | 30/12/15 | CLIENT COMMENTS TO UNIT 17 - COLUMN DRAWINGS | REF.: TPIT-MIDOR-T-00112 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00607 | 12/01/15
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2015-12-31_07-33 | 31/12/15 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-0150-101 | REF.:TPIT-MIDOR-T-00271 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01149/2544-00-MR-0150-101-A-CRS-REPLY_0 | 18/03/16
Email | MIDOR | 17 | PROCESS | MIDOR-TPIT-E-2015-12-31_09-47 | 31/12/15 | CLIENT COMMENTS TO UNIT 17 - PROCESS DATA SHEET | REF.:TPIT-MIDOR-T-00238
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2015-12-31_12-49 | 31/12/15 | CLIENT COMMENTS TO UNIT 42 - DUTY SPECIFICATION | REF.: TPIT-MIDOR-T-00243
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-01-01_11-01 | 01/01/16 | CLIENT COMMENTS TO UNIT 00 - CIVIL DRAWINGS | REF.:TPIT-MIDOR-T-00253
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-03_09-16 | 03/01/16 | CLIENT COMMENTS TO UNIT 00 - JSD | REF.:TPIT-MIDOR-T-00319 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00591 | 08/01/15
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-03_09-17 | 03/01/16 | CLIENT COMMENTS TO UNIT PROCESS DATA SHEET | REF.:TPIT-MIDOR-T-00317 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00698 | 21/01/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-03_09-17BIS | 03/01/16 | CLIENT COMMENTS TO UNIT 21 - PDS 0811 | REF.:TPIT-MIDOR-T-00277 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00995 | 01/03/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-03_09-18 | 03/01/16 | CLIENT COMMENTS TO UNIT 21 - PDS 0411/0480 | REF.:TPIT-MIDOR-T-00274 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00994 | 01/03/16
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2016-01-03_13-16 | 03/01/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 0150-101 | REF.:TPIT-MIDOR-T-00271
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2016-01-03_13-17 | 03/01/16 | CLIENT COMMENTS TO UNIT 20 - MECHANICAL DATA SHEET | REF.:TPIT-MIDOR-T-00301
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-03_13-19 | 03/01/16 | CLIENT COMMENTS TO UNIT 07 - PROCESS DATA SHEET | REF.:TPIT-MIDOR-T-00276
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-01-03_13-20 | 03/01/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 0910-001 | REF.:TPIT-MIDOR-T-00301
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2016-01-03_13-21 | 03/01/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 0150-101 | REF.:TPIT-MIDOR-T-00271
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-03_13-21BIS | 03/01/16 | CLIENT COMMENTS TO UNIT 46 - PROCESS DATA SHEET | REF.:TPIT-MIDOR-T-00318
Email | MIDOR | 00 | START UP | MIDOR-TPIT-E-2016-01-03_13-42 | 03/01/16 | CLIENT COMMENTS TO UNIT 00 - SPARE PART PHILOSOPHY | REF.:TPIT-MIDOR-T-00210 | TPIT RESPONSE REQUIRED |  | TPITI-MIDOR-E-01279/2544-00-SP-9200-01-A-CRS-REPLY_0 | 25/03/16
Email | MIDOR | 00 | START UP | MIDOR-TPIT-E-2016-01-03_13-42BIS | 03/01/16 | CLIENT COMMENTS TO UNIT 00 - SPARE PART PHILOSOPHY | REF.:TPIT-MIDOR-T-00210 | TPIT RESPONSE REQUIRED |  | TPITI-MIDOR-E-01279/2544-00-SP-9200-01-A-CRS-REPLY_0 | 25/03/16
Email | MIDOR | 00 | START UP | MIDOR-TPIT-E-2016-01-03_13-42BIS1 | 03/01/16 | CLIENT COMMENTS TO UNIT 00 - SPARE PART PHILOSOPHY | REF.:TPIT-MIDOR-T-00210 |  |  | TPITI-MIDOR-E-01279/2544-00-SP-9200-01-A-CRS-REPLY_0 | 25/03/16
Email | MIDOR | 47 | PROCESS | MIDOR-TPIT-E-2016-01-03_13-51 | 03/01/16 | CLIENT COMMENTS TO UNIT 47 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00182
Email | MIDOR | 47 | PROCESS | MIDOR-TPIT-E-2016-01-03_14-07 | 03/01/16 | CLIENT COMMENTS TO UNIT 47 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00265
Email | MIDOR | 47 | PROCESS | MIDOR-TPIT-E-2016-01-04_08-25 | 04/01/16 | CLIENT COMMENTS TO UNIT 47 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00182
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-06_08-06 | 06/01/16 | CLIENT COMMENTS TO UNIT 00 - DESIGN SPECIFICATION | REF.:TPIT-MIDOR-T-00272
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-09_18-48 | 09/01/16 | CLIENT COMMENTS TO UNIT 11 - PROCESS DATA SHEET | REF.:TPIT-MIDOR-T-00220
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-10_09-41 | 10/01/16 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.: TPIT-MIDOR-T-00051/00090 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00945 | 23/02/16
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-01-11_07-36 | 11/01/16 | CLIENT COMMENTS TO UNIT 00 - JOB CONSTRUCTION SPECIFICATION | REF.:TPIT-MIDOR-T-00308
Email | MIDOR | 00 | PROCUREMENT | MIDOR-TPIT-E-2016-01-12_07-13 | 12/01/16 | CLIENT COMMENTS TO BIDDER LISTS | REF.: TPIT-MIDOR-T-0180/0370/0371/0578
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-01-12_11-49 | 12/01/16 | CLIENT COMMENTS TO UNIT 15 - ELECTRICAL LOAD SUMMARY | REF.:TPIT-MIDOR-T-00300 |  |  | TPIT-MIDOR-E-00992 | 01/03/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-12_11-50 | 12/01/16 | CLIENT COMMENTS TO UNIT 00 - TECHNICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00268
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-12_11-51 | 12/01/16 | CLIENT COMMENTS TO UNIT 00 - GENERAL DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00229
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-13_07-38 | 13/01/16 | CLIENT COMMENTS TO UNIT 00 - QUALITY CONTROL PLANS | REF.:TPIT-MIDOR-T-00336
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-01-13_07-43 | 13/01/16 | CLIENT COMMENTS TO UNIT 00 - QCP BUILDINGS | REF.:TPIT-MIDOR-T-00340
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-01-13_08-05 | 13/01/16 | CLIENT COMMENTS TO UNIT 00 - QUALITY CONTROL PLANS) | REF.:TPIT-MIDOR-T-00328
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-13_08-46 | 13/01/16 | CLIENT COMMENTS TO UNIT 00 - MATERIAL REQUISITION | REF.:TPIT-MIDOR-T-00231 | TPIT RESPONSE REQUIRED |  | TPIT-MIDORT-00783 | 01/02/16
Email | MIDOR | 00 | BUILDINGS | MIDOR-TPIT-E-2016-01-13_13-15 | 13/01/16 | CLIENT COMMENTS TO UNIT 00 - BUILDING LIST | REF.: TPIT-MIDOR-T-00342 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00628 | 14/01/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-14_06-40 | 14/01/16 | CLIENT COMMENTS TO UNIT 02 - PROCESS DATA SHEET | REF.:TPIT-MIDOR-T-00320
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-14_06-50 | 14/01/16 | CLIENT COMMENTS TO UNIT 00 - JOB SPECIFICATION | REF.: TPIT-MIDOR-T-00345
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-14_06-53 | 14/01/16 | CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00235/MIDOR-E-00608 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00678 | 20/01/16
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-01-14_08-46 | 14/01/16 | CLIENT COMMENTS TO UNIT 00 - QCP | REF.:TPIT-MIDOR-T-00329
Email | MIDOR | 47 | PIPING | MIDOR-TPIT-E-2016-01-14_09-00 | 14/01/16 | CLIENT COMMENTS TO UNIT 47 - DETAILED PLOT PLAN | REF.: TPIT-MIDOR-T-00198 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00654 | 18/01/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-14_13-34 | 14/01/16 | CLIENT COMMENTS TO UNIT 00 - TECHNICAL SPECIFICATION | REF.: TPIT-MIDOR-T-00335 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00814 | 05/02/16
Email | MIDOR | 00 | MATERIAL TECHNOLOGY | MIDOR-TPIT-E-2016-01-15_08-47 | 15/01/16 | CLIENT COMMENTS TO UNIT 00 - PIPING MATERIAL CLASSES | REF.: TPIT-MIDOR-T-00339 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00741 | 26/01/16
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-01-18_14-26 | 18/01/16 | CLIENT COMMENTS TO UNIT 00 - FIRE PROOFING SPECIFICATION | REF.: TPIT-MIDOR-T-00357
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-18_14-26BIS | 18/01/16 | CLIENT COMMENTS TO UNIT 20 - DRAWING | REF.: TPIT-MIDOR-T-00359
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-01-19_07-08 | 19/01/16 | CLIENT COMMENTS TO UNIT 00 - CIVIL DRAWINGS | REF.: TPIT-MIDOR-T-00365 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00687 | 20/01/16
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-01-19_07-45 | 19/01/16 | CLIENT COMMENTS TO UNIT 00 - CIVIL DRAWING | REF: TPIT-MIDOR-T-00368 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00887 | 16/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-20_08-15 | 20/01/16 | CLIENT COMMENTS TO UNIT 00 - JOB DESIGN SPECIFICATION | REF.: TPIT-MIDOR-T-00355 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00760 | 28/01/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-21_07-16 | 21/01/16 | CLIENT COMMENTS ON UNIT 19 - UOP PROCESS FLOW DIAGRAMS | REF.: ID-00304/ UOP-MIDOR-T-289
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-21_08-26 | 21/01/16 | CLIENT COMMENTS ON UNIT 18 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00214
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-22_07-34 | 22/01/16 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.:TPIT-MIDOR-T-00128/E-00675 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00709 | 22/01/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-22_21-16 | 22/01/16 | CLIENT COMMENTS TO UNIT PROCESS DATA SHEET | REF.:TPIT-MIDOR-E-00698
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-01-24_22-05 | 24/01/16 | CLIENT COMMENTS ON UNIT 00 - QUALITY CONTROL PLANS | REF.: TPIT-MIDOR-T-00396
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-01-25_19-24 | 25/01/16 | CLIENT COMMENTS TO MACHINERY PROJECT SPECIFICATION | REF.: TPIT-MIDOR-T-00022/562
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2016-01-25_23-10 | 25/01/16 | CLIENT COMMENTS TO UNIT 22 - MECHANICAL DRAWINGS | REF.: TPIT-MIDOR-T-00383
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2016-01-25_23-27 | 25/01/16 | CLIENT COMMENTS TO UNIT 22 - MECHANICAL DRAWINGS | REF.: TPIT-MIDOR-T-00385
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-25_23-29 | 25/01/16 | CLIENT COMMENTS TO UNIT 18 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00389
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-01-26_07-17 | 26/01/16 | CLIENT COMMENTS TO UNIT 18 - FIREPROOFING DRAWING | REF.: TPIT-MIDOR-T-00404
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-26_07-17BIS | 26/01/16 | CLIENT COMMENTS TO UNIT 20 - DRAWING | REF.: TPIT-MIDOR-T-00360
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-26_09-13 | 26/01/16 | CLIENT COMMENTS TO UNIT 00 - JSS | REF.: TPIT-MIDOR-T-00379 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00379 | 26/01/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-26_13-29 | 26/01/16 | CLIENT COMMENTS TO UNIT 00 - JOB SPECIFICATION | REF.: TPIT-MIDOR-T-00424
Email | MIDOR | 00 | START UP | MIDOR-TPIT-E-2016-01-26_20-03 | 26/01/16 | CLIENT COMMENTS ON 2544-00-PP-907_A | REF.:TPIT-MIDOR-T-00225
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-01-27_09-55 | 27/01/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR COMMUNICATION SYSTEM | REF.: TPIT-MIDOR-T-00311
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2016-01-27_13-14 | 27/01/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-2520-101 | REF.: TPIT-MIDOR-T-00413
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-01-27_13-24 | 27/01/16 | CLIENT COMMENTS TO UNIT 18 - FIRE AND GAS LAYOUT | REF.: TPIT-MIDOR-T-00403 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00767 | 29/01/16
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-01-27_13-24BIS | 27/01/16 | CLIENT COMMENTS TO UNIT 05 - FIRE AND GAS LAYOUT | REF.: TPIT-MIDOR-T-00408
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-01-27-09-34 | 27/01/16 | CLIENT COMMENTS ON UOP PIPING AND INSTRUMENT DIAGRAMS | REF.: ID-00270/00322/00388/00414/00417
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-01-28_01-55 | 28/01/16 | CLIENT COMMENTS ON TPIT-MIDOR COMMENTS | REF.: TPIT-MIDOR-T-00153/155
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-28_02-01 | 28/01/16 | CLIENT COMMENTS ON UNIT 18 - PROCESS DATA SHEET | REF.: TPIT-MIDOR-T-00191/ID-00196
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2016-01-28_07-49 | 28/01/16 | CLIENT COMMENTS TO MATERIAL REQUISITION 00-MR-2520-101 | REF.: TPIT-MIDOR-T-00413
Email | MIDOR | 47 | PROCESS | MIDOR-TPIT-E-2016-01-28_13-57 | 28/01/16 | CLIENT COMMENTS TO UNIT 08-12-18-23-41-47 DATA SHEETS | TPIT-MIDOR-T-0152/159/160/172/178/179
Email | MIDOR | 00 | START UP | MIDOR-TPIT-E-2016-01-28_14-09 | 28/01/16 | CLIENT COMMENTS TO UNIT 00 - SP-9901-01 - MAINTENANCE PHILOSOPHY | REF.: TPIT-MIDOR-T-00211
Email | MIDOR | 47 | PIPING | MIDOR-TPIT-E-2016-01-29_09-10 | 29/01/16 | CLIENT COMMENTS TO UNIT 47 - DETAILED PLOT PLAN | REF.: TPIT-MIDOR-T-00198
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-01-29_12-17 | 29/01/16 | CLIENT COMMENTS TO MACHINERY PROJECT SPECIFICATION | REF.: TPIT-MIDOR-E-2016-01-28_03-59
Email | MIDOR | 00 | BUILDINGS | MIDOR-TPIT-E-2016-01-31_11-16 | 31/01/16 | CLIENT COMMENTS TO UNIT 00 - DW BUILDING | REF.:TPIT-MIDOR-T-00428
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-01-31_19-46 | 31/01/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEETS | REF.:TPIT-MIDOR-T-00472
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-01_06-56 | 01/02/16 | CLIENT COMMENTS TO UNIT 02 - PROCESS DATA SHEETS | REF.: TPIT-MIDOR-T-00237 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00787 | 02/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-01_11-13 | 01/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS | REF.:TPIT-MIDOR-T-00495 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00874 | 15/02/16
Email | MIDOR | 17 | PROCESS | MIDOR-TPIT-E-2016-02-02_06-45 | 02/02/16 | CLIENT COMMENTS TO UNIT 17 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00240
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-02_08-11 | 08/02/16 | CLIENT COMMENTS TO UNIT 46-PID-0031-068-01 | REF.: TPIT-MIDOR-T-1028 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01255
Email | MIDOR | 00 | PACKAGES | MIDOR-TPIT-E-2016-02-02_12-11 | 02/02/16 | CLIENT COMMENTS TO UNIT 11 - SPC FOR UNHEADING SYSTEM | REF.:TPIT-MIDOR-T-00410
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-02-02_19-09 | 02/02/16 | CLIENT COMMENTS TO UNIT 31 - SP-0910-01/02_PA | REF.:TPIT-MIDOR-T-00390/00420 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00834 | 08/02/16
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-02-02_19-21 | 02/02/16 | CLIENT COMMENTS TO UNIT 38 - SP-1111-01_PA | REF.:TPIT-MIDOR-T-00486 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00809 | 08/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-03_07-09 | 03/02/16 | CLIENT COMMENTS TO UNIT 19 - DATA SHEETS | REF.:TPIT-MIDOR-T-0472
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-03_07-10 | 03/02/16 | CLIENT COMMENTS TO UNIT 02 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00237
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-02-03_07-11 | 03/02/16 | CLIENT COMMENTS TO UNIT 38 - SP-1111-01_PA | REF.:TPIT-MIDOR-T-00486 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00836 | 08/02/16
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-02-03_07-16 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - SP-0310-201_A | REF: TPIT-MIDOR-T-00216
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-02-03_07-17 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR PUMPS | REF.:TPIT-MIDOR-T-00087
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-03_07-18 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - CONTROL PHILOSOPHY | REF.:TPIT-MIDOR-T-00309
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-02-03_23-13 | 03/02/16 | CLIENT COMMENTS TO UNIT 04 - I/O LIST | REF.:TPIT-MIDOR-T-00491
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-02-03_23-14 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - PIPING MATERIAL CLASSES | REF.:TPIT-MIDOR-T-00501
Email | MIDOR | 00 | PACKAGES | MIDOR-TPIT-E-2016-02-03_23-21 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - SP-0310-201_A | REF: TPIT-MIDOR-T-00216
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-03_23-25 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - JOB SPECIFICATION | REF.:TPIT-MIDOR-T-00345
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2016-02-03_23-30 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS-0400-01 | REF.:TPIT-MIDOR-T-00031
Email | MIDOR | 00 | PVHE | MIDOR-TPIT-E-2016-02-03_23-31 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - SP-0610-103/SP-0710-001 | REF.:TPIT-MIDOR-T-00234/MIDOR-T-00152
Email | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-E-2016-02-03_23-32 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - SP-0110-001 | REF.:TPIT-MIDOR-T-00158
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-03_23-34 | 03/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS-1684-01 | REF.:TPIT-MIDOR-T-00495
Email | MIDOR | 17 | HEATERS AND BOILERS | MIDOR-TPIT-E-2016-02-05_08-54 | 05/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS-0110-01/HEATER FANS DS 17-SP-0110-05/06 | REF: TPIT-MIDOR-E-00788 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00788/TPIT-MIDOR-E-01056 DTD 04/03/2016 | 02/02/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-05_23-22 | 05/02/16 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SUBSTATION CLEARANCE | REF: TPIT-MIDOR-T-00019
Email | MIDOR | 00 | BUILDINGS | MIDOR-TPIT-E-2016-02-07_21-27 | 07/02/16 | CLIENT COMMENTS TO UNIT 00 - BUILDING CONSTRUCTION STANDARD | REF: TPIT-MIDOR-00572 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00841 | 09/02/16
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-02-07_21-27BIS | 07/02/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR SHELTERS | REF: TPIT-MIDOR-T-00535
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-08_09-24 | 08/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS | REF.:TPIT-MIDOR-E-0734-TPIT-MIDOR-T-0379 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02205 | 03/10/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-08_09-36 | 08/02/16 | CLIENT COMMENTS TO UNIT 22-23-56 ELECTRICAL CONSUMER LIST | REF: TPIT-MIDOR-T-475/476/477 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-0022 | 08/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-09_16-52 | 09/02/16 | CLIENT COMMENTS TO UNIT 54 - PROCESS DATA SHEETS | REF: TPIT-MIDOR-T-00521 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00848 | 10/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-09_17-02 | 09/02/16 | CLIENT COMMENTS TO UNIT 41 - DATA SHEET | REF: TPIT-MIDOR-T-00177
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-02-10_14-24 | 10/02/16 | CLIENT COMMENTS TO UNIT 22 - D/S FOR PUMPS | REF: TPIT-MIDOR-T-00599
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-02-10_14-48 | 10/02/16 | CLIENT COMMENTS TO UNIT 00 - QCP | REF: TPIT-MIDOR-T-00325
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-11_10-15 | 11/02/16 | CLIENT COMMENTS TO UNIT 00 - PROJECT PROCEDURE | REF: TPIT-MIDOR-T-00605
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-02-11_23-29 | 11/02/16 | CLIENT COMMENTS TO UNIT 20 - 2544-20-DW-0051-01-01_A | REF: TPIT-MIDOR-T-00071
Email | MIDOR | 17 | MACHINERY | MIDOR-TPIT-E-2016-02-12_11-43 | 12/02/16 | CLIENT COMMENTS TO UNIT 17 - D/S FOR PUMPS | REF: TPIT-MIDOR-T-00626
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-02-12_18-25 | 12/02/16 | CLIENT COMMENTS TO UNIT 00 - JSD-1501-01 REV. B | REF: TPIT-MIDOR-T-00407 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00881 | 15/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-14_23-12 | 14/02/16 | CLIENT COMMENTS TO NEW RSU UNIT 22 - PIDS | REF: TPIT-MIDOR-T-00550
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-15_07-07 | 15/02/16 | CLIENT COMMENTS TO UNIT 00 - JSD | REF.:TPIT-MIDOR-T-00606 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00963 | 25/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-15_07-08 | 15/02/16 | CLIENT COMMENTS TO UNIT 00 - JSD | REF.:TPIT-MIDOR-T-00606 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00963 | 25/02/16
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-02-15_07-10 | 15/02/16 | CLIENT COMMENTS TO UNIT 18 - 2544-18-DW-1980-01-01_B | REF.:TPIT-MIDOR-T-00404 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00963 | 25/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-15_11-10 | 15/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS | REF.:TPIT-MIDOR-T-00051 |  |  | TPIT-MIDOR-E-00945 | 23/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-16_14-30 | 16/02/16 | CLIENT COMMENTS TO UNIT 05-19 - DATA SHEETS | REF: TPIT-MIDOR-T-0531/0546/0565/0627
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-02-16_21-52 | 16/02/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR ANALYSER SYSTEM | REF: TPIT-MIDOR-T-00588
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-17_09-22 | 17/02/16 | CLIENT COMMENTS TO UNIT 08 - PROCESS DATA SHEET | REF: TPIT-MIDOR-T-00584
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-17_10-07 | 17/02/16 | CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF: TPIT-MIDOR-T-00399 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00945 | 23/02/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-17_11-03 | 17/02/16 | CLIENT COMMENTS TO UNIT 49 - MAIN ONE LINE DIAGRAM | REF: TPIT-MIDOR-T-00608 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02204 | 03/10/16
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-02-17_12-20 | 17/02/16 | CLIENT COMMENTS TO UNIT 20 - 2544-20-DW-0051-01-01_A | REF: TPIT-MIDOR-T-00071 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00903 | 17/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-17_14-20 | 17/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS | REF: TPIT-MIDOR-T-00495 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01299 | 04/04/16
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-02-18_09-02 | 18/02/16 | CLIENT COMMENTS TO UNIT 20 - 2544-20-DW-0051-01-01_A | REF: TPIT-MIDOR-T-00071/00070/00513 |  |  | TPIT-MIDOR-E-01044 | 03/03/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-20_08-26 | 20/02/16 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEET | REF: TPIT-MIDOR-T-00664 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00940 | 23/02/16
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-02-20_08-35 | 20/02/16 | CLIENT COMMENTS TO UNIT 22 - CIVIL DRAWING | REF: TPIT-MIDOR-T-00638
Email | MIDOR | 17 | PROCESS | MIDOR-TPIT-E-2016-02-20_08-55 | 20/02/16 | CLIENT COMMENTS TO UNIT 17 - D/S | REF: TPIT-MIDOR-T-00113 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01164 | 21/03/16
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-02-20_09-00 | 20/02/16 | CLIENT COMMENTS TO UNIT 00 - JSD-1510-01 | REF: TPIT-MIDOR-T-00309
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-02-20_19-28 | 20/02/16 | CLIENT COMMENTS TO UNIT 23 - D/S FOR PUMP | REF: TPIT-MIDOR-T-00658
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-02-21_20-27 | 21/02/16 | CLIENT COMMENTS TO UNIT 20 - PIPING AND INSTRUMENT DIAGRAMS | REF: TPIT-MIDOR-T-00636
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-22_12-31 | 22/02/16 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00715 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00939 | 23/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-22_12-31BIS | 22/02/16 | CLIENT COMMENTS TO UNIT 02 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00710 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00941 | 23/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-22_12-31TRIS | 22/02/16 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00714 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00937 | 23/02/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-22_12-40 | 22/02/16 | CLIENT COMMENTS TO UNIT 22 - MAIN CABLE ROUTING | REF.:TPIT-MIDOR-T-00680 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01023 | 02/03/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-22_12-41 | 22/02/16 | CLIENT COMMENTS TO UNIT 23 - MAIN CABLE ROUTING | REF.:TPIT-MIDOR-T-00681 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01022 | 02/03/16
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-02-22_14-08 | 22/02/16 | CLIENT COMMENTS TO UNIT 56 - FIRE AND GAS DETECTION | REF.:TPIT-MIDOR-T-00713
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-23_07-09 | 23/02/16 | CLIENT COMMENTS TO UNIT 21 - DRAWINGS | REF.:TPIT-MIDOR-T-00694 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00993 | 01/03/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-23_12-20 | 23/02/16 | CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00715 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00938 | 23/02/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-23_12-20BIS | 23/02/16 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00714
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-23_12-21 | 25/02/16 | CLIENT COMMENTS TO UNIT 02 - PROCESS DATA SHEET | REF.:TPIT-MIDOR-T-00710
Email | MIDOR | 00 | MATERIAL TECHNOLOGY | MIDOR-TPIT-E-2016-02-23_14-10 | 23/02/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR WELDING | REF.:TPIT-MIDOR-T-00684
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-24_21-28 | 24/02/16 | CLIENT COMMENTS TO UNIT 21 - DESCRIPTION LIST | REF.:TPIT-MIDOR-T-00748
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-02-25_09-25 | 25/02/16 | CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.:TPIT-MIDOR-T-00666
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-02-25_22-19 | 25/02/16 | CLIENT COMMENTS TO UNIT 21 - DRAWINGS | REF.:TPIT-MIDOR-T-00694 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-00993 | 01/03/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-25_22-49 | 25/02/16 | CLIENT COMMENTS TO UNIT 56 - MAIN CABLE ROUTING | REF.:TPIT-MIDOR-T-00728
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-02-25_22-50 | 25/02/16 | CLIENT COMMENTS TO UNIT 21 - ELECTRICAL CONSUMER LIST | REF.:TPIT-MIDOR-T-00756
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-26_09-05 | 26/02/16 | CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00718
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-02-26_09-06 | 26/02/16 | CLIENT COMMENTS TO UNIT 18 - PROCESS DATA SHEETS | REF.:TPIT-MIDOR-T-00717
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-02-26_12-28 | 26/02/16 | CLIENT COMMENTS TO UNIT 48 - INSTRUMENT BUILDING LAYOUT | REF.:TPIT-MIDOR-T-00723
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-02-27_15-16 | 27/02/16 | CLIENT COMMENTS TO UNIT 56 - STEEL STRUCTURE | REF.:TPIT-MIDOR-T-00754
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-02-27_15-50 | 27/02/16 | CLIENT COMMENTS TO UNIT 56 - CIVIL DRAWINGS | REF.:TPIT-MIDOR-T-00763
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-02-27_17-01 | 27/02/16 | CLIENT COMMENTS TO UNIT 56 - SEWER AND DRAINAGE SYSTEM | REF.:TPIT-MIDOR-T-00762
Email | MIDOR | 00 | BUILDINGS | MIDOR-TPIT-E-2016-02-29_08-53 | 29/02/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR AIR CONDITIONING | REF.:TPIT-MIDOR-T-00794
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-02-29_12-19 | 29/02/16 | CLIENT COMMENTS TO UNIT 08 - FIRE AND GAS LAYOUT | REF.:TPIT-MIDOR-T-00758
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-03-01_11-37 | 01/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FIRE FIGHTING | REF.:TPIT-MIDOR-T-00606 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01018 | 02/03/16
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-03-02_08-15 | 02/03/16 | CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.:TPIT-MIDOR-T-00666 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01020 | 02/03/16
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-03-02_09-28 | 02/03/16 | CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.:TPIT-MIDOR-T-00666 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01017 | 02/03/16
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-03-02_09-42 | 02/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR ANALYSER SYSTEM | REF.:TPIT-MIDOR-T-00588
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-03-02_17-47 | 02/03/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR PUMPS | REF.:TPIT-MIDOR-T-00087
Email | MIDOR | 00 | PACKAGES | MIDOR-TPIT-E-2016-03-03_04-43 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - 2544-00-MR-4190-102_A | REF.:TPIT-MIDOR-T-00674
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-03-03_09-06 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FIRE FIGHTING | REF.: TPIT-MIDOR-E-01018 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01032 | 03/03/16
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-03-03_10-26 | 03/03/16 | CLIENT COMMENTS TO UNIT 00 - JDS FIRE FIGHTING | REF.:TPIT-MIDOR-T-00606
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-03-06_11-44 | 06/03/16 | CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.:TPIT-MIDOR-T-00666 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01078 | 08/03/16
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-03-07_08-18 | 07/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FIRE FIGHTING | REF.: TPIT-MIDOR-E-01032 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | BUILDINGS | MIDOR-TPIT-E-2016-03-07_08-20 | 07/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR HVAC | REF.:TPIT-MIDOR-T-00915
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-03-09_21-24 | 09/03/16 | CLIENT COMMENTS TO UNIT 0C - D/S FIREFIGHTING | REF.:TPIT-MIDOR-T-00726
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-03-09_22-22 | 09/03/16 | CLIENT COMMENTS TO UNIT 36 - PIPING AND INSTRUMENT DIAGRAM) | REF.: TPIT-MIDOR-T-00864
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-03-10_14-14 | 10/03/16 | CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.:TPIT-MIDOR-T-00666
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-03-11_11-18 | 11/03/16 | CLIENT COMMENTS TO TCF'S AREAS AVAILABILITY ON FREE ZONE | REF.:TPIT-MIDOR-T-01200
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-03-15_08-11 | 15/03/16 | CLIENT COMMENTS TO UNIT 19 - FIREFIGHTING LAYOUT | REF.:TPIT-MIDOR-T-01040
Email | MIDOR | 17 | HSE DESIGN | MIDOR-TPIT-E-2016-03-15_08-12 | 15/03/16 | CLIENT COMMENTS TO UNIT 17 - FIREFIGHTING LAYOUT | REF.:TPIT-MIDOR-T-01041
Email | MIDOR | 17 | HSE DESIGN | MIDOR-TPIT-E-2016-03-15_11-09 | 15/03/16 | CLIENT COMMENTS TO UNIT 17 - FIREFIGHTING LAYOUT | REF.:TPIT-MIDOR-T-00929
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-03-16_18-45 | 16/03/15 | CLIENT COMMENTS TO UNIT 00 - JSS AND JSD SPECIFICATIONS | REF.: TPIT-MIDOR-T-00259
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-03-16_22-07 | 16/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FIRE FIGHTING | REF.: TPIT-MIDOR-E-00903/1044
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-03-23_20-42 | 23/03/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR MACHINERY | REF.:TPIT-MIDOR-T-00900
Email | MIDOR | 00 | CIVIL | MIDOR-TPIT-E-2016-03-24_10-17 | 24/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD FOR FOUNDATION WORKS | REF.:TPIT-MIDOR-T-01194
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-03-31_09-47 | 31/03/16 | CLIENT COMMENTS TO UNIT 00 - JSD/JSS STATUS AS OF 15-03-2016 |  | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01312 | 06/04/16
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-04-01_11-54 | 01/04/16 | CLIENT COMMENTS TO UNIT 00 JSD COMMUNICATION STYSTEM DESIGN SPECIFICATION | REF: TPIT-MIDOR-T-00976 | TPIT RESPONSE REQUIRED |  | 2544-00-JSD-1530-01-0-CRS-REPLY_0 | 15/04/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-04-03_02-36 | 05/04/16 | CLIENT COMMENTS TO UNIT U&O P&ID REVIEW STATUS | REF.:TPIT-MIDOR-T-01255/1028/867/865 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-01342/2544-41-PID-0021-A-CRS-REPLY_0/2544-44-PID-0021-A-CRS-REPLY_0/2544-46-PID-0021-A-CRS-REPLY_0
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-04-09_06-53 | 09/02/16 | CLIENT COMMENTS TO UNIT 51 - PROCESS INSTRUMENT DIAGRAMS | REF.:TPIT-MIDOR-T-00920/00921/00922
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-04-13_10-13 | 13/04/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR PIPING | REF.:TPIT-MIDOR-T-01405
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-04-24_13-07 | 24/04/16 | CLIENT COMMENTS TO UNIT 00 - ELECTRICAL CONSUMER LIST | REF.:TPIT-MIDOR-T-01531 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-2016-04-29_15-58 | 29/04/16
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-04-26_20-33 | 26/04/16 | CLIENT COMMENTS TO UNIT 00 - JSS FOR PIPING SUPPORTS | REF.:TPIT-MIDOR-T-01501
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-05-08_22-16 | 08/05/16 | CLIENT COMMENTS TO UNIT 00 - JSD FIRE FIGHTING | REF.: TPIT-MIDOR-T-01457
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-05-11_01-10 | 31/05/16 | CLIENT COMMENTS TO AIR AIR COOLER PROCESS DATA SHEET UNIT 18 | REF: TPIT-MIDOR-T-01637 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-05-11_01-12 | 21/05/16 | CLIENT COMMENTS TO CONDENSER PROCESS DATA SHEET UNIT 20 | REF: TPIT-MIDOR-T-01637 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-05-16_19-10 | 16/05/16 | CLIENT COMMENTS TO UNIT 21 - PROCESS DATA SHEET | REF: 2544-21-SP-0910-02_02
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-05-17_14-17 | 17/05/16 | CLIENT COMMENTS TO UNIT 21 - DATA SHEET | REF: TPIT-MIDOR-T-01567
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-05-29_12-09 | 29/05/16 | CLIENT COMMENTS TO UNIT 21 - PROCESS DATA SHEET | REF: 2544-21-SP-0910-01-PC-CRS-REPLY_0
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-05-29_12-33 | 29/05/16 | CLIENT COMMENTS TO UNIT 21 - PROCESS DATA SHEET | REF: TPIT-MIDOR-T-01806
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-05-31_13-04 | 31/05/16 | CLIENT COMMENTS TO AIR COMPRESSOR UPGRADE 41K0 -C911630 & C911631-1, 2 / MIDOR / EGYPT / CONTROL PANEL UP-GRADE | REF: ID-00535 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-06-02_08-31 | 02/06/16 | CLIENT COMMENTS TO UNIT 34 - PIPING AND INSTRUMENT DIAGRAMS | REF.: TPIT-MIDOR-T-01854
Email | MIDOR | 17 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-06-08_12-31 | 08/06/16 | CLIENT COMMENTS TO UNIT 17 - UNIT 17 - LABORATORY SCHEDULE | REF: TPIT-MIDOR-T-01957 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-06-12_12-55 | 12/06/16 | CLIENT COMMENTS TO UNIT 00 BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | REF: 2544-00-JSD-0001-02-A-CRS-REPLY_2
Email | MIDOR | 00 | PIPING | MIDOR-TPIT-E-2016-07-13_08-12 | 13/07/16 | CLIENT COMMENTS TO TIE INS- 28 JUNE 2016.XLSX | REF.: TPIT-MIDOR-T-02183/2185/2186
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-07-19_11-14 | 19/07/16 | CLIENT COMMENTS TO TEST METHODS AND SAMPLING SCHEDULE SOLVENT DEAPSHALTING UNIT | REF: TPIT-MIDOR-T-02134
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2016-07-21_13-43 | 21/07/16 | CLIENT COMMENTS TO REQUEST FOR INQUIRY INTEGRITY ASSESSMENT OF EXISTING FACILITIES | REF: TPIT-MIDOR-T-02133
Email | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-E-2016-07-24_15-17 | 24/07/16 | CLIENT COMMENTS TO ENVIRONMENTAL PROTECTION DESIGN CRITERIA | REF: TPIT-MIDOR-T-02238 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02002 | 28/07/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-07-25_10-49 | 25/07/16 | CLIENT COMMENTS TO PROCESS DATA SHEET FOR PRODUCTS CONDENSER 04-E-02 | REF: TPIT-MIDOR-T-02283
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-07-26_17-04 | 26/07/16 | CLIENT COMMENTS TO UNIT 24 - DESIGN BASIS | REF: TPIT-MIDOR-T-02147 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02009 | 29/07/16
Email | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-E-2016-07-31_08-43 | 31/07/16 | CLIENT COMMENTS TO HEIGHT RESTRICTION BARRIER LOCATION PLAN AND DETAIL | REF: TPIT-MIDOR-T-02188
Email | MIDOR | 00 | START UP | MIDOR-TPIT-E-2016-08-02_12-19 | 02/08/16 | CLIENT COMMENTS TO PRECOMMISSIONING COMMISSIONING STAR-UP AND INITIAL OPERATION EXECUTION PLAN | REF: TPIT-MIDOR-T-02280 | OWNER RESPONSE REQUIRED |  | 2544-00-PP-901-A-CRS-REPLY_0 | 08/08/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-08-08_07-39 | 08/08/16 | CLIENT COMMENTS TO MAIN ONE LINE DIAGRAM | REF: TPIT-MIDOR-T-02348 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02052 | 08/08/16
Email | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-E-2016-08-08_07-40 | 08/08/16 | CLIENT COMMENTS TO KEY SINGLE LINE DIAGRAM | REF: TPIT-MIDOR-T-02347 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02053 | 08/08/16
Email | MIDOR | 00 | MACHINERY | MIDOR-TPIT-E-2016-08-10_21-28 | 10/08/16 | CLIENT COMMENTS TO TECHNICAL BID TABULATION ROTARY SCREW PUMP | REF: TPIT-MIDOR-T-02392 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-E-02067 | 11/08/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-08-30_13-44 | 30/08/16 | CLIENT COMMENTS TO MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE - REVAMPED HYDROCRACKING | REF: MIDOR-TPIT-T-00002 | TPIT RESPONSE REQUIRED |  | 2544-08-NM-0020-01-B-CRS-REPLY_0 TPIT-MIDOR-E-02091 | 31/08/16
Email | MIDOR | 00 | PROCESS | MIDOR-TPIT-E-2016-08-30_13-44_BIS | 30/08/16 | CLIENT COMMENTS TO MEMORANDUM - P&IDS PROCESS MARK-UP - FINAL ISSUE FOR EARLY WORKS AND OBE - REVAMPED HYDROCRACKING | REF: MIDOR-TPIT-T-00003 | TPIT RESPONSE REQUIRED |  | 2544-08-NM-0020-01_B-CRS-REPLY_1 | 31/08/16
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2016-10-17_10-37 | 17/10/16 | CLIENT COMMENTS TO UNIT 34 - PIPING AND INSTRUMENT DIAGRAMS | REF.: TPIT-MIDOR-T-00738 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-E-2017-05-29_10-52 | 29/05/17 | CLIENT COMMENTS TO DEMOLISHING INSTR IN U 11 | REF.: TPIT-MIDOR-T-02577 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-E-2017-10-27_15-14 | 27/10/17 | CLIENT COMMENTS TO ITEM INDEX REV 4 UNIT 11 | REF.: TPIT-MIDOR-T-02621 | TPIT RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00217 | 16/11/15 | RESPONSE CLIENT COMMENTS TO ELECT GENERAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-15_08-31 | OWNER RESPONSE REQUIRED | 20/11/15 | MIDOR-TPIT-E-2015-11-18_20-58 | 18/11/15
Email | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00259 | 19/11/15 | RESPONSE CLIENT COMMENTS TO UNIT 17 - PROCESS DATA SHEET | REF.: MIDOR-TPIT-E-2015-11-19_10-18
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00303 | 24/11/15 | TPIT REPLY TO CLIENT COMMENTS TO SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-15_14-08
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00342 | 27/11/15 | RESPONSE TO CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-21_08-30 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2015-11-30_08-17 | 30/11/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00346 | 27/11/15 | RESPONSE CLIENT COMMENTS TO UNIT 00 - TYPICAL INSTALLATION STANDARDS | REF.: MIDOR-TPIT-E-2015-11-26_06-46 | OWNER RESPONSE REQUIRED | 29/11/15 | MIDOR-TPIT-E-2015-11-30_08-26BIS | 30/11/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00352 | 27/11/15 | TPIT REPLY TO CLIENT COMMENTS TO SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-18_21-19
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00353 | 01/12/15 | RESPONSE TO CLIENT COMMENTS TO MATERIAL REQUISITION 0411-101 | REF.: MIDOR-TPIT-E-2015-11-18_21-17 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2015-12-30_06-31 | 30/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00357 | 26/11/15 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS FOR PACKAGE UNIT | REF.: MIDOR-TPIT-E-2015-11-26_20-44
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00365 | 30/11/15 | RESPONSE CLIENT COMMENTS TO PLOT PLANS (MIDOR DOCUMENTS CODING & NUMBERING SISTEM) | REF.: MIDOR-TPIT-E-2015-11-29_08-31 | OWNER RESPONSE REQUIRED | 01/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00369 | 30/11/15 | RESPONSE CLIENT COMMENTS TO PLOT PLANS | REF.: MIDOR-TPIT-E-2015-11-26_12-50
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00386 | 01/12/15 | RESPONSE CLIENT COMMENTS TO ELECT GENERAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-18_20-58 | OWNER RESPONSE REQUIRED | 02/12/15 | MIDOR-TPIT-E-2015-12-03_06-46 | 03/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00387 | 01/12/15 | RESPONSE CLIENT COMMENTS TO ELECT SPECIFICATION 00-JSS-1654-01 | REF.: MIDOR-TPIT-E-2015-11-28_10-51
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00388 | 01/12/15 | RESPONSE CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-29_08-29 | OWNER RESPONSE REQUIRED | 04/12/15 | MIDOR-TPIT-E-2015-12-03_06-43 | 03/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00389 | 01/12/15 | RESPONSE CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-29_08-30
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00406 | 03/12/15 | RESPONSE CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-11-28_07-31 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2015-12-07_08-52 | 07/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00413 | 03/12/15 | RESPONSE CLIENT COMMENTS TO UNIT 00 - TYPICAL INSTALLATION STANDARDS | REF.: MIDOR-TPIT-E-2015-11-30_08-26BIS | OWNER RESPONSE REQUIRED | 08/12/15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00445 | 10/11/15 | RESPONSE CLIENT COMMENTS TO GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.: MIDOR-TPIT-E-2015-11-22_11-39...
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00508 | 16/12/15 | RESPONSE CLIENT COMMENTS TO ELECT GENERAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-12-03_06-46
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00533 | 18/12/15 | TPIT REPLY TO CLIENT COMMENTS TO MATERIAL REQUISITION 2544-00-MR-0511-001 | REF.: MIDOR-TPIT-E-2015-12-15_09-41
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00581 | 07/01/16 | RESPONSE CLIENT COMMENTS TO UNIT 00 - ELECTRICAL SPECIFICATION | REF.:MIDOR-TPIT-E-2015-12-07_08-52/T-072
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00591 | 08/01/15 | RESPONSE CLIENT COMMENTS TO UNIT 00 - JSD | REF.: MIDOR-TPIT-E-2016-01-03_09-16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00606 | 27/12/15 | CLIENT COMMENTS TO MACHINERY PROJECT SPECIFICATION | REF.: MIDOR-TPIT-E-2015-12-27_20-27 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-01-25_19-24 | 25/01/16
Email | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00607 | 12/01/15 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 - COLUMN DRAWINGS | REF.: MIDOR-TPIT-E-2015-12-30_14-02
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00608 | 12/01/15 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2015-12-30_10-43BIS | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-01-14_06-53 | 14/01/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00626 | 14/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - DESIGN SPECIFICATION | REF.: MIDOR-TPIT-E-2015-12-06_09-37
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00628 | 14/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - BUILDING LIST | REF.: MIDOR-TPIT-E-2016-01-13_13-15
Email | MIDOR | 47 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00654 | 18/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 47 - DETAILED PLOT PLAN | REF.: MIDOR-TPIT-E-2016-01-14_09-00
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00675 | 19/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - GENERAL SPECIFICATION | REF.: MIDOR-TPIT-E-2015-12-08_12-01 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-01-22_07-34 | 22/01/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00678 | 20/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-01-14_06-53
Email | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00683 | 20/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2015-12-14_07-24
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00687 | 20/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 CIVIL DRAWINGS | REF.: MIDOR-TPIT-E-2016-01-19_07-08
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00697 | 21/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 37 - PROCESS DATA SHEET | REF.: MIDOR-TPIT-E-2015-12-25_15-46
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00698 | 21/01/16 | TPIT REPLY TO CLIENT COMMENTS TO PROCESS DATA SHEET | REF.: MIDOR-TPIT-E-2016-01-03_09-17 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-01-22_21-16 | 22/01/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00699 | 21/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 37 - PROCESS DATA SHEET | REF.: MIDOR-TPIT-E-2015-12-25_15-41
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00709 | 22/01/16 | TPIT REPLY TO CLIENT COMMENTS TO GENERAL SPECIFICATION | REF.: MIDOR-TPIT-E-2016-01-22_07-34
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00734 | 26/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS | REF.: MIDOR-TPIT-E-2016-01-26_09-13 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-02-08_09-24 | 08/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00741 | 26/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - PIPING MATERIAL CLASSES | REF.: MIDOR-TPIT-E-2016-01-15_08-47
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00760 | 28/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSD | REF.: MIDOR-TPIT-E-2016-01-20_08-15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00767 | 29/01/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 18 - FIRE AND GAS LAYOUT | REF.:MIDOR-TPIT-E-2016-01-27_13-24
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00768 | 29/01/16 | TPIT REPLY TO CLIENT COMMENTS TO AUXILIARY STEAM BOILERS DESIGN/GENERAL SUPPLY RULES FOR FIRED HEATERS | REF.: MIDOR-TPIT-E-2015-11-18_21-15
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00783 | 01/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - MATERIAL REQUISITION | REF.:MIDOR-TPIT-E-2016-01-13_08-46
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00787 | 02/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-02-01_06-56
Email | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00788 | 02/02/16 | TPIT REPLY TO MIDOR COMMENTS TO 2544-00-JSS-0110-01/HEATER FANS DS - UNIT 17-18-19-20 - MR 0110-001/0110-202 | REF: MIDOR-TPIT-E-2016-02-05_08-54 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-02-05_08-54 | 05/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00798 | 03/02/16 | TPIT REPLY TO CLIENT COMMENTS TO FIRE FIGHTING SPECIFICATION | REF.: MIDOR-TPIT-E-2015-12-20_16-38
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00809 | 08/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 38 - SP-1111-01_PA | REF.: MIDOR-TPIT-E-2016-02-02_19-21
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00811 | 04/02/16 | BIDDER LIST - FINAL ISSUE SYGNED BY MIDOR/TPIT - DISCIPLINE PROCUREMENT
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00814 | 05/02/16 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL SPECIFICATION FOR PRECAST CONCRETE | REF.: MIDOR-TPIT-E-2016-01-14_13-34
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00820 | 08/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 19 - DATA SHEET 19-H-01 | REF: MIDOR-TPIT-E-2016-02-03_07-09
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00822 | 08/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 22-23-56 ELECTRICAL CONSUMER LIST | REF.: MIDOR-TPIT-E-2016-02-08_09-36
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00834 | 08/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 31 - SP-0910-01/02_PA | REF.: MIDOR-TPIT-E-2016-02-02_19-09
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00836 | 08/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 38 - SP-1111-01_PA | REF.: MIDOR-TPIT-E-2016-02-03_07-11
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00837 | 08/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 46-PID-0031-068-01 | REF.: MIDOR-TPIT-E-2016-02-08_08-11
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00841 | 09/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - BUILDING CONSTRUCTION STANDARD | REF.: MIDOR-TPIT-E-2016-02-07_21-27
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00848 | 10/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 54 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-02-09_16-52
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00874 | 15/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS | REF.: MIDOR-TPIT-E-2016-02-01_11-13 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-02-17_14-20 | 17/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00881 | 15/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSD-1501-01_B - JOB SPECIFICATION FOR DESIGN FOR INSTRUMENTATION NUMBERING | REF.: TPIT-MIDOR-T-00407
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00887 | 16/02/16 | TPIT REPLY TO CLIENT COMMENTS TO MAJOR UNDERGROUND UNIT 18 -20 | REF.: MIDOR-TPIT-E-2016-01-19_07-45
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00903 | 17/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - 2544-20-DW-0051-01-01_A | REF.: MIDOR-TPIT-E-2016-02-17_12-20 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-02-18_09-02 MIDOR-TPIT-E-2016-03-16_22-07 DTD 16/03/2016 | 18/02/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00921 | 22/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 - PROCESS DATA SHEET | REF.: MIDOR-TPIT-E-2015-12-29_14-13
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00922 | 22/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 22 - PROCESS DATA SHEET | REF.: MIDOR-TPIT-E-2015-12-29_14-12
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00936 | 23/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2015-12-25_15-28BIS
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00937 | 23/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 05 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-02-22_12-31TRIS
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00938 | 23/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-02-23_12-20
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00939 | 23/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-02-22_12-31
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00940 | 23/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 20 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-02-20_08-26
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00941 | 23/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 02 - PROCESS DATA SHEETS | REF.: MIDOR-TPIT-E-2016-02-22_12-31BIS
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00945 | 23/02/16 | TPIT REPLY TO CLIENT COMMENTS TO MACHINERY PROJECT SPECIFICATIONS | REF.:
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00963 | 25/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSD FIRE FIGHTING | REF.: MIDOR-TPIT-E-2016-02-15_07-07 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-03-01_11-37 | 01/03/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00990 | 29/02/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - MACHINERY JSS | REF.:MIDOR-TPIT-E-2016-02-03_07-17
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00992 | 01/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 15 - ELECTRICAL LOAD SUMMARY | REF.: MIDOR-TPIT-E-2016-01-12_11-49
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00993 | 01/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 - DRAWINGS | REF.: MIDOR-TPIT-E-2016-02-23_07-09
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00994 | 01/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 PDS 0411/0480 | REF.: MIDOR-TPIT-E-2016-01-03_09-18
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-00995 | 01/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 21 PDS 0811 | REF.: MIDOR-TPIT-E-2016-01-03_09-17BIS
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01012 | 01/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.: MIDOR-TPIT-E-2016-02-25_09-25 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-03-02_08-15 MIDOR-TPIT-E-2016-03-02_09-28 | 02/03/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01017 | 02/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.: MIDOR-TPIT-E-2016-03-02_09-28 | OWNER RESPONSE REQUIRED | 06/03/16 | MIDOR-TPIT-E-2016-03-06_11-44 | 06/03/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01018 | 02/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSD FIRE FIGHTING | REF.: MIDOR-TPIT-E-2016-03-01_11-37 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-03-03_09-06 | 03/03/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01020 | 02/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.: TPIT-MIDOR-T-00666
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01022 | 02/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 23 - MAIN CABLE ROUTING | REF.: TPIT-MIDOR-T-00681
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01023 | 02/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 22 - MAIN CABLE ROUTING | REF.: TPIT-MIDOR-T-00680
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01032 | 03/03/16 | TPIT REPLY TO CLIENT COMMENTS TO 00 JSD FIRE FIGHTING | REF.: MIDOR-TPIT-E-2016-03-03_09-06 | TPIT RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-03-07_08-18 | 07/03/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01044 | 03/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - 2544-00-PP-126_A AND UNIT 20 PLOT PLAN | REF.: TPIT-MIDOR-T-00513 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-03-16_22-07 | 16/03/16
Email | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01056 | 04/03/16 | TPIT FINAL REPLY TO MIDOR COMMENTS TO 2544-00-JSS-0110-01/HEATER FANS DS - UNIT 17-SP-0110-05/06 | REF: MIDOR-TPIT-E-2016-02-05_08-54
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01078 | 08/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - PLOT PLAN | REF.: MIDOR-TPIT-E-2016-03-06_11-44 | OWNER RESPONSE REQUIRED | 13/03/16 | MIDOR-TPIT-E-2016-03-10_14-14 | 10/03/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01163 | 21/03/16 | TPIT REPLY TO CLIENT COMMENTS TO SPECIAL PURPOSE STEAM TURBINE | REF.: 2544-00-JSS-1112-01-2-CRS_0
Email | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01164 | 21/03/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 17 - D/S | REF.: MIDOR-TPIT-E-2016-02-20_08-55
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01188 | 23/03/16 | TPIT REPLY TO CLIENT COMMENTS TO JSS & JSD TO BE FINALIZED BEFORE SIGN | REF:CRS JSS & JSD FINALIZED BEFORE SIGN
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01202 | 23/03/16 | TPIT REPLY TO CLIENT COMMENTS TO JSS & JSD TO BE FINALIZED BEFORE SIGN | REF: TPIT-MIDOR-E-01188
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01255 | 03/04/16 | TPIT REPLY TO CLIENT COMMENTS TO U&O P&ID REVIEW STATUS | REF: MIDOR-TPIT-E--2016-4-03_02-36 | OWNER RESPONSE REQUIRED |  |  | 03/04/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01292 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO PLOT PLANS | REF: TPIT-MIDOR-E-01188
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01299 | 04/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS | REF.: TPIT-MIDOR-E-00874 | OWNER RESPONSE REQUIRED | 06/04/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01303 | 05/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS-6300-02/03/04/05 |  | OWNER RESPONSE REQUIRED | 07/04/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01312 | 06/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSD FOR PAINTING |  | OWNER RESPONSE REQUIRED | 08/04/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01461 | 22/04/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS | REF.: TPIT-MIDOR-E-01299 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-04-24/2544-00-JSS-1684-01-A-CRS_5 | 24/04/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01694 | 30/05/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS | REF.: TPIT-MIDOR-T-01253/01848 | OWNER RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01732 | 06/06/16 | TPIT REPLY TO (UNIT 00 - MACHINERY 2544-00-JSS-0940-01_0) FOR PROJECT 2544-DELAY | REF.:T-01410/2544-00-JSS-0940-01-0-CRS_0
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01770 | 10/06/16 | TPIT REPLY TO UNIT 02 PROCESS DATA SHEET FOR STRIPPER - TRAYS AND INTERNALS 02-IT-01 | REF.:T-01897/2544-02-SP-0570-01-PB-CRS_0
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01825 | 17/06/16 | TPIT REPLY TO CLIENT COMMENTS TO AS BUILT DOCUMENTATION PROCEDURE | REF.:T-01253/2544-00-PP-120-A-CRS_1
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01826 | 17/06/16 | TPIT REPLY TO CLIENT COMMENTS TO AS BUILT DOCUMENTATION PROCEDURE | REF.:T-01253/2544-00-PP-120-A-CRS_2
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-01859 | 27/06/16 | TPIT REPLY TO UNIT 55 - PIPING AND INSTRUMENT DIAGRAMS | REF.:2544-55-PID-0021-A-CRS_0
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02002 | 28/07/16 | TPIT REPLY TO ENVIRONMENTAL PROTECTION DESIGN CRITERIA | REF.: MIDOR-TPIT-E-2016-07-24_15-17
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02003 | 28/07/16 | TPIT REPLY TO UNIT 54 - PIPING AND INSTRUMENT DIAGRAMS | REF.:2544-55-PID-0021-A-CRS_1
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02009 | 28/07/16 | TPIT REPLY TO UNIT 24 SOUR WATER STRIPPER UNIT DESIGN BASIS | REF.:MIDOR-TPIT-E-2016-07-26_17-04
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02052 | 08/08/16 | TPIT REPLY TO UNIT 49 - MAIN ONE LINE DIAGRAM | REF.: MIDOR-TPIT-E-2016-08-08_07-39
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02053 | 08/08/16 | TPIT REPLY TO UNIT 00 - KEY SINGLE LINE DIAGRAM | REF.: MIDOR-TPIT-E-2016-08-08_07-40
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02067 | 11/08/16 | TPIT REPLY TO CLIENT COMMENTS TO TECHNICAL BID TABULATION ROTARY SCREW PUMP | REF.: MIDOR-TPIT-E-2016-08-10_21-28
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02083 | 30/08/16 | TPIT REPLY TO CLIENT COMMENTS TO PID UNIT 13 - SULPHUR RECOVERY UNIT | REF.: 2544-13-PID-0021-001-01-A-CRS_0
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02108 | 09/09/16 | TPIT REPLY TO CLIENT COMMENTS ITB MMS-MACHINE MONITORING SYSTEM MR | REF.:MIDOR-TPIT-T-00023
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02141 | 19/09/16 | TPIT REPLY TO CLIENT COMMENTS ON CRS FOR FIRE FIGHTING AND PROOFING SPECIFICATION | REF.: MIDOR-TPIT-T-00004
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02144 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS TO RFQ 1682-01 ELECRICAL HEAT TRACING SYSTEM | REF.: MIDOR-TPIT-T-00028 | OWNER RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02162 | 20/09/16 | TPIT REPLY TO CLIENT COMMENTS TO MR FOR CATHODIC PROTECTION SYSTEM (OBE) | REF.: MIDOR-TPIT-T-00031
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02163 | 23/09/16 | TPIT REPLY TO CLIENT COMMENTS TO INTERNALS FOR REACTORS (REVAMP) | REF.: MIDOR-TPIT-T-00035
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02189 | 30/09/16 | TPIT REPLY TO CLIENT COMMENTS TO PIPING MATERIAL CLASS SPECIFICATION | REF: MIDOR-TPIT-E-0026/TPIT-MIDOR-T-2121 | OWNER RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02204 | 03/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 49 - MAIN ONE LINE DIAGRAM | REF:T-0608/MIDOR-TPIT-E-2016-02-17_11-03 | OWNER RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02205 | 03/10/16 | TPIT REPLY TO CLIENT COMMENTS TO UNIT 00 - JSS | REF:T-0379/MIDOR-TPIT-E-2016-02-08_09-24 | OWNER RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-02232 | 06/10/16 | TPIT REPLY TO CLIENT COMMENTS TO - JSS-4261-01 - JSS FOR MECHANICAL AGITATORS
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-03582 | 2018-01-30 | TPIT REPLY TO CLIENT COMMENTS TO - MS-6850-51_CRS_0 |  | OWNER RESPONSE REQUIRED
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-2016-01-28_15-59 | 25/01/16 | TPIT REPLY TO CLIENT COMMENTS TO MACHINERY PROJECT SPECIFICATION | REF.: TPIT-MIDOR-T-00562 | OWNER RESPONSE REQUIRED |  | MIDOR-TPIT-E-2016-01-29_12-17 | 29/01/16
Email | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-E-2016-04-29_15-58 | 29/04/16 | TPIT REPLY TO CLIENT COMMENTS ELECTRICAL CONSUMERS LIST | REF.: 1531/MIDOR-TPIT-E-2016-04-24_13-07 | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00002 | 06/03/16 | PRELIMINARY CONSTRUCTABILITY WORKSHOP | REF.: TPIT-MIDOR-L-00010 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00003 | 06/03/16 | TECHNICAL CONTINGENCIES QUANTIFICATION MEETING 1 "RISK OPPORTUNITY ASSESMENT" | REF.: TPIT-MIDOR-L-00012 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00004 | 06/03/16 | MIDOR'S LIBRARY FILE LIST | ELECTRONIC FILE ON HOLD | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00005 | 16/03/16 | RISK OPPORTUNITY ASSESMENT WORKSHOP | REF.:TPIT-MIDOR-L-00014 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00006 | 19/03/16 | INTEGRATED TEAM PMC MIDOR | REF. : TPIT- MIDOR-L-00022 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00007 | 19/05/16 | CONTRACTOR'S REQUEST OF C.O NO 1 TPIT-MIDOR-L-0024 | REF.: TPIT- MIDOR-L-00023 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00008 | 19/05/16 | REQUEST OF C.O NO 2, 3 AND 4 | REF.: TPIT- MIDOR-L-00025/26/27 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00009 | 05/06/16 | GUARANTEED FUEL EFFICIENCY ON HETHER 08-H-01 | REF.:TPIT-MIDOR-L-00029 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00010 | 05/06/16 | STRUCTURAL MECHANICAL/CIVIL VERIFICATION OF REVAMPED EQUIPMENT | REF.: TPIT-MIDOR-L-00030 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00011 | 10/07/16 | MULTI HEADS DOSING PUMPS IN MULTIPLE SERVICE OR MULTI INJECTION POINTS | REF.: TPIT-MIDOR-L-00028 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00012 | 10/07/16 | CHANGE ORDER FOR DCC SERVICES FOR MIDOR PMC IN TPIT OFFICES | REF.: TPIT-MIDOR-L-00023 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00013 | 10/07/16 | REPLY TO MIDOR CEO CLARIFICATION ON APRIL PROGRESS | REF.:TPIT-MIDOR-L-00038 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00014 | 10/07/16 | QRA | REF.:TPIT-MIDOR-L-00045 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00015 | 10/07/16 | UNIT 21 NITROGEN RECIRCULATION COMPRESSOR MAINTENANCE | TPIT-MIDOR-L-00037 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00016 | 10/07/16 | PMC COMMENTS TO CONTRACTOR'S SPECIFICATIONS (JSS/JSD) | REF.: TPIT-MIDOR-L-00042 | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00017 | 25/07/16 | PROJECT CORRESPONDENCE, DOCUMENT TRANSMITTAL AND APPROVAL |  | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00018 | 11/08/16 | PMC COMMENTS TO CONTRACTOR'S SPECIFICATIONS (JSS/JSD)
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00019 | 11/08/16 | PROJECT CORRESPONDENCE, DOCUMENT TRANSMITTAL AND APPROVAL | REF.: TPIT-MIDOR-L-0061/L-MIDOR-TPIT-017 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00020 | 11/08/16 | MINIMUM REQUIREMENTS ON TPITS FROM OWNER | REF.: TPIT-MIDOR-L-00055 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00020 BIS | 11/08/16 | QRA AND SIMOPS |  | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00021 | 05/10/16 | MODULAR LPG MEROX UNIT |  | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00022 | 05/10/16 | CHANGE ORDER REQUEST N. 06 FOR QRA AND SIMOPS SUBCONTRACT | REF. : TPIT- MIDOR-L-00064 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00023 | 05/10/16 | CAPEX MITIGATION | REF. : TPIT-MIDOR-L-00059/MOM-00075 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00024 | 05/10/16 | STRUCTURAL/MECHANICAL/CIVIL VERIFICATION OF REVAMPED EQUIPMENT | REF.: TPIT- MIDOR-L-00057 | TPIT RESPONSE REQUIRED |  | TPIT-MIDOR-L-00069 | 12/10/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00025 | 13/10/16 | CONTRACTOR'S INVOICES | REF.: TPIT-MIDOR-L-00067 | CLOSED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00026 | 20/11/16 | CRS'S ANALYSIS | REF.: TPIT-MIDOR-L-00077 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00027 | 20/11/16 | CO FOR DCC SERVICES FOR MIDOR PMC IN TP OFFICE AUG SEPT 2016 | TPIT-MIDOR-L-00054 | CLOSED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00028 | 20/11/16 | STRUCTURAL/MECHANICAL/CIVIL VERIFICATIONS OF REVAMPED EQUIPMENT | REF.: TPIT-MIDOR-L-00069 | CLOSED |  | TPIT-MIDOR-L-00105 | 20/11/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00030 | 26/11/16 | REQUEST OF UPGRADE OF EXISTING UNIT 51 |  | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00031 | 26/11/16 | MODULAR LPG TREATMENT SYSTEM | REF.: TPIT-MIDOR-L-00074 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00033 | 22/05/17 | CHANGE ORDER REQUEST N.07 REV 02 MODULAR LPG TREATMENT UNIT | REF.: TPIT-MIDOR-L-00094 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00034 | 31/07/17 | CHANGE ORDER REQUEST N. 7 REV. 3 FOR MODULAR LPG TREATMENT UNIT | REF. : TPIT- MIDOR-L-00100 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00036 | 2018-03-04 | CHANGE ORDER N.12 FOR DCC SERVICES FOR MIDOR PMC IN TECHNIPFMC PERMISES IN ROME FEB-APR 2018 | REF. : TPIT- MIDOR-L-00112 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00037 | 2018-05-16 | CHANGE ORDER N.13 FOR DCC SERVICES FOR MIDOR PMC IN TECHNIPFMC PERMISES IN ROME MAY 2018 | REF. : TPIT- MIDOR-L-00115 | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | L-MIDOR-TPIT-00038 | 2018-07-25 | MIDOR NEW LEGAL ADDRESS | REF. | TPIT RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00001 | 30/10/15 | INVOICE TRANSMISSION
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00002 | 04/11/15 | NEGOTIATION OF EPC CONTRACT MEETING IN ROME 16-20TH NOVEMBER 2015 |  | OWNER RESPONSE REQUIRED | 05/11/15
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00003 | 10/11/15 | INVOICE TRANSMISSION MILESTONE 2
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00004 | 10/11/15 | INVOICE TRANSMISSION MILESTONE 2
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00005 | 12/11/15 | OPEN BOOK ESTIMATE: REFERENCE EXCHANGE RATES |  | OWNER RESPONSE REQUIRED | 19/11/15
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00006 | 09/12/15 | DESIGN CAPACITY OF NEW HPU INIT 21
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00007 | 15/01/16 | ENPPI SUBCONTRACT: VARIATION OF PAYMENT TERMS AND CONDITION | REF.: | CLOSED | 19/01/16 | L-MIDOR-TPIT-00001 | 16/03/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00009 | 29/01/16 | TECHNICAL CONTINGENCIES QUALIFICATION |  | OWNER RESPONSE REQUIRED | 15/02/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00010 | 01/02/16 | CONSTRUCTABILITY WORKSHOP |  | CLOSED |  | L-MIDOR-TPIT-00002 | 16/03/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00011 | 15/02/16 | MONTHLY PROGRESS: JANUARY 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00012 | 25/02/16 | TECHNICAL CONTINGENCIES QUANTIFICATION - MEETING # 1 RISK OPPORTUNITY ASSESSMENT | REF.:TPIT-MIDOR-L-00009 | CLOSED | 04/03/16 | L-MIDOR-TPIT-00003 | 16/03/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00013 | 01/03/16 | IMPORT DUTY AND SALES TAX EXEMPTION |  | OWNER RESPONSE REQUIRED | 03/03/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00014 | 07/03/16 | RISK/OPPORTUNITY ASSESSMENT WORKSHOP: MEETING IN ROME, 30TH - 31ST MARCH 2016 |  | CLOSED | 04/03/16 | L-MIDOR-TPIT-00005 | 16/03/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00015 | 10/03/16 | DRAFT AMENDMENT 2 AND PAYMENT INVOICE 20151000086/B | REF.:L-MIDOR-TPIT-00001 | OWNER RESPONSE REQUIRED | 18/03/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00016 | 15/03/16 | MONTHLY PROGRESS: FEBRUARY 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00017 | 15/03/16 | INVOICE TRANSMISSION MILESTONE D)
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00018 | 01/04/16 | OWNER'S REQUEST TO MOVE RISK ASSESSMENT WORKSHOP AND CONSTRUCTABILITY WORKSHOP IN CAIRO | REF.:L-MIDOR-TPIT-00005 | OWNER RESPONSE REQUIRED | 03/04/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00019 | 06/04/16 | CONSTRUCTABILITY WORKSHOP IN ROME FROM MA 9 TO MAY 13 2016 | REF.:TPIT-MIDOR-L-00010 | OWNER RESPONSE REQUIRED | 11/04/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00020 | 12/04/16 | RISK-OPORTUNITY ASSESSMENT WORKSHOP MEETING IN ROME 7-8 JUNE 2016 |  | OWNER RESPONSE REQUIRED | 18/04/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00021 | 13/04/16 | MONTHLY PROGRESS: MARCH 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00022 | 28/04/16 | PMC/MIDOR INTEGRATED TEAM |  | CLOSED | 04/05/16 | L-MIDOR-TPIT-00006 | 19/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00023 | 22/04/16 | CHANGE ORDER FOR DCC SERVICES FOR MIDOR PMC IN TPIT OFFICE |  | CLOSED | 26/04/16 | L-MIDOR-TPIT-00007_DTD.19/05/2016 L-MIDOR-TPIT-00012 | 10/07/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00024 | 26/04/16 | INVOICE TRANSMISSION MILESTONE "C" |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00025 | 09/05/16 | CHANGE ORDER FOR RFQ PREPARATION FOR MIDOR REFINERY EXISTING UNITS INTEGRITY CHECK |  | CLOSED | 16/05/16 | L-MIDOR-TPIT-00008 | 19/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00026 | 09/05/16 | CO FOR QUANTITATIVE RISK ASSESSMENT (QRA) |  | CLOSED | 16/05/16 | L-MIDOR-TPIT-00008 | 19/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00027 | 09/05/16 | SIMULTANEOUS OPERATIONS (SIMOPS) |  | CLOSED | 13/05/16 | L-MIDOR-TPIT-00008 | 19/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00028 | 12/05/16 | MULTI HEADS DOSING PUMPS IN MULTIPLE SERVICE OR MULTI INJECTION POINTS |  | CLOSED |  | L-MIDOR-TPIT-00011 | 10/06/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00029 | 12/05/16 | GUARANTEED FUEL EFFICIENCY ON HEATER 18-H-01 |  | CLOSED |  | TPIT-MIDOR-L-00029 | 05/06/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00030 | 12/05/16 | STRUCTURAL/MECHANICAL/CIVIL VERIFICATION OF REVAMPED EQUIPMENT |  | CLOSED |  | L-MIDOR-TPIT-00010 | 05/06/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00031 | 18/05/16 | NOTICE OF CHANGE TO EARLY WORKS COMPLETION DATE |  | OWNER RESPONSE REQUIRED | 27/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00032 | 20/05/16 | MIDOR REPLY TO TPIT-MIDOR-L-00022 - PMC/MIDOR INTEGRATED TEAM | REF.: L-MIDOR-TPIT-00006 | OWNER RESPONSE REQUIRED | 27/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00033 | 31/05/16 | MONTHLY PROGRESS: APRIL 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00034 | 23/05/16 | CHANGE ORDER N.001 REV.01 FOR DCC SERVICES FOR MIDOR PMC IN TPIT OFFICE |  | OWNER RESPONSE REQUIRED | 27/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00035 | 26/05/16 | DRAFT AMENDMENT 2 REV 01 AND PAYMENT INVOICE 20151000086/B | REF.: L-MIDOR-TPIT-00001 | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00036 | 27/05/16 | INVOICE TRANSMISSION:MILESTONE "E" U&O BULK MATERIAL QUANTITIES |  | OWNER RESPONSE REQUIRED | 27/05/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00037 | 10/06/16 | UNIT 21 NITROGEN RECIRCULATION COMPRESSOR MAINTENANCE |  | CLOSED | 17/06/16 | L-MIDOR-TPIT-00015 | 10/07/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00038 | 10/06/16 | REPLY TO MIDOR CEO CLARIFICATION ON APRIL PROGRESS |  | CLOSED |  | L-MIDOR-TPIT-00013 | 10/07/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00039 | 14/06/16 | MONTHLY PROGRESS: MAY 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00040 | 10/06/16 | MOBILIZATION OF MIDOR KEY PERSONNEL IN ROME |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00041 | 13/06/16 | DELAY IN PAYMENT OF CONTRACTOR INVOICES |  | OWNER RESPONSE REQUIRED | 16/06/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00042 | 13/06/16 | PMC COMMENTS TO CONTRACTOR'S SPECIFICATION (JSS/JSD) - NOTICE OF CHANGE |  | CLOSED |  | L-MIDOR-TPIT-00016 | 10/07/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00043 | 22/06/16 | INVOICE TRANSMISSION_MILESTONE D RELEVANT TO ENPPI PORTION |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00044 | 23/06/16 | DELAY IN PAYMENT OF CONTRACTOR'S INVOICES |  | OWNER RESPONSE REQUIRED | 27/06/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00045 | 28/07/16 | EXTENDED QRA |  | CLOSED | 01/07/16 | L-MIDOR-TPIT-00019 | 10/07/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00046 | 01/07/16 | INVOICE TRANSMISSION MILESTONE C RELEVANT TO ENPPI PORTIN |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00047 | 04/07/16 | CO N 001 DCC SERVICES FOR MIDOR PMC IN TPIT OFFICES SUSPENSION OF SERVICE |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00048 | 07/07/16 | ELECTRIC POWER REQUIRED AFTER MIDOR REFINERY EXPANSION |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00049 | 07/07/16 | RAW WATER REQUIRED AFTER MIDOR REFINERY EXPANSION |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00050 | 12/07/16 | MONTHLY PROGRESS: JUNE 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00051 | 13/07/16 | UNIT 21 NITROGEN RECIRCULATION COMPRESSOR MAINTENANCE |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00052 | 25/07/16 | REPLY TO MIDOR LETTER #00013 - MIDOR CEO CLARIFICATIONS ON APRIL PROGRESS |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00053 | 25/07/16 | REPLY TO MIDOR LETTER #00011 - MULTI HEADS DOSING PUMPS IN MULTIPLE SERVICE OR MULTI INJECTION POINTS |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00054 | 24/07/16 | CHANGE ORDER N.001 REV.01 FOR DCC SERVICES FOR MIDOR PMC IN TPIT OFFICE (AUG-OCT) |  | CLOSED | 29/07/16 | L-MIDOR-TPIT-00027 | 20/11/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00055 | 25/07/16 | MINIMUM REQUIREMENTS FOR ITPS FROM OWNER |  | CLOSED |  | L-MIDOR-TPIT-00020 | 11/08/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00056 | 25/07/16 | PMC COMMENTS TO CONTRACTOR'S SPECIFICATIONS (JSS/JSD) - NOTICE OF CHANGE | REF: L-MIDOR-TPIT-00016 | CLOSED |  | L-MIDOR-TPIT-00018 | 11/08/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00057 | 25/07/16 | REPLY TO MIDOR LETTER #00010 - STRUCTURAL/MECHANICAL/CIVIL VERIFICATIONS OF REVAMPED EQUIPMENT |  | CLOSED | 01/08/16 | L-MIDOR-TPIT-00024 | 05/10/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00058 | 25/07/16 | INVOICE TRANSMISSION : CO NO 001 DCC SERVICES FOR MIDOR PMC IN TPIT OFFICES |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00059 | 04/08/16 | CAPEX MITIGATION | REF: | CLOSED |  | L-MIDOR-TPIT-00023 | 05/10/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00060 | 01/08/16 | PDPS FINAL ISSUE | REF: | OWNER RESPONSE REQUIRED | 05/08/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00061 | 01/08/16 | PROJECT CORRESPONDENCE - DOCUMENT TRANSMITTAL AND APPROVAL | REF: | CLOSED | 08/08/16 | L-MIDOR-TPIT-00019 | 11/08/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00062 | 04/08/16 | CRSS STATUS | REF: | OWNER RESPONSE REQUIRED | 12/08/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00063 | 06/09/16 | MONTHLY PROGRESS JULY 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00064 | 26/08/16 | CO N6 FOR QRA AND SIMOPS | REF.:L-MIDOR-TPIT-00020 | CLOSED | 15/09/16 | L-MIDOR-TPIT-00022 | 13/09/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00065 | 19/09/16 | MONTHLY PROGRESS:AUGUST 2016
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00066 | 21/09/16 | PMC COMMENTS TO CONTRACTORS SPEC NOTICE OF CHANGE
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00067 | 28/09/16 | DELAY IN PAYMENT OF CONTRACTOR’S INVOICES |  | CLOSED | 03/10/16 | L-MIDOR-TPIT-00025 | 13/10/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00068 | 07/10/16 | SUSPENSION OF DCC SERVICES TO PMC
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00069 | 12/10/16 | STRUCTURAL/MECHANICAL/CIVIL VERIFICATIONS OF REVAMPED EQUIPMENT | REF.: L-MIDOR-TPIT-00024
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00070 | 12/10/16 | DELAY IN PAYMENT OF CONTRACTOR’S INVOICES | REF.: L-MIDOR-TPIT-00025
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00071 | 20/10/16 | CHANGE ORDER REQUEST N.06 FOR QRA AND SIMOPS SUBCONTRACT | REF.:L-MIDOR-TPIT-0022/TPIT-MIDOR-L-0064 | OWNER RESPONSE REQUIRED | 27/10/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00072 | 03/11/16 | BUILT LEASE AND TRANSFER CONTRACT |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00073 | 11/11/16 | CHANGE ORDER REQUEST N. 08 UNFORESEEN CHANGES AND DELAYS OF THE BASIC DESIGN PACKAGE |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00074 | 11/11/16 | CHANGE ORDER REQUEST N. 07 MODULAR LPG TREATMENT UNIT |  | CLOSED | 18/11/16 | MIDOR-TPIT-L-00031 | 01/12/16
Letter | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00076 | 11/11/16 | CHANGE ORDER N 09 FOR DCC SERVICES FOR MIDOR PMC IN TPIT OFFICE (NOV ’16 TO JAN ’17) |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00077 | 10/11/16 | CRS ANALYSIS |  | CLOSED |  | L-TPIT-MIDOR-L-00026 | 20/11/16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00078 | 10/11/16 | U-51 CONDENSATE SYSTEM |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00079 | 11/11/16 | INVOICE TRANSMISSION : CO NO 005 DCC SERVICES FOR MIDOR PMC IN TPIT OFFICES (AUG-OCT 2016) |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00080 | 14/11/16 | INVITATION FOR MEETING IN ROME FOR TECHNICAL BID TABULATION APPROVAL FOR MACHINERY EQUIPMENT |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00081 | 22/11/16 | INTEGRITY ASSESMENT OF EXISTING FACILITIES STATUS AND CLARIFICATION ON THE SCOPE |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00082 | 22/11/16 | TCF DRAINING AND DISCHARGE TO THE LAKE |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00083 | 22/11/16 | IMPACT TO EARLY WORKS OF SAVING SELECTED BY OWNER |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00084 | 22/12/16 | CHANGE ORDER REQUEST N.07 REV.1 MODULAR LPG TREATMENT UNIT | REF.: L-MIDOR-TPIT-00031 | OWNER RESPONSE REQUIRED | 09/01/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00085 | 22/12/17 | TRANSMISSION OF AMENDMENT II |  | OWNER RESPONSE REQUIRED | 02/01/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00086 | 17/01/17 | TECHNIP SA MERGED WITH FMC TECNOLOGIES INC |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00087 | 10/02/17 | TECHNIP FMC :NEW GROUP LOGO |  |  | 09/01/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00088 | 20/02/17 | ADDITIONAL ACTIVITIES |  | OWNER RESPONSE REQUIRED | 27/02/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00089 | 20/02/17 | INVOICE TRANSMISSION CO N-009 DCC SERVICES FOR MIDOR PMC IN TPIT OFFICES
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00090 | 24/02/17 | INVOICE TRANSMISSION MILESTONE F (PART 1 OF 3)
Letter | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00091 | 28/02/17 | CHANGE ORDER N. 10FOR DCC SERVICES FOR MIDOR PMC IN TECHNIP FMC PREMISES IN ROME (FEB '17 TO JUL'17)
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00094 | 20/04/17 | CHANGE ORDER REQUEST N.07 REV. 02 MODULAR LPG TREATMENT UNIT | REF: | CLOSED | 30/04/17 | L-MIDOR-TPIT-00033 | 22/05/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00095 | 02/05/17 | COMPLIANCE WITH CURRENT LAW OF WWT EFFLUENT DISCHARGE | REF: | OWNER RESPONSE REQUIRED | 07/05/17
Letter | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00097 | 22/06/17 | INVOICE TRANSMISSION: CO N. 10 PERIOD MAY - JUL 2017 |  | CLOSED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00098 | 22/06/17 | INVOICE TRANSMISSION: MILESTONE "F" (PART 2 OF 3) |  | CLOSED
Letter | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00099 | 27/06/17 | CHANGE ORDER N. 11 FOR DCC SERVICES FOR MIDOR DCC IN TECHNIPFMC PERMISES IN ROME AUG 17T O JAN 18 |  | OWNER RESPONSE REQUIRED | 15/07/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00100 | 13/07/17 | CHANGE ORDER REQUEST N.07 REV. 03 MODULAR LPG TREATMENT UNIT | REF: L-MIDOR-TPIT-00033 | CLOSED | 30/07/17 | L-MIDOR-TPIT-00034 | 31/07/17
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00101 | 26/07/17 | REMOVAL OF FACILITIES FROM REFINERY AREAS
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00102 | 02/08/17 | INVOICE TRANSMISSION CHANGE ORDER N.07 REV. 03 1ST PAYMENT |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00103 | 23/08/17 | SEGREGATION ACTIVITIES FOR THE CONFIDENTIAL INFORMATION RELATED TO UNIT 11 |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00104 | 06/10/17 | TECHNICAL CONTINGENCY LEVEL SELECTION WORKSHOP IN ROME |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00105 | 20/11/17 | INTEGRITY ASSESSMENT OF EXISTING FACILITIES | REF.: L-MIDOR-TPIT-00028
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00106 | 17/11/17 | CHANGE ORDER PROPOSAL N.012 - FREE ZONE - NEW ACCESS - PHASE 1 (ENGINEERING) | REF.: ITEM 8 OF TPIT-MIDOR-MOM-00186 | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00107 | 17/11/17 | INVOICE TRANSMISSION: CHANGE ORDER N.11 REV.0
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00109 | 22/12/17 | UNIT 37 BASIS OF DESIGN CHANGED SCOPE OF WORK | REF.: MIDOR-TPIT-E-0155
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00110 | 2018-01-30 | ENPPI LETTER: LETTERS OF CREDIT IN EPC SUBCONTRACT | REF.: EN/TECHNIP-LTR-001/2018 | OWNER RESPONSE REQUIRED | 2018-02-04
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00111 | 2018-02-07 | OWNER COMMENTS TO OBE DRAFT REPORT | REF.: TPIT-MIDOR-L-00108 | OWNER RESPONSE REQUIRED | 2018-02-14
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00112 | 2018-02-07 | CHANGE ORDER N.12 FOR DCC SERVICES FOR MIDOR PMC IN TECHNIP FMC PERMISES IN ROME (FEB' 18 TO MAR' 18) |  | OWNER RESPONSE REQUIRED | 2018-02-16
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00114 | 2018-03-28 | INVOICE TRANSMISSION CO N.12 PERIOD FEB-APRIL 2018 |  | OWNER RESPONSE REQUIRED
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00115 | 2018-04-18 | CHANGE ORDER N.13 FOR DCC SERVICES FOR MIDOR PMC IN TECHNIP FMC PERMISES IN ROME (MAY 18) |  | OWNER RESPONSE REQUIRED | 2018-04-26
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00116 | 2018-05-29 | INVOICE TRANSMISSION: CHANGE ORDER N.13 FOR DCC SERVICES FOR MIDOR PMC IN TECHNIP FMC PERMISES IN ROME (MAY 18)
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00117 | 2018-07-30 | INVOICE TRANSMISSION: MILESTON "F" (PART 3 OF 3)
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00118 | 2018-08-08 | ELECRICAL POWER FOR THE EXPANSION PROJECT - UPDATE
Letter | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-L-00119 | 2018-08-10 | RAW WATER REQUIREDT AFTER REFINERY EXPANSION - UPDATE | TPIT-MIDOR-L-00049
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00001 | 14/09/15 | KICK-OFF MEETING OF 14/09/2015
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00002 | 16/09/15 | OPERATIVE KICK-OFF MEETING OF 16/09/2015
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00003 | 17/09/15 | KICK-OFF MEETING - CONSTRUCTION TABLE OF 16/09/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00004 | 17/09/15 | OPERATIVE KICK-OFF MEETING - DAY 2 - OF 17/09/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00005 | 17/09/15 | PROCUREMENT TABLE OF 17/09/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00007 | 17/09/15 | KICK-OFF MEETING OF 17/09/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00008 | 17/09/15 | KICK-OFF MEETING ENGINEERING TABLE (ITEMIZED EQUIPMENT) OF 16-17/09/2015
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00010 | 17/09/15 | CORPORATE SOCIAL RESPONSIBILITY OF 16/09/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00011 | 17/09/15 | PROCESS KICK-OFF MEETING OF 17/09/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00012 | 17/09/15 | OPERATIVE KICK-OFF MEETING DAY 2 OF 17/09/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00013 | 17/10/15 | SITE SURVEY FOR ELECTRICAL MAIN TOPICS FROM 13 TO 17/10/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00014 | 17/10/15 | KICK-OFF MEETING FROM 13 TO 17/10/2015
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00015 | 18/10/15 | SITE SURVEY MEETING FROM 13 TO 17/10/2015
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00026 | 29/10/15 | TCF PLAN REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00027 | 29/10/15 | GENERAL PLOT PLAN REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00030 | 11/12/15 | WEEKLY CONFERENCE CALL |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00032 | 18/12/15 | GENERAL PLOT PLAN REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00034 | 21/12/16 | SITE SURVEY FOR ELECTRICAL MAIN TOPICS
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00035 | 21/01/16 | UNIT 21 HYDROGEN PRODUCTION UNIT 2ND TRAIN PFD REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00035 BIS | 25/01/16 | UNIT 21 HYDROGEN PRODUCTION UNIT 2ND TRAIN PFD REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00036 | 29/01/16 | DISCUSSED ABOUT THE POSSIBLE CSR
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00037 | 29/01/16 | BASIC DESIGN STATUS MEETING WITH UOP
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00040 | 24/02/16 | MAJOR ENGINEERING TOPICS REVIEW MEETINGS
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00043 | 10/02/16 | IT INFRASTRUCTURE
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00044 | 22/02/16 | UNIT 22 - PID REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00045 | 25/02/16 | WWT AND WATER REUSE DESIGN BASIS
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00046 | 06/02/16 | GENERAL PLOT PLAN REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00047 | 04/02/16 | UNIT 11 (DCU) DRUM ISOLATION LOGIC MATRIX REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00048 | 07/03/16 | BASIC DESIGN FINAL REVIEW MEETING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00051 | 24/03/16 | UNIT 14-15 PERFORMANCE OF FEED SURGE DRUMS
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00052 | 24/03/16 | PLOT PLAN REVIEW MEETING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00054 | 31/03/16 | TCF PLAN REVIEW MEETING & OTHER CIVIL TOPICS
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00056 | 01/04/16 | PLOT PLAN REVIEW MEETING UNIT 17 AND UNIT 19
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00060 | 14/04/16 | SITE SURVEY FOR ELECTRICAL MAIN TOPICS
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00062 | 12/07/16 | UNIT 54/55 DESIGN BASIS AND PFDS REVIEW
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00065 | 02/10/16 | OVERALL AND UNIT PLOT PLANTS PMC COMMENTS REVIEW MEETING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00066_REV1 | 07/07/16 | CIVIL SPECIFICATIONS - PMC COMMENTS REVIEW MEETING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00070 | 26/07/16 | REVIEW FOR TBT 1011-101 REV 1 CENTRIFUGAL COMPRESSORS
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00071 | 22/10/16 | TBT 1020-001 REVIEW MEETING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00072 | 14/07/16 | WEEKLY COORDINATION MEETING (W28)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00073 | 21/07/16 | WEEKLY COORDINATION MEETING (W29)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00074 | 16/09/16 | PID APPROVAL & COMMENTS CLOSURE
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00075 | 10/08/16 | MANAGMENT MEETING IN CAIRO
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00076 | 23/09/16 | WEEKLY COORDINATION MEETING (W37 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00077 | 20/09/16 | UNIT 21 - PLOT PLAN REVIEW MEETING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00078 | 21/09/16 | APPROVAL OF TBT FOR MR-0411-101 - LAS REACTORS (CAT.0) | CHIUSURA CRS 0411-101
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00079 | 21/09/16 | REVIEW FOR TBT 0610-103 REV 0
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00080 | 22/09/16 | WEEKLY COORDINATION MEETING (W38 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00081 | 27/09/16 | PLOT PLANSFINAL REVIEW MEETING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00082 | 27/09/16 | REVIEW FOR TBT 0150-101 REV-A (AUXILIARY STEAM BOILERS)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00083 | 28/09/16 | APPROVAL OF TBT FOR MR-0511-001 - MAIN SHOP-ASSEMBLED COLUMNS (CAT.0)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00084 | 05/10/16 | WEEKLY COORDINATION MEETING (W39 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00085 | 27/09/16 | APPROVAL OF TBT FOR MR-0110-001 - FIRED HEATERS (CAT.0)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00086 | 04/10/16 | REVIEW FOR TBT FOR MR-0811-101 - (HIGH PRESSURE VESSELS |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00087 | 04/10/16 | APPROVAL OF TBT FOR MR-0570-001 - PROPRIETARY INTERNALS FOR MAIN SHOP-ASSEMBLED COLUMNS (CAT.1 )
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00088 | 04/10/16 | APPROVAL OF TBT FOR MR-0570-002 - INTERNALS FOR MAIN SHOP-ASSEMBLED COLUMNS (CAT.1)
Minutes of Meeting | MIDOR | 47 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00089 | 04/10/16 | APPROVAL OF TBT FOR MR-0470-R02 - INTERNALS FOR REACTORS (REVAMP) (CAT.1)
Minutes of Meeting | MIDOR | 47 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00090 | 04/10/16 | APPROVAL OF TBT FOR MR-0470-101 -'PROPRIETARY INTERNALS FOR LOW-ALLOY REACTORS (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00091 | 07/07/17 | REVIEW FOR TBS 0610-01 REV. 1 & 0 (HIGH PRESSURE & SPECIAL MATERIAL SHELL & TUBE HEAT EXCHANGERS)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00093 | 06/10/16 | PIDS APPROVAL AND COMMENTS CLOSURE
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00094 | 11/10/16 | WEEKLY COORDINATION MEETING (W41 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00095 | 11/10/16 | APPROVAL OF TBT FOR MR-0110-R01 - FIRED HEATERS (REVAMP) (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00096 | 11/10/16 | APPROVAL OF TBT FOR MR-0182-101 - DERRICK SUPPORTED ELEVATED FLARES (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00097 | 27/01/17 | REVIEW FOR TBT 0710-001 REV 0 /AIR COOLER HET EXCHANGER | CHIUSURA CRS TBT-0710-001
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00098 | 13/10/16 | APPROVAL OF TBT FOR MR-0210-101 - DEMINERALIZATION AND ULTRAFILTRATION PACKAGE (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00099 | 13/10/16 | APPROVAL OF TBT FOR MR-0851-001 - VACUUM UNIT PACKAGE (CAT.1)
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00100 | 13/10/16 | APPROVAL OF TBT FOR MR-4171-201 - INSTRUMENT AIR DRYER PACKAGE (CAT.1)
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00101 | 26/10/16 | REVIEW MEETING FOR TBT FOR MR-4117-101 - LIN STORAGE PACKAGE (CAT.1) |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00102 | 21/10/16 | WEEKLY COORDINATION MEETING (W42 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00104 | 25/10/16 | APPROVAL OF TBT FOR MR-1515-003 - MACHINERY MONITORING SYSTEM
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00105 | 08/02/17 | REVIEW FOR TBT FOR MR-0310-201 COOLING TOWERS CAT.1 | CHIUSURA CRS MR/TBT/ITP/SP- 0310-201
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00106 | 16/03/17 | REVIEW FOR TBT FOR MR-4111-001 - PSA UNITS (CAT.1) |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00107 | 26/10/16 | REVIEW MEETING FOR TBT FOR MR-4151-101 - REFRIGERATION PACKAGE (CAT.1) |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00108 | 26/10/16 | APPROVAL OF TBT FOR MR-4190-101 BOTTOM UNHEADING VALVES (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00109 | 28/10/16 | WEEKLY COORDINATION MEETING (W43 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00110 | 28/10/16 | WEEKLY COORDINATION MEETING (W45 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00111 | 15/11/16 | APPROVAL OF TBT FOR MR-0610-403 - SULPHUR CONDENSERS (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00112 | 15/11/16 | APPROVAL OF TBT FOR MR-0127-401 - CONVECTION MODULES PACKAGES (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00113 | 15/11/16 | APPROVAL OF TBT FOR MR-0168-401 - THERMAL REACTOR-WASTE HEAT BOILER-WHB STEAM DRUM(CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00114 | 15/11/16 | APPROVAL OF TBT FOR MR-0191-401 - THERMAL REACTOR BURNERS (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00115 | 15/11/16 | APPROVAL OF TBT FOR MR-0191-402 - INCENERATOR BURNERS (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00116 | 15/11/16 | APPROVAL OF TBT FOR MR-4141-201 - DESALTER (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00117 | 22/11/16 | WEEKLY COORDINATION MEETING (W46 Y16) |  | CLOSED
Minutes of Meeting | MIDOR | 47 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00118 | 24/11/16 | WEEKLY COORDINATION MEETING (W47 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00119 | 02/12/16 | WEEKLY COORDINATION MEETING (W48 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00120 | 19/07/17 | REVIEW FOR TBT FOR MR 1013-201 - INTEGRALLY GEARED COMPRESSORS (CAT, 1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00121 | 04/04/16 | REVIEW FOR TBT FOR MR 1031-101-ROTARY SCREW COMPRESSORS (CAT.1) | CHIUSURA CRS MR/TBT-1031-101
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00122 | 15/12/16 | REVIEW FOR TBT 1011-102 WET GAS COMPRESSOR (CAT.1) | CHIUSURA CRS TBT-1011-102
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00123 | 15/12/16 | REVIEW FOR TBT 0910-402 SULPHUR PUMPS (CAT. 1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00124 | 20/06/17 | REVIEW FOR TBT FOR MR-4300-402 SULPHUR SOLIDIFICATION PACKAGE (CAT.1) |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00125 | 15/12/16 | WEEKLY COORDINATION MEETING (W50 Y16)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00126 | 13/11/17 | REVIEW FOR TBT FOR MR-0910-001 CENTRIFUGAL PUMPS(CAT.1) |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00127 | 07/03/17 | REVIEW FOR TBT FOR RFQ- 0910-R01 CENTR. PUMPS (REVAM FLOWSEWRVE) CAT.1 | CHIUSURA CRS RFQ-0910-R01
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00128 | 04/04/17 | REVIEW FOR TBT FOR RFQ- 0910-R02 CENTR. PUMPS (REVAM GABBIOETA) CAT.1 | CHIUSURA CRS RFQ-TBT-0910-R02
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00129 | 27/02/17 | REVIEW FOR TBT FOR RFQ- 0910-R03 CENTR. PUMPS (REVAM SUNSTRAND) CAT.1 | CHIUSURA CRS RFQ-0910-R03
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00130 | 19/07/17 | REVIEW FOR TBT FOR MR 0920-001 - RECIPROCATING PUMPS (CAT, 1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00131 | 2016-07-26 | REVIEW FOR TBT FOR MR 0931-201 - ROTARY SREW (CAT, 1) | SIGNED BY PMC JULY 26TH 2018 | CLOSED |  | APPROVED/CLOSED 2544-00-TBT-0931-201_0-CRXS_0 AND SP-SR-DL-ITP-MR-0931-201_A-CRS_0 /2544-19-SP-1111-01-PB-CRS_1
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00132 | 16/02/17 | EARLY WORKS STATUS REVIEW MEETING | DATE OF MEETING 10-11/01/2017
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00133 | 02/02/17 | APPROVAL OF TBT FOR MR 0570-R02 -TRAYS AND INTERNALS FOR COLUMNS REVAMP CAT.1 | CHIUSURA CRS RFQ7TBT-0570-R02
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00134 | 22/05/17 | APPROVAL OF TBS FOR MR 0710-R01 MOTORS AND FANS EXISTING AIRCOOLERS REVAMP (CAT. 1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00135 | 06/07/17 | APPROVAL OF TBS FOR MR 0811-R01 MISCELLANEOUS PRESSURE VESSELS REVAMP (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00136 | 02/02/17 | APPROVAL OF TBT FOR MR 2520-101-TSITE ASSEMBLED STORAGE TANKS CAT.1 | CHIUSURA CRS MR/TBT/ITP/SP-2520-101
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00137 | 02/03/17 | REVIEW FOR TBT FOR MR 1020-301 - RECIPROCATION COMPRESSOR (AUXILIARY SERVICE) (CAT.1)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00139 | 04/04/17 | REVIEW FOR TBT FOR MR-1040-402 COMBUSTION AIR BLOWER (CAT.1) | CHIUSURA CRS RFQ-TBT-0910-R02
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00140 | 30/01/17 | WEEKLY COORDINATION MEETING (W4 Y17)
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00141 | 02/02/17 | WEEKLY COORDINATION MEETING (W5 Y17)
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00144 | 02/02/17 | WEEKLY COORDINATION MEETING (W7 Y17)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00145 | 23/02/17 | COMMENT TO REFORMER TECHNICAL OFFER
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00148 | 22/03/17 | TELECONFERENCE ON INCENERATOR SYSTEM
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00151 | 28/03/17 | WEEKLY COORDINATION MEETING (W12 Y17)
Minutes of Meeting | MIDOR | 17 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00156 | 12/06/17 | WEEKLY COORDINATION MEETING (W23 Y17)
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00185 | 21/07/17 | REVIEW AND CLOSURE OF OWNER COMMENTS TO REFORMER PACKAGE TECHNICAL PROPOSAL |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00207 | 03/08/17 | MEETING WITH HONEYWELL FOR ICSS |  |  |  | APPROVAL/CLOSED CRS TELECOM MR/TBT 1530-01, NM 1530-06
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00209 | 08/08/17 | CLOSURE OF TECHNICAL COMMENTS ON TELECOM MR/TBT 1530-01, TIE-IN LIST NM 1530-06 AND OTHER RELATED DESIGN ISSUE |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00217 | 09/07/17 | APPROVAL OF FIRE FIGHTING, FIRE & GAS, FIREPROOFING SPECIF, PROCESS DESIGN SAFETY, CRITERIA & FIRE FIGHT. & F&G LAYOUTS |  |  |  | APPROVAL/CLOSED TBT PIPING
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00223 | 10/08/17 | CLOSURE OF TECHNICAL COMMENTS ON TECHNICAL BID TABULATIONS FOR PIPING |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00268 | 28/09/17 | EPC SCHEDULE |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00272 | 25/09/17 | CLOSURE OF TECHNICAL/COMMERCIAL COMMENTS ON CRS FOR REFORMER PACKAGE (TPB SOW) |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00276 | 28/09/17 | GENERAL MATERIAL AND INSPECTION ISSUES |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00277 | 28/09/17 | ITP MEETING |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00293 | 2018-01-24 | APPROVAL OF FIELD SUPERVISION FOR CONSTRUCTION AND PRECOMMISSIONING |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00320_REV2 | 2018-01-31 | REVIEW OF SPECIAL ACTIVITIES AND SUBCONTRACTOR ASSISTANCE TO COMMISSIONING TPB SOW |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00326 | 2018-03-01 | EPC CONTRACT STATUS MEETING |  | CLOSED
Minutes of Meeting | MIDOR | 00 | PROJECT MANAGEMENT | TPIT-MIDOR-MOM-00332 | 2018-06-21 | SITE VISIT TO MIDOR PERMISES | MOM WITH TPIT/MIDOR/PTJ/ENPPI | CLOSED
Report | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-RR-1005 | 10/05/16 | WEEKLY COORDINATION MEETING | SEE TPIT-MODOR MOM FILE
Report | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-RR-1006 | 26/05/16 | WEEKLY COORDINATION MEETING | SEE TPIT-MODOR MOM FILE
Report | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-RR-1008 | 13/06/16 | WEEKLY COORDINATION MEETING | REF.:TPIT-MIDOR-E-01801
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00001 | 04/12/15 | PIPERACK AND STRUCTURE | ORIGINATOR: FERRANTINI - RUA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00001_1 | 04/12/15 | PIPERACK AND STRUCTURE | OR: FRATONI ATTACHMENTS SAME OF REV 0
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00002 | 04/12/15 | UNDERGROUND SYSTEM AND CIVIL WORK | ORIGINATOR: FERRANTINI - RUA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00004 | 04/12/15 | CARBON STEEL PIPING COMPONENTS - NACE | ORIGINATOR: RUA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00005 | 04/12/15 | REVAMPING OF FURNACE 02-H-01 OUT OF TP SCOPE | ORIGINATOR: RUA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00006 | 05/12/15 | LIMITS PRINCIPAL BETWEEN ENPPI AND TPIT | ORIGINATOR: DI BIASE - VANGELISTA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00006_1 | 27/01/16 | LIMITS PRINCIPAL BETWEEN ENPPI AND TPIT | ORIGINATOR: DI BIASE - VANGELISTA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00006_2 | 05/07/17 | LIMITS PRINCIPAL BETWEEN ENPPI AND TPIT (REV. 2) | ORIGINATOR: R. VANGELISTA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00008 | 14/12/15 | BATTERY LIMITS PRINCIPAL BETWEEN TPB AND TPIT | ORIGINATOR: FRATONI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00008_1 | 14/12/15 | BATTERY LIMITS PRINCIPAL BETWEEN TPB AND TPIT | ORIGINATOR: FRATONI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00009 | 09/12/15 | BATTERY LIMITS PRINCIPAL BETWEEN KT AND TPIT | ORIGINATOR: FRATONI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00009_1 | 22/03/16 | BATTERY LIMITS PRINCIPAL BETWEEN KT AND TPIT | ORIGINATOR: FRATONI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00009_2 | 08/02/17 | BATTERY LIMITS PRINCIPAL BETWEEN KT AND TPIT | ORIGINATOR: VANGELISTA/RUA
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00009_3 | 15/02/17 | BATTERY LIMITS PRINCIPAL BETWEEN KT AND TPIT | ORIGINATOR: VANGELISTA/RUA
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00010 | 22/12/15 | INSTRUMENT AIR SYSTEM | ORIGINATOR: CALDAROLA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00011 | 23/12/15 | BATTERY LIMITS PRINCIPAL BETWEEN ENPPI AND TPIT | ORIGINATOR: VANGELISTA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00012 | 13/01/16 | BATTERY LIMITS PRINCIPAL BETWEEN KT AND TPIT FOT TELECOM | ORIGINATOR: FRATONI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00013 | 13/01/16 | BATTERY LIMITS PRINCIPAL BETWEEN TPB AND TPIT FOT TELECOM | ORIGINATOR: FRATONI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00014 | 12/01/16 | BATTERY LIMITS PRINCIPAL BETWEEN KT AND TELECOM | ORIGINATOR: LOPEZ | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00016 | 15/01/16 | ELECTRICAL FEEDERS | ORIGINATOR: CALDAROLA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00017 | 15/01/16 | DRAIN CONNECTION IN ALLOY 825 | ORIGINATOR: LOPEZ | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00018 | 18/01/16 | SOIL DATA FOR OBE | ORIGINATOR: LOPEZ | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00020 | 26/01/16 | TYPICAL AND INFORMATION FOR PACKAGE MACHINERIES AND FIRED HEATER FOR PROCESS UNIT | ORIGINATOR: DI BIASE | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00022 | 02/02/16 | PRESSURE AND DIFFERENTIAL MEASUREMENTS ONHIGH POURPOINT FLUIDS | ORIGINATOR: CALDAROLA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00023 | 16/02/16 | INSULATION AND FIREPROOFING DETAILS | ORIGINATOR: FRATONI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00025 | 02/03/16 | CABLE ROUTING IN REVAMPED UNITS | ORIGINATOR: CALDAROLA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00026 | 12/04/16 | ASME - STAMP APPLICABILITY | ORIGINATOR: CAGNIZZI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00026_1 | 20/04/16 | ASME - STAMP APPLICABILITY | ORIGINATOR: CAGNIZZI | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00027 | 12/04/16 | NEW YARD TOILET BUILDING IN CDU/VDU, SDA AREA | ORIGINATOR: VANGELISTA | TPIT RESPONSE REQUIRED
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00029 | 01/03/17 | GROUNDING OF EQUIPMENT | ORIGINATOR: LOPEZ
Technical Notice | TPIT | 00 | PROJECT MANAGEMENT | 2544-00-TN-00030 | 12/07/17 | UG STANDARDIZATION LAY-OUT | ORIGINATOR: LOPEZ/RUA
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00001 | 19/08/16 | CLIENT COMMENTS TO MACHINERY DATA SHEET
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00002 | 19/08/16 | CLIENT COMMENTS TO 2544-08-NM-0020-01_B PID FINAL ISSUE MARKED UP
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00003 | 22/08/16 | CLIENT COMMENTS TO GENERAL
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00004 | 29/08/16 | CLIENT COMMENTS TO FIREFIGHTING SPECIFICATION
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00005 | 29/08/16 | CLIENT COMMENTS TO SAFETY PROCESS DESIGN CRITERIA
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00006 | 29/08/16 | CLIENT COMMENTS TO CATHODIC PROTECTION SYSTEM
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00007 | 29/08/16 | CLIENT COMMENTS TO ELECTRICAL GENERAL SUPPLY SPECIFICATIONS
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00008 | 29/08/16 | CLIENT COMMENTS TO GENERAL
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00010 | 01/09/16 | CLIENT COMMENTS TO FIREFIGHTING DOCUMENTATION
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00011 | 02/09/16 | CLIENT COMMENTS TO SATELLITE INSTRUMENT BUILDIGN ALYUT CR01 TO CR10
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00012 | 02/09/16 | CLIENT COMMENTS TO MR ROTARY SCREW COMPRESSOR AND MR FOR CENTRIFUGAL PUMPS (REVAMP)
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00013 | 02/09/16 | CLIENT COMMENTS TO MR FOR HP AND SPECIAL MATERIAL SHELL AND TUBE H.E. AND FOR HP PRESSURE VESSELS
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00014 | 02/09/16 | CLIENT COMMENTS TO OVERALL MAIN FIREFIGHTING LAYOUT
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00015 | 05/09/16 | CLIENT COMMENTS TO PROCESS HAZARD ANALYSIS PROCEUDRE
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00016 | 06/09/16 | CLIENT COMMENTS TO MSD UNIT 15 SOUR WATER STRIPPER UNIT
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00017 | 06/09/16 | CLIENT COMMENTS TO MR FOR SULPHURE CONDENSATE
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00018 | 06/09/16 | CLIENT COMMENTS TO FLARE STUDY
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00019 | 08/09/16 | CLIENT COMMENTS TO CONSTR. PRECOM. COMMISSIONING START-UP INITIAL OPERATION AND PERFORMANCE TEST SPLIT OF WORK AND RESP.
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00020 | 08/09/16 | CLIENT COMMENTS TO MR AIR COOLED HEAT EXCHANGERS
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00021 | 08/09/16 | CLIENT COMMENTS TO MR 0127-401/MR-0168-401/MR-0182-101/MR-0210-101/MR-0310-201
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00022 | 08/09/16 | CLIENT COMMENTS TO MR FOR SULPHUR PUMPS (2544-00-MR-0910-402)
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00023 | 09/09/16 | CLIENT COMMENTS TO MR MATERIAL REQUISITION FOR MMS - MACHINERY MONITORING SYSTEM (2544-00-MR-1515-003)
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00024 | 12/09/16 | CLIENT COMMENTS TO MR/SP/ITP/TBT FOR PROPIETARY INTERNALS FOR LOW ALLOY REACTORS
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00025 | 12/09/16 | CLIENT COMMENTS TO UNIT 54 UTILITIES CONSUMPTION WASTE WATER TREATMENT
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00026 | 12/09/16 | CLIENT COMMENTS TO MR/SR/SP/ITP/TBT FOR THERMAL REACTOR BURNER
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00027 | 12/09/16 | CLIENT COMMENTS TO MACHINERY MONITORING SYSTEM (MMS)
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00028 | 13/09/16 | CLIENT COMMENTS TO RFQ 1682-01 FOR ELECTRICAL HEAT TRACING SYSTEM | MIDOR-TPIT-T-00028
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00029 | 14/09/16 | CLIENT COMMENTS TO RFQ/TBT/ITB FOR CENTRIFUGAL PUMPS (REVAMP)
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00031 | 14/09/16 | CLIENT COMMENTS TO MR FOR CATHODIC PROTECTION SYSTEM (OBE)
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00032 | 15/09/16 | CLIENT COMMENTS TO MR MACHINE MONITORING SYSTEM
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00034 | 19/09/16 | CLIENT COMMENTS TO MR AIR BLOWR 2544-00-MR-1040-402_A
Transmittal | MIDOR | 47 | PVHE | MIDOR-TPIT-T-00035 | 19/09/16 | CLIENT COMMENTS TO MR 0470-R02 FOR INTERNALS FOR REACTORS (REVAMP)
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00039 | 21/09/16 | CLIENT COMMENTS TO JSD INSTRUMENTATION
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00040 | 21/09/16 | CLIENT COMMENTS TO MR 0920-001_B RECIPROCATING PUMPS
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00041 | 22/09/16 | CLIENT COMMENTS TO MR 0110-R01_A FIRE HEATER REV. - MR 4141-201_A DESALTER PACKAGE
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00042 | 22/09/16 | CLIENT COMMENTS TO MR 4111-001_A FOR PSA UNIT
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00043 | 22/09/16 | CLIENT COMMENTS TO P&I UNIT 46
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00045 | 22/09/16 | CLIENT COMMENTS TO JSS SPEC
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00046 | 23/09/16 | CLIENT COMMENTS TO MR 0570-001/002_A FOR COLUMNS
Transmittal | MIDOR | 00 | PIPING | MIDOR-TPIT-T-00047 | 23/09/16 | CLIENT COMMENTS TO PLOT PLAN - UNITS 46-52-53-56-60
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00048 | 23/09/16 | CLIENT COMMENTS TO JOB SPC FOR INSTRUMENTS
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00049 | 23/09/16 | CLIENT COMMENTS TO P&ID 057-02/059-01
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00050 | 23/09/16 | CLIENT COMMENTS TO FOR P&ID 061-01 UNIT 46
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00051 | 26/09/16 | CLIENT COMMENTS TO FOR P&ID
Transmittal | MIDOR | 00 | PIPING | MIDOR-TPIT-T-00052 | 27/09/16 | CLIENT COMMENTS TO JSD 1300-01_2
Transmittal | MIDOR | 00 | PIPING | MIDOR-TPIT-T-00054 | 27/09/16 | CLIENT COMMENTS TO 18/22/23-DW-0051
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00055 | 27/09/16 | CLIENT COMMENTS TO BASIC DESIGN DATA
Transmittal | MIDOR | 17 | PACKAGES | MIDOR-TPIT-T-00056 | 27/09/16 | CLIENT COMMENTS TO MR 0851-001_A MR 4171-201_B
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00057 | 28/09/16 | CLIENT COMMENTS TO EMERGENCY DIESEL GENERATOR
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00058 | 28/09/16 | CLIENT COMMENTS TO COMMUNICATION SYSTEM DESIGN SPECIFICATION
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00059 | 29/09/16 | CLIENT COMMENTS TO EQUIPMENT LIST UNIT 21/22
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00062 | 29/09/16 | CLIENT COMMENTS TO P&ID 46-PID-0021-001-02_B
Transmittal | MIDOR | 00 | PIPING | MIDOR-TPIT-T-00063 | 30/09/16 | CLIENT COMMENTS TO PLOT PLANS UNIT 24/31/37/46
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00064 | 30/09/16 | CLIENT COMMENTS TO MATERIAL REQUISITION R MR-0910-002/MR-0931-201/MR-0940-101_A
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00065 | 03/10/16 | CLIENT COMMENTS TO RFQ FOR COMMUNICATION SYSTEM 1530-01
Transmittal | MIDOR | 00 | PIPING | MIDOR-TPIT-T-00067 | 04/10/16 | CLIENT COMMENTS TO 23-DW-0051-01_C PLOT PLANS
Transmittal | MIDOR | 00 | PROCUREMENT | MIDOR-TPIT-T-00068 | 05/10/16 | CLIENT COMMENTS TO INSPECTION AND TEST PLAN FOR PSA UNIT
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00069 | 05/10/16 | CLIENT COMMENTS TO MECHANICAL TIE-IN LIST UNIT 08 AND 53
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00070 | 05/10/16 | CLIENT COMMENTS TO PFD UNIT 15 AND PID UNIT 22
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00071 | 05/10/16 | CLIENT COMMENTS TO TBT FOR MMS AND DW SATELLITE INSTRUMENT BUILDING LAYOUT UNIT 48
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00072 | 06/10/16 | CLIENT COMMENTS TO GEOTECHNICAL RECOMMENDATION FOR EPC PHASE
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00073 | 06/10/16 | CLIENT COMMENTS TO CRS FOR INERT CERAMIC BALLS
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00074 | 06/10/16 | CLIENT COMMENTS TO RFQ FOR FUEL GAS PREPARATION SYSTEMS
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00075 | 07/10/16 | CLIENT COMMENTS TO MR 0710-R01_B FOR MOTORS AND FANS FOR EXISTING AIRCOOLER (REVAMPING)
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00076 | 07/10/16 | CLIENT COMMENTS TO TBT 1511-01 FOR ICSS TECHNICAL TABULATION
Transmittal | MIDOR | 17 | HEATERS AND BOILERS | MIDOR-TPIT-T-00077 | 10/10/16 | CLIENT COMMENTS TO MR 0172-401 FOR MATERIAL REQUISITION STACK
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00078 | 10/10/16 | CLIENT COMMENTS TO MR 0270-101 FOR MATERIAL REQUISITION API SEPARATORS, DAF PACKAGE & SLUGE BELT PRESS
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00079 | 11/10/16 | CLIENT COMMENTS TO DW1442-01/02 MAJOR UNDERGR.FOR UNIT 00-18 & DW 1823-01 STEEL STRUCTURE UNIT 56
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00081 | 11/10/16 | CLIENT COMMENTS TO MR 0910-001 FOR CENTRIFUGAL PUMPS AND MR 4300-402 FOR SULPHUR SOLIDIFICATION PACKAGE
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00082 | 10/10/16 | CLIENT COMMENTS TO 00-JSS-2620-01 FOR MECHANICAL EQUIP LUBRICANTS SPEC
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00083 | 11/10/16 | CLIENT COMMENTS TO MR-4151-101 FOR MATERIAL REQUISITION FOR REFRIGERATION PACKAGE
Transmittal | MIDOR | 17 | PACKAGES | MIDOR-TPIT-T-00084 | 11/10/16 | CLIENT COMMENTS TO MR 0845-001 FOR FOR DEAERATOR AND MR 4117-101 FOR LIN STORAGE PACKAGE
Transmittal | MIDOR | 00 | PIPING | MIDOR-TPIT-T-00086 | 11/10/16 | CLIENT COMMENTS TO JSD 1300-08 JOB SPECIFICATION FOR PIPING STRESS ANALYSIS
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00087 | 13/10/16 | CLIENT COMMENTS TO MR 1515-003 FOR MMS MACHINE MONITORING SYSTEM
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00088 | 13/10/16 | CLIENT COMMENTS TO PID 0021-001-02 FOR PID UNIT 46 AND 53 SP-0910-05 FOR 53-P-05 A/B
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00089 | 13/10/16 | CLIENT COMMENTS TO JSD 1410 GEOTECHNICAL RECOMMENDATION FOR EPC PHASE
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00090 | 13/10/16 | CLIENT COMMENTS TO DW 1663-01 FOR ELE AND CONTROL SYST BLOCK DIAGRAM-ECMS AND DW 1622-03 FOR UNIT 36,37,38,41,42,43,44
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00091 | 13/10/16 | CLIENT COMMENTS TO DW 1612-01MAIN GROUN LAYOUT,49 DW 1625 02 SUBST EQUIP LAY. SS2, 49-DW-1652-11-MAIN ONE LINE DIAG SS-1
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00092 | 13/10/16 | CLIENT COMMENTS TO DW-1442-04 CONCEPTUAL OVERALL MAJOR ELE INTER , JSS-1682-01 GENERAL SUPPLY ELE HEAT TRACING SYSTEM
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00093 | 13/10/16 | CLIENT COMMENTS TO JSS-1684-01 GENERAL SUPPLY SPEC CATHODIC PROTECTON
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00094 | 17/10/16 | CLIENT COMMENTS TO MR-1682-01 ELE HEAAT TRACING SYS/MR 4123-01EMERG DIESEL GENER/ NM-2000-01 BUILD TIE-IN
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00096 | 17/10/16 | CLIENT COMMENTS TO JSD 0150-01 AUXILIARY STEAM BOILER, JSD-2300-01 PAINTING
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00097 | 17/10/16 | CLIENT COMMENTS TO CRS FOR MATERIAL REQUISITION FOR STACK
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00098 | 17/10/16 | CLIENT COMMENTS TO CRS FOR JSS PUMPS AND COMPRESSOR
Transmittal | MIDOR | 00 | BUILDINGS | MIDOR-TPIT-T-00100 | 18/10/16 | CLIENT COMMENTS TO 00-NM-2000-01_A CRS FOR BUILDING TIE-IN LIST
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00102 | 18/10/16 | CLIENT COMMENTS TO MR-0910-001_A-CRS_1 AND MR-1031-101_A-CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00103 | 19/10/16 | CLIENT COMMENTS TO 00-JSS-0940-01_0 -CRS_1
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00104 | 19/10/16 | CLIENT COMMENTS TO 00-MR-4151-101_B-CRS_1
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00105 | 25/10/16 | CLIENT COMMENTS TO 00-MR-2520-101_B-CRS_0
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00107 | 25/10/16 | CLIENT COMMENTS TO 00-MR-0570-R02_A-CRS_0
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00108 | 25/10/16 | CLIENT COMMENTS TO 00-JSS-1515-03_1-CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00109 | 25/10/16 | CLIENT COMMENTS TO 00-MR-1040-402_A-CRS_1
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00110 | 25/10/16 | CLIENT COMMENTS TO 15-PFD-0010-01-01_C-CRS_1 AND 53-PID-0021-001-01_A-CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00111 | 26/10/16 | CLIENT COMMENTS TO 15-PFD-0010-01-01_C-CRS_1 AND 53-SP-0910-05_PA_CRS3
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00113 | 26/10/16 | CLIENT COMMENTS TO 00-JSS-0910-01-0-CRS_1, 00-JSS-0950-01-1-CRS_0, 00-JSS-1112-01-2-CRS_1
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00118 | 03/11/16 | CLIENT COMMENTS TO 55-PID-0021-003-01_A-CRS_1
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00119 | 03/11/16 | CLIENT COMMENTS TO 00-MS-1593-02_A-CRS_1 AND 00-MS-1593-03_A-CRS_1
Transmittal | MIDOR | 17 | PIPING | MIDOR-TPIT-T-00120 | 03/11/16 | CLIENT COMMENTS TO 17-DW-0051-01_A-CRS_1 AND 21-DW-0051-01_A-CRS_1
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00121 | 03/11/16 | CLIENT COMMENTS TO JSD AND JSS FOR EQUIPMENT, PRESSURE VESSELS COLUMNS INTERNALS AND HEAT EXCHANGERS
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00122 | 07/11/16 | CLIENT COMMENTS TO 2544-31-JSD-0001-01_A_CRS_2
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00124 | 14/11/16 | CLIENT COMMENTS TO 2544-00-CN-1626-01-B-CRS-0 AND PP-919_0
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00125 | 14/11/16 | CLIENT COMMENTS TO MR-0811-R01-B-CRS_0
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00126 | 17/11/16 | CLIENT COMMENTS TO 2544-00-DW-1622-03-A-CRS_1
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00127 | 07/11/16 | CLIENT COMMENTS TO 2544-00-MR-0610-002-C-CRS_0
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00128 | 16/11/16 | CLIENT COMMENTS TO 53-SP-0910-05_PB_CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00129 | 21/11/16 | CLIENT COMMENTS TO 2544-00-MR-4261-001_A-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00130 | 22/11/16 | CLIENT COMMENTS TO 2544-00-MR-4261-001_A-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00131 | 22/11/16 | CLIENT COMMENTS TO 31-JSD-0001-01-A-CRS_3 AND 53-PID-0021-001-01_A_CRS_2
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00132 | 24/11/16 | CLIENT COMMENTS TO 2544-00-MR-4065-001-A-CRS_0
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00133 | 24/11/16 | CLIENT COMMENTS TO MR INCINERATORS-VAPORIZER-SULPHUR AND FILTER
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00135 | 28/11/16 | CLIENT COMMENTS TO MRS FOR COLUMNS, HEAT EXCHANGERS AND PRESSURE VESSELS CRS_0
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00136 | 01/12/16 | CLIENT COMMENTS TO 00-MR-0910-401_A-CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00138 | 01/12/16 | CLIENT COMMENTS TO 00-MR-0310-102_A-CRS_0 AND 00-MR-0846-R01_A-CRS_0
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00139 | 02/12/16 | CLIENT COMMENTS TO 00-JSD-6000-01_A-CRS_1 AND 00-JSD-6000-03_A-CRS_1
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00140 | 02/12/16 | CLIENT COMMENTS TO 00-MR-1900-001_A-CRS_0
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00141 | 02/12/16 | CLIENT COMMENTS TO 00-RFQ-0932-101_B-CRS_0
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00143 | 05/12/16 | CLIENT COMMENTS TO 00-MR-1040-102_A-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00144 | 12/12/16 | CLIENT COMMENTS TO MR-0836-0844-0852-0853-4263-CRS_0
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00145 | 12/12/16 | CLIENT COMMENTS TO MR-0411-0661-2510-2520-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00147 | 12/12/16 | CLIENT COMMENTS TO 53-PID-0021-001- CRS FOR P&ID UNIT 53 3 12/12/2016
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00148 | 14/12/16 | CLIENT COMMENTS TO 00-MR-0960-301_A_CRS_0
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00150 | 19/12/16 | CLIENT COMMENTS TO 21-DW-1920-01-C-CRS-REPLY_0
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00151 | 21/12/16 | CLIENT COMMENTS TO 53-SP-0910-05_PB_CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00155 | 11/01/17 | CLIENT COMMENTS TO 2544-00-JSS-0910-01-2-CRS_0 2544-00-JSS-1112-01-3-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00156 | 11/01/17 | CLIENT COMMENTS TO 2544-40-PID-0021-001-01-B-CRS_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00157 | 11/01/17 | CLIENT COMMENTS TO ELECTRICAL BID TABULATIONS
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00161 | 16/01/17 | CLIENT COMMENTS TO 00-DW-1622-02-01-B-CRS_1 00-DW-1622-05-A-CRS-_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00162 | 16/01/17 | CLIENT COMMENTS TO ELECTRICAL DRAWINGS
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00165 | 20/01/17 | CLIENT COMMENTS TO 00-JSS-0910-01-2-CRS_1 00-JSS-1112-01-3-CRS_1
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00168 | 30/01/17 | CRS FOR PROCESS INTERCONNECTION PIDS
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00171 | 06/02/17 | CLIENT COMMENTS TO IN/OUT LIST UNIT 38 AN LAYOUT DW UNIT 00
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00173 | 06/02/17 | CLIENT COMMENTS TO 02-DW-1572-01
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00177 | 15/02/17 | CRS FOR EMERGENCY DIESEL GENERATOR | 2544-00MR-4123-01_A | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00178 | 16/02/17 | CRS FOR DW LAYOT UNIT 02 AND IN/OUT LIST UNIT 38 | 02-DW-1572-01/38-NM-1511-01 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00186 | 23/02/17 | CRS FOR 2544-07-DW-1622-01-B-CRS-0 2544-22-23-56-LS-1601-02-A-0 |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00187 | 23/02/17 | CRS FOR 2544-00-DW-1622-03-B-CRS-0 |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00189 | 24/02/17 | CRS FOR ELCTRICAL POWER BALANC AND TOOLS TEMPORARY EQUIP PROCEDURE | CN-1626-01_B AND PP-919_0 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00193 | 24/02/17 | CRS FOR IN/OUT LIST UNIT 02 | 2544-02-NM-1511-01-A-CRS_0 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00195 | 27/02/17 | CRS FOR COMUNICATION SYSTEM TECHNICAL TABULATION | 2544-00-TBT-1530-01-01-CRS_0 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00197 | 01/03/17 | CRS APPROVED FOR PROCESS DATA SHEETS PACKAGES AND PVHE | APPROVED CLOSED | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00206 | 07/03/17 | CRS FOR PROCESS DATA SHEETS SP-0710 UNIT PB |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00207 | 07/03/17 | CRS FOR CRS FOR CIVIL WORK UNIT 21 AND STEEL STRUCTURE UNIT 60 |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | PROCUREMENT | MIDOR-TPIT-T-00212 | 10/03/17 | CRS FOR VARIOUS COMMERCIAL BID TABULATION |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00213 | 13/03/17 | CRS FOR 00-JSS-6300-02-3-CRS_1 08-SP-0570-05-PA-CRS_1 | APPROVED CLOSED
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00214 | 13/03/17 | CRS FOR 00-DW-1442-04-B-CRS_0 AND 21-DW-1620-01-C-CRS_1 |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00215 | 13/03/17 | CRS FOR 00-PP-919-0-CRS_2, AA-1442-01-A-CRS_1 AND ELECTRICAL DWGS |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00219 | 13/03/17 | CRS FOR VARIOUS SP FOR PUMPS |  | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00222 | 16/03/17 | CRS FOR ELECTRICAL POWER CONSUMPTION FROM UPS IN MIDOR REFINERY | REF.TPIT-MIDOR-02531
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00223 | 16/03/17 | CRS FOR21-AA-1442-01-A-CRS_2 21-DW-1620-01-B-CRS_2 21-DW-1620-01-C-CRS_2
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00224 | 16/03/17 | CRS FOR 00-RFQ-4046-R01_A-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00225 | 16/03/17 | CRS FOR VARIOUS DATA SHEET FOR PUMPS AND STEAM TURBINE
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00228 | 23/03/17 | CRS FOR 0B-TBT-0910-002-0_CRS_0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00238 | 28/03/17 | CRS FOR PP-919 TOOLS AND TEMPORARY EQUIPMENT
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00244 | 30/03/17 | CRS FOR 00-RFQ-4046-001_C-CRS_0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00246 | 04/04/17 | CRS FOR 00-DW-8200-01-D-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00248 | 04/04/17 | CRS FOR 19-SP-4046-0X_PA-CRS-0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00249 | 04/04/17 | CRS FOR 00-PP-919_C-CRS_1
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00250 | 04/04/17 | CRS FOR 00-SOW-9000-02_B-CRS-0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00255 | 05/04/17 | CRS FOR 00-DW-8200-01-D-CRS-1
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00258 | 06/04/17 | CRS FOR 00-MR-1515-002_2-CRS_0 AND SITE SURVEY REPORT FOR DCS/ESD/F&G EQUIPMENTS
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00259 | 07/04/17 | CRS FOR 21-SP-0910-02_02-CRS-1
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00263 | 07/04/17 | CRS FOR 00-TBT-1511-01-CRS_03-PMC_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00274 | 20/04/17 | CRS FOR DATA SHEET FOR STEAM TURBINE AND FOR PUMPS
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00275 | 20/04/17 | CRS FOR DATA SHEET FOR 02-SP-0910-03-PA-CRS_1
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00276 | 20/04/17 | CRS FOR 00-NM-2121-101-A-CRS_0
Transmittal | MIDOR | 17 | PROCESS | MIDOR-TPIT-T-00280 | 20/04/17 | CRS FOR DSH FOR STEAM TURBINE 17-STP-56B
Transmittal | MIDOR | 17 | MACHINERY | MIDOR-TPIT-T-00281 | 20/04/17 | CRS FOR 17-SP-0910-16-A-CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00284 | 20/04/17 | CRS FOR 03-SP-0910-01-PA-CRS_1 04-SP-0910-02-PA-CRS_1 07-SP-0910-03-PA-CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00285 | 20/04/17 | CRS FOR 08-SP-0910-09-PA-CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00290 | 25/04/17 | CRS FOR 19-SP-1111-01_PB-CRS_2
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00298 | 04/05/17 | CRS FOR 00-PP-919-D-CRS_0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00300 | 04/05/17 | CRS FOR 00-PP-901-A-CRS_0
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00304 | 08/05/17 | CRS FOR 02-SP-0910-03-PA-CRS_2
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00306 | 08/05/17 | CRS FOR 00-MR-0113-301-1-CRS_0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00311 | 11/05/17 | CRS FOR 00-SOW-9000-02_B-CRS-1 20-SP-4046-01_PB-CRS_0
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00323 | 19/05/17 | CRS FOR 0A-ES-0630-001-CRS_0 0A-ES-4261-001-CRS_0 0A-ES-852-001-CRS_0
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00329 | 24/05/17 | CRS FOR 00-NM-1530-06-A-CRS_0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00334 | 31/05/17 | CRS FOR 2544-00-DW-8200-01-D-CRS-1
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00336 | 31/05/17 | CRS FOR PROCESS DATA SHEET PVHE VARIOUS UNITS
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00337 | 31/05/17 | CRS FOR 00-MR-1515-002_2-CRS_1 AND 00-RT-1500-02-B-CRS_1
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00341 | 06/06/17 | CRS FOR 2544-00-TBT-1511-01-CRS_4_PMC_1 |  |  |  | REVIEW WITH COMMENTS 2544-00-NM-2121-101-B-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00355 | 27/06/17 | CRS FOR LABORATORY EQUIPMENT LIST FOR REVAMPING |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-02-SP-0910-03-PA-CRS_3 / 2544-17-SP-1111-04-A-CRS_2 / 2544-17-SP-1111-06-A-CRS_2
Transmittal | MIDOR | 17 | PROCESS | MIDOR-TPIT-T-00359 | 10/07/17 | CRS FOR DATA SHEETS FOR 02-P-04 A/B / 17-STP-15B / 17-STP-56B |  | CLOSED |  | APPROVED/CLOSED 2544-08-SP-4046-01_PA-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00360 | 12/07/17 | CRS FOR DATA SHEET 08-PK-51 |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-NM-1530-06-A-CRS_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00361 | 13/07/17 | CRS FOR TIE IN LIST TELECOM SYSTEMS |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS TPIT-MIDOR-T-2611-CRS-1
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00362 | 13/07/17 | CRS FOR TCF SITE PREPARATION |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-ES-1900-001-CRS_0
Transmittal | MIDOR | 00 | HSE DESIGN | MIDOR-TPIT-T-00363 | 14/07/17 | CRS FOR FIRE FIGHTING EQUIPMENT |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-MR-1531-A-CRS_0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00364 | 14/07/17 | CRS FOR TEMPORARY ACCESS CONTROL & PERSONNEL ON BOARD SYSTEMS |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-EL-001_REV4_CRS-0
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00365 | 14/07/17 | CRS FOR ITEM INDEX REV.4 |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-22-SP-1040-01_PA/PB-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00366 | 18/07/17 | CRS FOR DATA SHEET FOR AIR BLOWER 22-K-01 |  | CLOSED |  | APPROVED/CLOSED 2544-00-JSS-1531-01-A-CRS_0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00368 | 19/07/17 | CRS FOR JOB SPECIFICATION FOR SUPPLY OF TEMPORARY ACCESS CONTROL AND PERSONNEL ON BOARD SYSTEM |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-EL-001_REV 4-CRS_1
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00369 | 19/07/17 | CRS FOR ITEM INDEX REV.4 |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-0A-ES-4065/4118-001-0-CRS_0/2544-0B-ES-0570-003/0630-001-A-CRS_0/2544-0C-ES-0836/0853-001-0-CRS_0/2544-0C-ES-2630-001-B-CRS_0
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00370 | 19/07/17 | CRS FOR PVHE (ENPPI/KT/TPB) |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-19-SP-0910-03_A-CRS_0/2544-19-SP-0910-05_A-CRS-1
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00371 | 26/07/17 | CRS FOR DATA SHEET FOR PUMPS 19-P-09 A/B/19P-04 A/B, 19-P-05 A/B, 19-P0-9 A/B, 19P-13, 19-P-14 |  | CLOSED |  | REVIEW WITH COMMENTS 2544-0A/0B/0C/00-ES-0610-002/0811-002/0841-001/4046-001/2520-402/0844-101/1040-102/2510-102
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00372 | 26/07/17 | CRS FOR PVHE (ENPPI/KT/TPB/TPIT) |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 544-17-SP-0910-04/10/14/15/16/21-A-CRS/2544-47-SP-0910-02-A-CRS
Transmittal | MIDOR | 17 | PROCESS | MIDOR-TPIT-T-00373 | 28/07/17 | CRS FOR DATA SHEET FOR PUMPS 17-P-04/10/14/58/17/55 A/B/47-P-02 |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-PP-811_0-CRS_0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00374 | 28/07/17 | CRS FOR PREPARATION OF CONS,PRECOM QUALITY DOSSIER |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-19-SP-0910-05_A-CRS-2
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00375 | 28/07/17 | CRS FOR DATA SHEET FOR PUMPS 19P-04 A/B, 19-P-05 A/B, 19-P0-9 A/B, 19P-13, 19-P-14 |  | CLOSED |  | REVIEW WITH COMMENTS 2544-0A/0C/00-ES-15XX-YYY-0-CRS_0
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00376 | 03/08/17 | CRS FOR INSTRUMENTATION (ENPPI/KT/TPIT) |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-CBT-0113-301-0-CRS_0/2544-00-CBT-6720-01-0-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00377 | 24/08/17 | CRS FOR REFORME PACKAGE/TRANSPORTATION |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 544-00-JSS-0910-01-3-CRS_0/2544-17-SP-0910-04/10/14/15/16/21/02-A-CRS_2
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00378 | 24/08/17 | CRS FOR GENERAL SPECIFICATION FOR CENTRIFUGAL PUMPS/DATA SHEETS |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-SP-9200-01-1-CRS_0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00379 | 24/08/17 | CRS FOR SPARE PARTS PHILOSOPHY |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-ML-320-10_05_2017-CRS_0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00380 | 29/08/17 | CRS FOR CAPITAL SPARES SUMMARY |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-00-PP-903_C-CRS_0/2544-00-PP-910-A-CRS_0
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00381 | 29/08/17 | CRS FOR HANDOVER / CONSTRUCTION, PRE-COMMISSIONING, START-UP, AND PERFORMANCE TEST SPLIT OF WORK AND RESPONSIBILITY |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-SOW-9000-02_B-CRS-2
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00382 | 31/08/17 | CRS FOR RESPONSABILITY MATRIX FOR SUBCONTRACTOR SOW COMMISIONING |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-00-MS-1393-16_A-CRS_0/2544-20-SP-1111-02_PB-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00383 | 04/09/17 | CRS FOR JOB COMMISSIONING GUIDELINE/PROCESS FRACTIONATOR BOTTOMS |  | CLOSED |  | APPROVED/CLOSED 2544-22-SP-1040-01_PB-CRS_1
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00384 | 05/09/17 | CRS FOR DATA SHEET FOR AIR BLOWER 22-K-01 |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-TBT-0920-001-1_CRS_1
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00385 | 06/09/17 | CRS FOR TECHNICAL BID TABULATION FOR RECIPROCATING PUMPS |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-17-SP-4046-0X_PA-CRS-0/2544-18-SP-0910-07_A-CRS_0
Transmittal | MIDOR | 17 | PACKAGES | MIDOR-TPIT-T-00386 | 07/09/17 | CRS FOR 2544-17-SP- DOSING PACKAGE/DATA SHEET FOR 18-P- 08-A/B EJECTOR RECEIVER |  | CLOSED |  | REVIEW WITH COMMENTS 2544-55-SP-0930-03_PA-CRS_0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00387 | 07/09/17 | CRS FOR DATA SHEET FOR PUMP 55-P-03 |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-00-DS-1663-01-A-CRS_1/2544-00-DW-1622-01-A-CRS_0
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00388 | 07/09/17 | CRS FOR ELECTRICAL MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM-ECMS/U00 MAIN INTERCONNECTING CABLE ROUTING |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-TBT-1684-01-A-CRS_0
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00389 | 07/09/17 | CRS FOR CATHODIC PROTECTION SYSTEM |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-17-SP-0510-05-PA-CRS_0/2544-17-SP-0510-06-PA-CRS_0
Transmittal | MIDOR | 17 | PROCESS | MIDOR-TPIT-T-00392 | 12/09/17 | CRS FOR PROCESS DATA SHEET 17-T05/17-T04 |  | CLOSED |  | REVIEW WITH COMMENTS 2544-54-SP-1040-01_PB-CRS-0
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00393 | 12/09/17 | CRS FOR 54K02C DATA SHEET |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-0A/0B/00-TBT-0511-001/0610-001/0710-001-1-CRS_0
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00394 | 13/09/17 | CRS FOR TECHNICAL BID TABULATION ENPPI/TPB/TPIT |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-0A/00-ES-1518-201/1541/1531/1530/1545/1546/1547/1552-01/02/06/21
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00396 | 15/09/17 | CRS FOR INSTRUMENTATION TPIT/ENPPI |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-0A/0C/00-ES-1562/1565/1585/1553/1554/1564/1565/1566/1572/1574/1575-01/11/06/31
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00397 | 18/09/17 | CRS FOR INSTRUMENTATION TPIT/ENPPI/KT |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-00-TBT-1641/1652/1654/1661-01-A-CRS_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00398 | 19/09/17 | CRS FOR ELECTRICAL TECHNICAL TABULATION |  | CLOSED |  | APPROVED/CLOSED 2544-00-TBT-0570-R02-1-CRS_0/2544-00-TBT-0570-002-1-CRS_0
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00399 | 19/09/17 | CRS FOR TECHNICAL BID TABULATION FOR COLUMNS |  | CLOSED |  | APPROVED/CLOSED 2544-00-PP-919-D-CRS_1
Transmittal | MIDOR | 00 | START UP | MIDOR-TPIT-T-00400 | 19/09/17 | CRS FOR TOOLS AND TEMPORARY EQUIPMENT FOR PRECOMMISSIONING AND COMMISSIONING |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-TBT-4171-101-1-CRS_0/4234-101-0-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00401 | 26/09/17 | CRS FOR TBT FOR PACKAGES |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-RT-1500-06-A-CRS_0
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00402 | 28/09/17 | CRS FOR SSR FOR INSTR EQUIP |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-54-SP-1040-01_PB-CRS-1
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00403 | 02/10/17 | CRS FOR 54K02C DATA SHEET |  | CLOSED |  | REVIEW WITH COMMENTS 2544-0C-PP-800-02_A-CRS-0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00404 | 05/10/17 | CRS FOR SITE ORGANIZATION CHART FOR KT |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-MS-0000-02_D-CRS_0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00405 | 05/10/17 | CRS FOR SPLIT OF SCOPE OF WORK (DIRECT & |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-MR-4110-101-A-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00406 | 06/10/17 | CRS FOR MR FOR MODULAR LPG TREATMENT UNIT 25 |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-0C-TBT-0710-001-1-CRS_0
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00407 | 17/10/17 | CRS FOR TECHNICAL BID TABULATION FOR AIR COOLED HEAT EXCHANGERS (UNITS: 22 & 23) |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-MS-6850-51_0-CRS-0
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00408 | 17/10/17 | CRS FOR JOB CONSTRUCTION SPECIFICATION FOR MACHINERY AND AIR COOLERS INSTALLATION |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-MS-8265-02-A-CRS_1
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00409 | 23/10/17 | CRS FOR TECHNICAL SPECIFICATION FOR NEW ACCESS ROAD AND COMMON UTILITIES NETWORKS |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-0C-NM-1410-01-A-CRS_0
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00410 | 23/10/17 | CRS FOR CIVIL UNDERGROUND TIE-IN LIST |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-JSS-1694-01-A-CRS_0
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00411 | 23/10/17 | CRS FOR GENERAL SUPPLY SPECIFICATION FOR HIGH VOLTAGE VARIABLE FREQUENCY DRIVES |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-0C-NM-1410-01-A-CRS_1
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00412 | 15/11/17 | CRS FOR CIVIL UNDERGROUND TIE-IN LIST |  | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED 2544-0C-TBT-0710-001-1-CRS_1
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00413 | 28/11/17 | CRS FOR TBT FOR AIR COOLED HEAT EXCHANGERS (UNITS 22 & 23) |  | CLOSED |  | APPROVED/CLOSED 2544-0B-TBT-0710-001-1-CRS_1
Transmittal | MIDOR | 00 | HEATERS AND BOILERS | MIDOR-TPIT-T-00415 | 29/11/17 | CRS FOR TBT FOR AIR COOLED HEAT EXCHANGERS (ITEM 21-E-06) |  | CLOSED
Transmittal | MIDOR | 00 | PVHE | MIDOR-TPIT-T-00418 | 30/11/17 | CRS FOR CALCULATION REPORT - REACTOR 08-R-01/02-07/R-01 AND VESSEL 05/V-51 |  | TPIT RESPONSE REQUIRED |  | REWIEV WITH COMMENTS 2544-00-ML-320-CRS_0
Transmittal | MIDOR | 00 | PROJECT MANAGEMENT | MIDOR-TPIT-T-00427 | 18/12/17 | CRS FOR CAPITAL SPARE PARTS |  | TPIT RESPONSE REQUIRED |  | REWIEV WITH COMMENTS 2544-00-ML-320-CRS_0
Transmittal | MIDOR | 00 | CONSTRUCTION | MIDOR-TPIT-T-00430 | 2018-01-08 | CRS FOR CONSTRUCTION COST SUMMARY |  | TPIT RESPONSE REQUIRED |  | REWIEV WITH COMMENTS 2544-00-TBT-4110-101-0-CRS_0
Transmittal | MIDOR | 00 | PACKAGES | MIDOR-TPIT-T-00431 | 12/01/18 | CRS FOR TBT FOR MODULAR LPG TREATMENT UNIT 25 OBE PURPOSE |  | TPIT RESPONSE REQUIRED |  | APPROVED 2544-0C-NM-1410-01-A-CRS_2
Transmittal | MIDOR | 00 | CIVIL | MIDOR-TPIT-T-00432 | 2018-01-16 | CRS FOR TBT FOR CIVIL UNDERGROUND TIE-IN LIST |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-QCP-6800-51_C_CRS_0
Transmittal | MIDOR | 00 | MECHNICAL | MIDOR-TPIT-T-00433 | 2018-01-30 | CRS FOR MECHANICAL PRE-COMMISSIONING QUALITY |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-15-PFD-0010-01-01-D_CRS_0
Transmittal | MIDOR | 15 | PROCESS | MIDOR-TPIT-T-00434 | 2018-01-31 | CRS FOR PFD 01-01 UNIT 15 |  | TPIT RESPONSE REQUIRED |  | APPROVED 2544-00-ML-320-ATT24.28&29/30&31-CRS_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00435 | 2018-02-08 | CRS FOR PBE REPORT -ML-320- ELECTRICAL PRICED DETAILS AND COST SUMMARY TPIT |  | CLOSED |  | APPROVED 2544-00-JSS-1694-01-A-CRS_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00436 | 2018-02-12 | CRS FOR GENERAL SUPPLY SPECIFICATION FOR HIGH VOLTAGE VARIABLE FREQUENCY DRIVES |  | CLOSED |  | APPROVED 2544-00-ML-320-ATT24.07/09/10/12/13/15/16/61/62/63-CRS_1
Transmittal | MIDOR | 00 | MECHNICAL | MIDOR-TPIT-T-00437 | 2018-02-12 | CRS FOR MECHANICAL EQUIP SUMMARY AND TRANSPORTATION DETAILS |  | CLOSED |  | REVIEW WITH COMMENTS 2544-00-ML-320-ATT24.08/11/14/17/18/19/20/21/22/23/24/25/39-CRS_1
Transmittal | MIDOR | 00 | MECHNICAL | MIDOR-TPIT-T-00438 | 2018-02-12 | CRS FOR MECHANICAL EQUIP PRICED DETAILS AND PIPING COST SUMMARY/DETAILS |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-ML-320-CAPITAL SPARE PARTS/ATT24.47-CRS_1
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00439 | 2018-02-13 | CRS FOR CAPITAL SPARE PARTS AND VENDOR REPRESENTATIVES COST SUMMARY |  | TPIT RESPONSE REQUIRED |  | REVIEW WITH COMMENTS 2544-00-JSD-0001-01-B-CRS_0
Transmittal | MIDOR | 00 | MECHNICAL | MIDOR-TPIT-T-00440 | 2018-02-14 | CRS FOR UNIT 54,55 DESIGN BASIS |  | TPIT RESPONSE REQUIRED |  | APPROVED 2544-00-ML-320-ATT24.06-CRS_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00441 | 2018-02-15 | CRS FOR MECHANICAL EQUIP SUMMARY TPIT |  | CLOSED |  | APPROVED 2544-00-MR-1621/2544-00-MR-1671-01/2544-00-MR-1672-01
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00442 | 2018-02-19 | CRS FOR ELECTRICAL MR-1621/1671/1672 |  | CLOSED |  | REVIEWED WITH COMMENTS
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00443 | 2018-02-19 | CRS FOR F&G TECHNICAL TABULATION |  | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00444 | 2018-02-19 | CRS FOR PP-817/818/859/860 REV A AND TBT 4110-101_0 |  | TPIT RESPONSE REQUIRED |  | CLOSED APPROVED 2544-00-DW-1622-04-A-CRS-REPLY_1 AND 2544-21-AA-1442-01-A-CRS-REPLY_1
Transmittal | MIDOR | 00 | ELECTRICAL | MIDOR-TPIT-T-00445 | 2018-02-21 | CRS FOR DW-1622-04_A & 21-AA-1442-01-A |  | CLOSED |  | REVIEWED WITH COMMENTS
Transmittal | MIDOR | 15 | HSE DESIGN | MIDOR-TPIT-T-00446 | 2018-02-21 | CRS FOR 21-DW-1920-01-01-D-CRS_0 | REF.: TPIT-MIDOR-T-02837 | TPIT RESPONSE REQUIRED |  | REVIEWED WITH COMMENTS
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00447 | 2018-02-21 | CRS FOR 2544-00-MS-6850-51-0-CRS_1 | REF.: TPIT-MIDOR-T-00308 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 21 | PROCESS | MIDOR-TPIT-T-00448 | 2018-02-26 | CRS FOR PFD-0010-01-01_D UNIT 15 SOUR WATER STRIPPER | REF.: TPIT-MIDOR-T-02849 | CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00449 | 2018-03-02 | CRS FOR PP-817 ENERGY ISOLATIONLOCK OUT AND TAG OUT PROCEDURE | REF.: TPIT-MIDOR-T-02715 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00450 | 2018-03-05 | CRS FOR U -21 AREA CLASSIFICATION LAYOUT | REF.: TPIT-MIDOR-T-02837 | CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00451 | 2018-03-06 | CRS FOR 05 & 08 PLOT PLAN UNITS | REF.: TPIT-MIDOR-T- 02860/02861 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00452 | 2018-03-07 | CRS FOR TRANSPORTATION SUMMARY ALL 2544-00-ML-320 | REF.: TPIT-MIDOR-T-02793 | CLOSED
Transmittal | MIDOR | 00 | INSTRUMENTATION | MIDOR-TPIT-T-00453 | 2018-03-07 | CRS FOR CBT 1515-001 DISTRIBUTED CONTROL SYSTEM (DCS) | REF.: 2544-00-CBT-1515-001 | CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00454 | 2018-03-12 | CRS FOR PIPING COST SUMMARY TPIT/ENPPI/KT/TPB | REF.: TPIT-MIDOR-T-02793 | CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00455 | 2018-03-12 | CRS FOR F&G TECHNICAL BID TABULATION TBT-1515-002 | REF.: TPIT-MIDOR-T-02858 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00456 | 2018-03-15 | CRS FOR CONSTRUCTION SUMMARY AND DETAILS TPIT/ENPPI | REF.: TPIT-MIDOR-T-02793 | CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00457 | 2018-03-15 | CRS FOR CONSTRUCTION COST SUMMARY AND DETAILS KT/TPB | REF.: TPIT-MIDOR-T-02793 | CLOSED
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00458 | 2018-03-19 | CRS FOR CAP SPARE PARTS/TCF COST SUMMARY AND EQUIP PRICE DETA | REF.: TPIT-MIDOR-T-02793 | CLOSED
Transmittal | MIDOR | 00 | MACHINERY | MIDOR-TPIT-T-00459 | 2018-03-21 | CRS FOR CBT MACHINE MONITORING SYSTEM UNIT 00/0A | REF.:0A-CBT-1515-003_1/CBT-00-1515-003_0 | CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00460 | 2018-03-22 | CRS FOR UNIT 54-55 DESIGN BASIS | REF.:ARRIVED BEFORE OFFICIAL ISSUE | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00461 | 2018-03-22 | CRS FOR GENE SPECFOR RECIPROCATING COMPRESSORS FOR AUXILIARY SERVICES | REF.:TPIT-MIDOR-T-02872 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00462 | 2018-03-28 | CRS FOR MR 4110-101 MODULAR LPG TREATMENT UNIT 25 | REF.:TPIT-MIDOR-T-02710 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00463 | 2018-04-05 | CRS FOR DW-0051 UNITS 05 & 08 | REF.:TPIT-MIDOR-T-02860/2861 | CLOSED
Transmittal | MIDOR | 00 | CHEMICAL | MIDOR-TPIT-T-00464 | 2018-04-05 | CRS FOR CHEMICALS,CATALYST INERTS & LUBRICANTS LIST | REF.:TPIT-MIDOR-T-02889 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00465 | 2018-04-05 | CRS FOR UNITS 54,55 DESIGN BASIS | REF.:TPIT-MIDOR-T-03584 | CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00466 | 2018-04-09 | CRS FOR TBT 4110-101 MODULAR LPG TREATMENT UNIT 25 | REF.:TPIT-MIDOR-T-02710 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00467 | 2018-04-10 | CRS FOR ITEM INDEX REV 4 | REF.:TPIT-MIDOR-T-02621 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00468 | 2018-04-11 | CRS FOR ITEM INDEX REV 4 | REF.:TPIT-MIDOR-T-02621 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 | PROCESS | MIDOR-TPIT-T-00469 | 2018-04-18 | CRS FOR PROCESS HAZARDS ANALYSIS PROCEDURES | REF.:TPIT-MIDOR-T-02893 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 25 |  | MIDOR-TPIT-T-00470 | 2018-05-24 | CRS FOR FORTBT MODULAR LPG TREATEMENT UNIT (UNIT 25) OBE PURPOSE | REF.:TPIT-MIDOR-T-02822 | TPIT RESPONSE REQUIRED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00471 | 2018-05-25 | CRS FOR SCHNEIDER DCS OFFER AND THE MATERISL REQUISITION | REF.:TPIT-MIDOR-T-02899 | TPIT RESPONSE REQUIRED |  | APPROVED/CLOSED
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00472 | 2018-07-06 | CRS FOR LPG TREATMENT UNITS - CBT 4110-101 | REF.: |  |  | APPROVED/CLOSED 2544-00-TBT-1515-002-01-CRS_3
Transmittal | MIDOR | 00 |  | MIDOR-TPIT-T-00473 | 2018-07-24 | CRS FOR F&G TECHNICAL TABULATION | REF.:TPIT-MIDOR-T-02858